# CASEY Strategic Board Intelligence Pack

Rail / Transit scenario view: Base. CASEY indicates $7.4B P50 exposure, $6.2B - $10.9B range, 90 months baseline, Medium-High risk and 69% confidence. Confidence is governed by possessions, signalling integration, systems migration and operator acceptance. Trade-off: Balanced cost, time and evidence posture.

# CASEY Position

CASEY POSITION

CASEY does not judge Rail Infrastructure on headline progress alone.

The programme should be governed through possessions, signalling integration, migration sequencing and trial operations. Current confidence (69%) is a board-defensibility signal, not an optimism score. Risk posture is Medium-High; approval should be conditional until evidence proves the governing constraint is controlled.

If management cannot evidence this constraint, the programme is not approval-ready; it is only reportable.

# Traditional Controls vs CASEY

TRADITIONAL CONTROLS VS CASEY

Traditional controls view:
Civil works and corridor progress look reportable.

CASEY view:
Operational migration, possessions and signalling assurance govern opening confidence.

Why this matters:
Traditional reporting can remain green while confidence is already deteriorating. CASEY reads the behaviour underneath the dashboard: evidence maturity, governing constraint exposure, and whether float/reserve are actually usable.

# Likely Board Attacks

1. Which possessions are truly executable rather than assumed?

2. What evidence proves signalling migration readiness?

3. Where is rolling-stock interface liability owned?

4. What trial-running gate will fail first?

5. Is float usable under live corridor access constraints?

# What The Board Is Really Deciding

WHAT THE BOARD IS REALLY DECIDING

The board is not simply approving cost and schedule.

The board is accepting:
- exposure to possessions, signalling integration, migration sequencing and trial operations
- the current evidence maturity position
- whether reserve is credible against P80/P90 behaviour
- whether management can recover if the governing constraint slips

Evidence required before unconditional approval:
- signed possession strategy
- signalling integration test plan
- rolling-stock interface evidence
- trial running readiness gate
- operator acceptance criteria

CASEY POSITION
Approval should be conditional. Confidence improvement requires evidence closure, not a more polished narrative.

# If This Programme Fails

IF THIS PROGRAMME FAILS

The most likely external explanation will be:
"systems integration and possession access failed to mature before trial running and regulator acceptance."

The internal explanation will be sharper:
Management treated reported progress as equivalent to board-defensible readiness.

CASEY WARNING
The failure mode is behavioural before it is numerical: optimism, weak evidence closure, and late recognition of the governing constraint.

# Intervention Intelligence

INTERVENTION INTELLIGENCE

The highest-value intervention is not another status pack.

1. Prove possessions, signalling integration, migration sequencing and trial operations with auditable evidence.
2. Convert the weakest assumption into an owned mitigation with trigger, date, owner and residual exposure.
3. Re-run P80/P90 after evidence closure, not after narrative revision.

Fastest confidence unlock:
Close the first missing evidence item: signed possession strategy.

CASEY POSITION
The programme needs targeted evidence closure where confidence is actually governed.

# Core Metrics

| Metric | Value |
| --- | --- |
| Cost P50 | $7.4B |
| Cost Range | $6.2B - $10.9B |
| Schedule | 90 months |
| Risk | Medium-High |
| Confidence | 69% |
| Sector Ontology | Rail / Transit |

# Top Risks

R-002 Market escalation — Early procurement, index-linked allowances, market testing, FX strategy

R-004 Design maturity gap — Design maturity gates, independent review, assumption register

R-001 Scope growth — Freeze scope baseline, change board, value gates, client decision log

R-006 Productivity underperformance — Package productivity controls, daily planning, earned value cadence

R-005 Supply chain delay — Alternate suppliers, early orders, expediting, framework options

R-008 Interface misalignment — Interface control documents, weekly interface board, accountable owners

R-007 Commissioning delay — Commissioning readiness plan, early test packs, digital systems integration

R-003 Permits / approvals delay — Authority plan, consent tracker, early submissions, stakeholder map