## 00 Executive Dashboard
CASEY - EXECUTIVE PROJECT CONTROLS INTELLIGENCE
Board-ready first-pass cost, schedule, risk and confidence model generated from a single connected project basis.
Project | Airport Infrastructure | Sector | Airport / Aviation | Scenario | Faster | Generated | 2026-05-04 21:32 UTC
P10 Cost |  | P50 Cost |  | P90 Cost |  | QCRA P80
$9.2B |  | $11.5B |  | $14.9B |  | $17.9B
Schedule |  | QSRA P80 |  | Risk |  | Confidence
85 months |  | 102.19 months |  | Medium |  | 59%
Direct |  | Indirect |  | Reserve
$11.6B |  | $2.0B |  | $1.0B
Executive Summary
Airport Infrastructure has been classified as Airport / Aviation in Global / Not specified. CASEY estimates $11.5B P50 cost, $9.2B to $14.9B range, 85 month baseline, Medium risk and 59% confidence under the Faster scenario.
Board Recommendation
1 | Acceleration selected: schedule compression is funded through logistics premium, parallel procurement and higher delivery intensity.
2 | Controls consequence: QSRA risk should be watched closely because interface density and commissioning pressure rise.
3 | Board decision: approve acceleration only with package-level recovery plan and explicit acceleration cost allowance.
4 | Run a risk workshop to validate probability and O/M/P impacts.
5 | Confirm top five CBS cost drivers with benchmark or supplier evidence.
6 | Validate the Level 3/4 schedule logic and critical path assumptions.
7 | Prepare board decision paper with Base/Faster/Cheaper/Lower-Risk cases.
8 | Create confidence improvement plan targeting design maturity, consents and procurement evidence.
Cost Composition
Type | P50 BN
Direct | 11.603
Indirect | 1.953
Reserve | 1.034

## 01 Basis
BASIS OF ESTIMATE AND CONTROL MODEL
Traceability page: no board output should be read without understanding the class, maturity, location, scenario and assumptions.
Input | Value
Prompt | Modern airport expansion with terminal, runway, baggage systems and live operations
Client | Airport Owner
Mode | Earth
Sector | Airport / Aviation
Location | Global / Not specified
Scale | Project
Estimate class | Class 3 Budget Authorization
Estimate maturity | 10-40% definition maturity
Schedule level | 4
Scenario | Faster
Scenario rationale | Parallel design/procurement, acceleration, premium logistics and higher interface risk.
Confidence Explanation
• | Class 3 Budget Authorization: 10-40% definition maturity drives the starting confidence level.
• | Schedule Level 4: more detailed schedule logic improves QSRA traceability.
• | Faster: Parallel design/procurement, acceleration, premium logistics and higher interface risk.
• | Location/space factor: Global / Not specified applies a 1.00 delivery premium.
• | live environment

## 02 Cost Estimate
SELECTED CLASS COST ESTIMATE - DIRECT / INDIRECT / RESERVE
Only the selected class estimate is exported. P10 / P50 / P90 and direct / indirect / reserve are visible and auditable.
CBS | Description | Type | Basis | P10 BN | P50 BN | P90 BN | Min BN | Most Likely BN | Max BN | Scenario Impact | Evidence / Challenge
01.01 | Site Preparation / Enabling | Direct | Demolition, enabling, logistics and access | 0.551 | 0.689 | 0.896 | 0.551 | 0.689 | 0.896 | Faster | Site Preparation / Enabling priced as 6.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
01.02 | Substructure / Foundations | Direct | Piling, groundworks, retaining and foundations | 0.735 | 0.919 | 1.195 | 0.735 | 0.919 | 1.195 | Faster | Substructure / Foundations priced as 8.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
01.03 | Superstructure / Civil Works | Direct | Frame, civils, primary structures | 1.287 | 1.608 | 2.091 | 1.287 | 1.608 | 2.091 | Faster | Superstructure / Civil Works priced as 14.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
01.04 | MEP / Systems / Utilities | Direct | Mechanical, electrical, controls and utilities | 1.287 | 1.608 | 2.091 | 1.287 | 1.608 | 2.091 | Faster | MEP / Systems / Utilities priced as 14.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
01.05 | Specialist Equipment / Fit-Out | Direct | Permanent equipment and specialist fit-out | 1.103 | 1.379 | 1.792 | 1.103 | 1.379 | 1.792 | Faster | Specialist Equipment / Fit-Out priced as 12.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
01.06 | Airfield Works | Direct | Runway, taxiway, apron and airfield systems | 1.287 | 1.608 | 2.091 | 1.287 | 1.608 | 2.091 | Faster | Airfield Works priced as 14.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
01.07 | Terminal / Passenger Systems | Direct | Terminal, baggage, security and passenger systems | 0.919 | 1.149 | 1.494 | 0.919 | 1.149 | 1.494 | Faster | Terminal / Passenger Systems priced as 10.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
01.09 | Direct Labour | Direct | Productivity, supervision and trade labour | 0.827 | 1.034 | 1.344 | 0.827 | 1.034 | 1.344 | Faster | Direct Labour priced as 9.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
01.10 | Direct Materials | Direct | Concrete, steel, envelope, MEP materials | 0.919 | 1.149 | 1.494 | 0.919 | 1.149 | 1.494 | Faster | Direct Materials priced as 10.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
01.11 | Plant / Equipment | Direct | Cranes, heavy plant and site equipment | 0.368 | 0.46 | 0.597 | 0.368 | 0.46 | 0.597 | Faster | Plant / Equipment priced as 4.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
02.01 | General Conditions / Prelims | Indirect | Site management, safety, offices and temporary services | 0.643 | 0.804 | 1.045 | 0.643 | 0.804 | 1.045 | Faster | General Conditions / Prelims priced as 7.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
02.02 | Design / Professional Fees | Indirect | Design, QS, controls, assurance and consultants | 0.643 | 0.804 | 1.045 | 0.643 | 0.804 | 1.045 | Faster | Design / Professional Fees priced as 7.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
02.03 | Permits / Insurance / Bonds | Indirect | Permits, inspections, legal, bonds and insurance | 0.276 | 0.345 | 0.448 | 0.276 | 0.345 | 0.448 | Faster | Permits / Insurance / Bonds priced as 3.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
03.01 | QCRA Contingency | Reserve | Known-unknown risk allowance | 0.551 | 0.689 | 0.896 | 0.551 | 0.689 | 0.896 | Faster | QCRA Contingency priced as 6.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
03.02 | Management Reserve | Reserve | Sponsor-held reserve | 0.276 | 0.345 | 0.448 | 0.276 | 0.345 | 0.448 | Faster | Management Reserve priced as 3.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15.
Type | P50 BN | Share
Direct | 11.603
Indirect | 1.953
Reserve | 1.034

## 03 Indirects & Reserves
INDIRECTS, CONTINGENCY AND RESERVE ASSURANCE
Separates project delivery cost from sponsor-held uncertainty and contingency.
CBS | Description | Type | P10 BN | P50 BN | P90 BN | Assurance Question | Board Treatment
02.01 | General Conditions / Prelims | Indirect | 0.643 | 0.804 | 1.045 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.
02.02 | Design / Professional Fees | Indirect | 0.643 | 0.804 | 1.045 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.
02.03 | Permits / Insurance / Bonds | Indirect | 0.276 | 0.345 | 0.448 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.
03.01 | QCRA Contingency | Reserve | 0.551 | 0.689 | 0.896 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.
03.02 | Management Reserve | Reserve | 0.276 | 0.345 | 0.448 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.

## 04 QCRA
QCRA COST RISK ANALYSIS
Cost curve and separate tornado drivers. QCRA is not mixed with QSRA.
Percentile | Cost BN | Schedule Months | Rank | Driver | CBS | Mean BN | Score | Board Challenge
1 | 12.252 | 85.53 | 1 | Market escalation | 01.07 | 0.735 | 73.51 | Request evidence for cost range and owner-retained exposure.
5 | 13.28 | 88.44 | 2 | Operational phasing disruption | 01.04 | 0.567 | 56.71 | Request evidence for cost range and owner-retained exposure.
10 | 13.901 | 90.21 | 3 | Scope growth | 01.06 | 0.541 | 54.14 | Request evidence for cost range and owner-retained exposure.
20 | 14.662 | 92.53 | 4 | Design maturity gap | 01.10 | 0.532 | 53.19 | Request evidence for cost range and owner-retained exposure.
30 | 15.226 | 94.15 | 5 | Supply chain delay | 01.11 | 0.463 | 46.27 | Request evidence for cost range and owner-retained exposure.
40 | 15.735 | 95.64 | 6 | Productivity underperformance | 02.01 | 0.453 | 45.32 | Request evidence for cost range and owner-retained exposure.
50 | 16.226 | 97.1 | 7 | Baggage / security systems integration | 01.05 | 0.396 | 39.58 | Request evidence for cost range and owner-retained exposure.
60 | 16.73 | 98.59 | 8 | Interface misalignment | 02.03 | 0.372 | 37.2 | Request evidence for cost range and owner-retained exposure.
70 | 17.277 | 100.24 | 9 | Commissioning delay | 02.02 | 0.303 | 30.25 | Request evidence for cost range and owner-retained exposure.
80 | 17.889 | 102.19 | 10 | Permits / approvals delay | 01.09 | 0.217 | 21.67 | Request evidence for cost range and owner-retained exposure.
90 | 18.783 | 104.98
95 | 19.523 | 107.22
99 | 21.003 | 111.34

## 05 QSRA
QSRA SCHEDULE RISK ANALYSIS
Schedule curve and separate tornado drivers. QSRA is not mixed with QCRA.
Percentile | Schedule Months | Cost BN | Rank | Driver | Activity | Mean Days | Score | Recovery / Mitigation Challenge
1 | 85.53 | 12.252 | 1 | Operational phasing disruption | A1400 | 50.9 | 25.47 | Confirm critical path logic, float erosion and recovery option.
5 | 88.44 | 13.28 | 2 | Permits / approvals delay | A1800 | 45.4 | 22.68 | Confirm critical path logic, float erosion and recovery option.
10 | 90.21 | 13.901 | 3 | Scope growth | A1600 | 37 | 18.49 | Confirm critical path logic, float erosion and recovery option.
20 | 92.53 | 14.662 | 4 | Supply chain delay | A2000 | 33.5 | 16.74 | Confirm critical path logic, float erosion and recovery option.
30 | 94.15 | 15.226 | 5 | Productivity underperformance | A2100 | 33.2 | 16.61 | Confirm critical path logic, float erosion and recovery option.
40 | 95.64 | 15.735 | 6 | Design maturity gap | A1900 | 32.4 | 16.2 | Confirm critical path logic, float erosion and recovery option.
50 | 97.1 | 16.226 | 7 | Baggage / security systems integration | A1500 | 30.8 | 15.38 | Confirm critical path logic, float erosion and recovery option.
60 | 98.59 | 16.73 | 8 | Interface misalignment | P2000 | 23.6 | 11.79 | Confirm critical path logic, float erosion and recovery option.
70 | 100.24 | 17.277 | 9 | Commissioning delay | P1000 | 22.2 | 11.11 | Confirm critical path logic, float erosion and recovery option.
80 | 102.19 | 17.889 | 10 | Market escalation | A1700 | 0 | 0 | Confirm critical path logic, float erosion and recovery option.
90 | 104.98 | 18.783
95 | 107.22 | 19.523
99 | 111.34 | 21.003

## 06 Risk Register
RISK REGISTER PRO - CAUSE / EVENT / IMPACT / RESPONSE
Board-grade register with quantified cost and schedule exposure, owners and linked WBS/CBS.
Risk ID | Category | Title | Cause | Risk Event | Impact Description | Probability % | Cost O BN | Cost M BN | Cost P BN | Cost EMV BN | Schedule O Days | Schedule M Days | Schedule P Days | Schedule EMV Days | Activity | CBS | Owner | Trigger | Mitigation | Response Strategy | Residual | Status | Board
R-002 | Commercial | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | 53 | 0.46 | 1.218 | 2.482 | 0.645 | 0 | 0 | 0 | 0 | A1700 | 01.07 | Commercial Lead | Index exceeds allowance by 3% | Early procurement, index-linked allowances, market testing, FX strategy | Mitigate | Medium | Open | Yes
R-A01 | Operations | Operational phasing disruption | Works in or near live airport operations constrain access and sequencing | Operational restrictions reduce productive windows | Delay, night-work premiums, stakeholder disruption and ORAT pressure | 49 | 0.287 | 0.974 | 2.233 | 0.477 | 20 | 85 | 205 | 41.6 | A1400 | 01.04 | ORAT Lead | Possession windows rejected | Phasing simulation, possession plan, airport ops integration board | Mitigate | Medium | Open | Yes
R-001 | Scope | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | 49 | 0.345 | 0.974 | 1.985 | 0.477 | 15 | 55 | 154 | 26.9 | A1600 | 01.06 | Project Director | Scope change rate exceeds 2% of package value | Freeze scope baseline, change board, value gates, client decision log | Reduce | Low | Open | Yes
R-004 | Technical | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | 44 | 0.345 | 1.096 | 2.233 | 0.482 | 15 | 55 | 154 | 24.2 | A1900 | 01.10 | Design Manager | Design deliverables miss maturity gate | Design maturity gates, independent review, assumption register | Reduce | Low | Open | Yes
R-006 | Delivery | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | 41 | 0.345 | 0.974 | 1.985 | 0.399 | 15 | 61 | 166 | 25 | A2100 | 02.01 | Delivery Lead | SPI/CPI deteriorates for two reporting periods | Package productivity controls, daily planning, earned value cadence | Mitigate | Low | Open | Yes
R-005 | Procurement | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | 47 | 0.23 | 0.852 | 1.861 | 0.401 | 10 | 49 | 154 | 23 | A2000 | 01.11 | Procurement Lead | Supplier promise date slips | Alternate suppliers, early orders, expediting, framework options | Transfer / Mitigate | Low | Open | Yes
R-A02 | Systems | Baggage / security systems integration | Complex passenger systems integration and vendor interfaces uncertain | Integrated airport systems do not pass readiness testing | Commissioning delay, passenger disruption and late operational readiness | 40 | 0.23 | 0.852 | 1.861 | 0.341 | 15 | 61 | 154 | 24.4 | A1500 | 01.05 | Systems Lead | FAT/SAT defect trend above threshold | Factory acceptance testing, integration lab, ORAT dry-runs | Reduce | Low | Open | Yes
R-008 | Integration | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | 40 | 0.23 | 0.852 | 1.737 | 0.341 | 10 | 43 | 128 | 17.2 | P2000 | 02.03 | Integration Manager | Interface actions overdue | Interface control documents, weekly interface board, accountable owners | Mitigate | Low | Open | No
R-007 | Handover | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | 37 | 0.23 | 0.731 | 1.489 | 0.27 | 10 | 43 | 128 | 15.9 | P1000 | 02.02 | Commissioning Lead | Test failures trend upward | Commissioning readiness plan, early test packs, digital systems integration | Reduce | Low | Open | No
R-003 | Regulatory | Permits / approvals delay | Authority process, stakeholder objections or incomplete submissions | Consent milestone slips beyond baseline | Critical path delay, extended preliminaries and potential redesign conditions | 41 | 0.115 | 0.487 | 0.993 | 0.2 | 20 | 85 | 230 | 34.9 | A1800 | 01.09 | Consents Lead | Consent milestone slips by 30 days | Authority plan, consent tracker, early submissions, stakeholder map | Mitigate | Low | Open | Yes

## 07 Schedule
SCHEDULE LOGIC - LEVEL SELECTED
Linked schedule activities for QSRA and export to P6/XER.
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis | Risk Links
A1000 | Governance | Project initiation / controls setup |  | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-A01
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-A02
A1600 | Design | Detailed design / IFC development | A1300 | 8 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-001
A1700 | Procurement | Long-lead procurement | A1500 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-002
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-003
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 19 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-004
A2000 | Integration | Systems integration and testing | A1900 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-005
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-006
P1000 | Package | Airfield works | A1900 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-007
P2000 | Package | Terminal systems | P1000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-008
P3000 | Package | Baggage/security systems | P2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4000 | Package | ORAT | P3000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## 08 Scenarios
SCENARIO COMPARISON - BASE / FASTER / CHEAPER / LOWER RISK / PREMIUM
Scenario choice must change cost, schedule, risk and confidence.
Scenario | P50 Cost | Schedule | Risk | Confidence | Cost Change Logic | Schedule Change Logic | Risk Logic
base |  |  | Medium | 64 | Balanced reference case.
faster |  |  | Medium | 59 | Parallel design/procurement, acceleration, premium logistics and higher interface risk.
cheaper |  |  | Medium | 58 | Value engineering, tighter scope and procurement competition, with schedule/quality exposure.
lower_risk |  |  | Low | 77 | More surveys, assurance, stage gates, contingency and schedule buffers.
premium |  |  | Low | 80 | Best assurance, independent review, early procurement and high-confidence governance.
investor |  |  | Low | 71 | Investment-framing case with transparent risk and commercial challenge.
survival |  |  | Medium | 54 | Minimum viable scope, warning-heavy, high residual risk.

## 09 Benchmarking
BENCHMARKING AND PEER CHALLENGE
Use to challenge Tier 1 contractor estimates, market rates and sponsor assumptions.
Benchmark / Peer | What to compare | Why it matters | Challenge question | Evidence required
Dubai Airports | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log
Heathrow operators | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log
Changi Airport Group | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log
AD Airports | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log
Saudi airport programmes | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log

## 10 Assumptions
ASSUMPTIONS, LIMITATIONS AND DECISION GATES
Makes the output honest: a first-pass project controls intelligence pack, not a final tender estimate.
Area | Assumption / Limitation | Board Action
Estimate | Class 3 Budget Authorization with 10-40% definition maturity; not a contractor tender price. | Use to challenge, shortlist and frame approval gates.
Schedule | Level 4 logic; critical path and float require validation against project-specific constraints. | Run schedule risk workshop and validate dependencies.
Risk | QCRA and QSRA distributions are modelled from the generated register and selected scenario. | Replace assumptions with workshop data as evidence improves.
Scenario | Parallel design/procurement, acceleration, premium logistics and higher interface risk. | Compare Base / Faster / Cheaper / Lower Risk before board decision.
Outputs | Exports are board-preparation outputs and should be reviewed before external release. | Apply owner governance, sign-off and evidence checks.