# CASEY Executive Board Intelligence Pack

Airport Infrastructure | Airport / Aviation | Faster scenario | Generated 2026-05-04 21:32 UTC

Airport Infrastructure has been classified as Airport / Aviation in Global / Not specified. CASEY estimates $11.5B P50 cost, $9.2B to $14.9B range, 85 month baseline, Medium risk and 59% confidence under the Faster scenario.

# 1. Board Decision Snapshot

| Metric | Value | Interpretation | Board Action |
| --- | --- | --- | --- |
| P50 Cost | $11.5B | Most likely first-pass cost based on selected class and scenario. | Use as initial investment control point. |
| Cost Range | $9.2B - $14.9B | Class/maturity and QCRA uncertainty range. | Do not approve without range acknowledgement. |
| QCRA P80 | $17.9B | Risk-adjusted cost confidence level. | Set funding envelope and contingency rules. |
| Baseline / QSRA P80 | 85 months / 102.19 months | Schedule risk exposure and delivery confidence. | Require critical path validation. |
| Risk / Confidence | Medium / 59% | Early-stage confidence and data quality status. | Approve evidence-improvement plan. |
| Direct / Indirect / Reserve | $11.6B / $2.0B / $1.0B | Prevents reserves being hidden inside direct cost. | Challenge contractor and adviser basis. |

# 2. Executive Recommendation

Acceleration selected: schedule compression is funded through logistics premium, parallel procurement and higher delivery intensity.

Controls consequence: QSRA risk should be watched closely because interface density and commissioning pressure rise.

Board decision: approve acceleration only with package-level recovery plan and explicit acceleration cost allowance.

Run a risk workshop to validate probability and O/M/P impacts.

Confirm top five CBS cost drivers with benchmark or supplier evidence.

Validate the Level 3/4 schedule logic and critical path assumptions.

Prepare board decision paper with Base/Faster/Cheaper/Lower-Risk cases.

Create confidence improvement plan targeting design maturity, consents and procurement evidence.

# 3. Cost Estimate - Selected Class Only

| CBS | Description | Type | P10 | P50 | P90 | Basis |
| --- | --- | --- | --- | --- | --- | --- |
| 01.01 | Site Preparation / Enabling | Direct | $551M | $689M | $896M | Site Preparation / Enabling priced as 6.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 01.02 | Substructure / Foundations | Direct | $735M | $919M | $1.2B | Substructure / Foundations priced as 8.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 01.03 | Superstructure / Civil Works | Direct | $1.3B | $1.6B | $2.1B | Superstructure / Civil Works priced as 14.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 01.04 | MEP / Systems / Utilities | Direct | $1.3B | $1.6B | $2.1B | MEP / Systems / Utilities priced as 14.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 01.05 | Specialist Equipment / Fit-Out | Direct | $1.1B | $1.4B | $1.8B | Specialist Equipment / Fit-Out priced as 12.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 01.06 | Airfield Works | Direct | $1.3B | $1.6B | $2.1B | Airfield Works priced as 14.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 01.07 | Terminal / Passenger Systems | Direct | $919M | $1.1B | $1.5B | Terminal / Passenger Systems priced as 10.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 01.09 | Direct Labour | Direct | $827M | $1.0B | $1.3B | Direct Labour priced as 9.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 01.10 | Direct Materials | Direct | $919M | $1.1B | $1.5B | Direct Materials priced as 10.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 01.11 | Plant / Equipment | Direct | $368M | $460M | $597M | Plant / Equipment priced as 4.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 02.01 | General Conditions / Prelims | Indirect | $643M | $804M | $1.0B | General Conditions / Prelims priced as 7.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 02.02 | Design / Professional Fees | Indirect | $643M | $804M | $1.0B | Design / Professional Fees priced as 7.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 02.03 | Permits / Insurance / Bonds | Indirect | $276M | $345M | $448M | Permits / Insurance / Bonds priced as 3.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 03.01 | QCRA Contingency | Reserve | $551M | $689M | $896M | QCRA Contingency priced as 6.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |
| 03.02 | Management Reserve | Reserve | $276M | $345M | $448M | Management Reserve priced as 3.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.15. |

# 4. QCRA and QSRA

QCRA cost P10 / P50 / P80 / P90: $13.9B / $11.5B / $17.9B / $18.8B

QSRA schedule P10 / P50 / P80 / P90: 90.21 / 97.1 / 102.19 / 104.98 months

## 5. QCRA Tornado Drivers

Market escalation - 01.07 - mean exposure $735M

Operational phasing disruption - 01.04 - mean exposure $567M

Scope growth - 01.06 - mean exposure $541M

Design maturity gap - 01.10 - mean exposure $532M

Supply chain delay - 01.11 - mean exposure $463M

Productivity underperformance - 02.01 - mean exposure $453M

Baggage / security systems integration - 01.05 - mean exposure $396M

Interface misalignment - 02.03 - mean exposure $372M

## 6. QSRA Tornado Drivers

Operational phasing disruption - A1400 - mean exposure 50.9 days

Permits / approvals delay - A1800 - mean exposure 45.4 days

Scope growth - A1600 - mean exposure 37.0 days

Supply chain delay - A2000 - mean exposure 33.5 days

Productivity underperformance - A2100 - mean exposure 33.2 days

Design maturity gap - A1900 - mean exposure 32.4 days

Baggage / security systems integration - A1500 - mean exposure 30.8 days

Interface misalignment - P2000 - mean exposure 23.6 days

# 7. Risk Register - Board Top Risks

R-002 Market escalation

Cause: Supplier market tightness, inflation, FX and long procurement window. Event: Rates exceed assumed escalation profile. Impact: P50 cost becomes understated; commercial approvals or procurement strategy may need reset. Mitigation: Early procurement, index-linked allowances, market testing, FX strategy. Owner: Commercial Lead.

R-A01 Operational phasing disruption

Cause: Works in or near live airport operations constrain access and sequencing. Event: Operational restrictions reduce productive windows. Impact: Delay, night-work premiums, stakeholder disruption and ORAT pressure. Mitigation: Phasing simulation, possession plan, airport ops integration board. Owner: ORAT Lead.

R-001 Scope growth

Cause: Ambiguous requirements, immature scope freeze and late stakeholder changes. Event: Approved scope expands after estimate freeze. Impact: Additional quantities, redesign, rework, procurement churn and board contingency drawdown. Mitigation: Freeze scope baseline, change board, value gates, client decision log. Owner: Project Director.

R-004 Design maturity gap

Cause: Estimate is based on immature design, incomplete surveys or unresolved interfaces. Event: Design basis changes during detailed design. Impact: Cost growth, quantity movement, rework and schedule resequencing. Mitigation: Design maturity gates, independent review, assumption register. Owner: Design Manager.

R-006 Productivity underperformance

Cause: Access constraints, poor sequencing, labour scarcity or learning curve. Event: Actual production rates underperform plan. Impact: Extended duration, increased preliminaries and loss of float. Mitigation: Package productivity controls, daily planning, earned value cadence. Owner: Delivery Lead.

R-005 Supply chain delay

Cause: Long-lead equipment, constrained suppliers or late procurement release. Event: Supplier promise dates move right. Impact: Delayed installation, critical path movement and acceleration cost. Mitigation: Alternate suppliers, early orders, expediting, framework options. Owner: Procurement Lead.

R-A02 Baggage / security systems integration

Cause: Complex passenger systems integration and vendor interfaces uncertain. Event: Integrated airport systems do not pass readiness testing. Impact: Commissioning delay, passenger disruption and late operational readiness. Mitigation: Factory acceptance testing, integration lab, ORAT dry-runs. Owner: Systems Lead.

R-008 Interface misalignment

Cause: Multiple contractors, unclear interface ownership or late design coordination. Event: Package interfaces do not align during installation/integration. Impact: Rework, claims, delay and fragmented accountability. Mitigation: Interface control documents, weekly interface board, accountable owners. Owner: Integration Manager.

R-007 Commissioning delay

Cause: Incomplete readiness, software integration issues or defects during testing. Event: Systems fail tests or require repeated commissioning cycles. Impact: Delayed handover, operational readiness slippage and liquidated damages exposure. Mitigation: Commissioning readiness plan, early test packs, digital systems integration. Owner: Commissioning Lead.

R-003 Permits / approvals delay

Cause: Authority process, stakeholder objections or incomplete submissions. Event: Consent milestone slips beyond baseline. Impact: Critical path delay, extended preliminaries and potential redesign conditions. Mitigation: Authority plan, consent tracker, early submissions, stakeholder map. Owner: Consents Lead.

# 8. Challenge Questions

What evidence supports the P50 cost and P80 confidence?

Which five risks create most contingency?

Which activities drive the QSRA finish-date risk?

What data would increase confidence before approval?

What is the fastest credible lower-risk path?

# 9. Assumptions and Limitations

This is a first-pass project controls intelligence pack. It is designed to challenge, accelerate and structure decision-making; it is not a final contractor tender or signed cost plan. Each output includes assumptions and should be validated against project-specific evidence before commitment.