## Risk Dashboard
CASEY RISK REGISTER PRO
Cause - Event - Impact - Response - Quantified cost and schedule exposure.
Risks |  |  | Board Visible |  |  | QCRA P80
10 |  |  | 8 |  |  | $17.9B
QSRA P80 |  |  | Top Risk |  |  | Scenario
102.19 months |  |  | Market escalation |  |  | Faster
Rank | Risk | Cost EMV BN | Schedule EMV Days | Owner | Response
1 | Market escalation | 0.645 | 0 | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy
2 | Operational phasing disruption | 0.477 | 41.6 | ORAT Lead | Phasing simulation, possession plan, airport ops integration board
3 | Scope growth | 0.477 | 26.9 | Project Director | Freeze scope baseline, change board, value gates, client decision log
4 | Design maturity gap | 0.482 | 24.2 | Design Manager | Design maturity gates, independent review, assumption register
5 | Productivity underperformance | 0.399 | 25 | Delivery Lead | Package productivity controls, daily planning, earned value cadence
6 | Supply chain delay | 0.401 | 23 | Procurement Lead | Alternate suppliers, early orders, expediting, framework options
7 | Baggage / security systems integration | 0.341 | 24.4 | Systems Lead | Factory acceptance testing, integration lab, ORAT dry-runs
8 | Interface misalignment | 0.341 | 17.2 | Integration Manager | Interface control documents, weekly interface board, accountable owners
9 | Commissioning delay | 0.27 | 15.9 | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration
10 | Permits / approvals delay | 0.2 | 34.9 | Consents Lead | Authority plan, consent tracker, early submissions, stakeholder map

## Risk Register Pro
FULL RISK REGISTER PRO
Every risk has a cause, event, impact description, owner, response and quantification.
Risk ID | Category | Title | Cause | Risk Event | Impact Description | Probability % | Cost O BN | Cost M BN | Cost P BN | Cost EMV BN | Schedule O Days | Schedule M Days | Schedule P Days | Schedule EMV Days | Activity | CBS | Owner | Trigger | Mitigation | Response Strategy | Residual | Status | Board
R-002 | Commercial | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | 53 | 0.46 | 1.218 | 2.482 | 0.645 | 0 | 0 | 0 | 0 | A1700 | 01.07 | Commercial Lead | Index exceeds allowance by 3% | Early procurement, index-linked allowances, market testing, FX strategy | Mitigate | Medium | Open | Yes
R-A01 | Operations | Operational phasing disruption | Works in or near live airport operations constrain access and sequencing | Operational restrictions reduce productive windows | Delay, night-work premiums, stakeholder disruption and ORAT pressure | 49 | 0.287 | 0.974 | 2.233 | 0.477 | 20 | 85 | 205 | 41.6 | A1400 | 01.04 | ORAT Lead | Possession windows rejected | Phasing simulation, possession plan, airport ops integration board | Mitigate | Medium | Open | Yes
R-001 | Scope | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | 49 | 0.345 | 0.974 | 1.985 | 0.477 | 15 | 55 | 154 | 26.9 | A1600 | 01.06 | Project Director | Scope change rate exceeds 2% of package value | Freeze scope baseline, change board, value gates, client decision log | Reduce | Low | Open | Yes
R-004 | Technical | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | 44 | 0.345 | 1.096 | 2.233 | 0.482 | 15 | 55 | 154 | 24.2 | A1900 | 01.10 | Design Manager | Design deliverables miss maturity gate | Design maturity gates, independent review, assumption register | Reduce | Low | Open | Yes
R-006 | Delivery | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | 41 | 0.345 | 0.974 | 1.985 | 0.399 | 15 | 61 | 166 | 25 | A2100 | 02.01 | Delivery Lead | SPI/CPI deteriorates for two reporting periods | Package productivity controls, daily planning, earned value cadence | Mitigate | Low | Open | Yes
R-005 | Procurement | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | 47 | 0.23 | 0.852 | 1.861 | 0.401 | 10 | 49 | 154 | 23 | A2000 | 01.11 | Procurement Lead | Supplier promise date slips | Alternate suppliers, early orders, expediting, framework options | Transfer / Mitigate | Low | Open | Yes
R-A02 | Systems | Baggage / security systems integration | Complex passenger systems integration and vendor interfaces uncertain | Integrated airport systems do not pass readiness testing | Commissioning delay, passenger disruption and late operational readiness | 40 | 0.23 | 0.852 | 1.861 | 0.341 | 15 | 61 | 154 | 24.4 | A1500 | 01.05 | Systems Lead | FAT/SAT defect trend above threshold | Factory acceptance testing, integration lab, ORAT dry-runs | Reduce | Low | Open | Yes
R-008 | Integration | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | 40 | 0.23 | 0.852 | 1.737 | 0.341 | 10 | 43 | 128 | 17.2 | P2000 | 02.03 | Integration Manager | Interface actions overdue | Interface control documents, weekly interface board, accountable owners | Mitigate | Low | Open | No
R-007 | Handover | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | 37 | 0.23 | 0.731 | 1.489 | 0.27 | 10 | 43 | 128 | 15.9 | P1000 | 02.02 | Commissioning Lead | Test failures trend upward | Commissioning readiness plan, early test packs, digital systems integration | Reduce | Low | Open | No
R-003 | Regulatory | Permits / approvals delay | Authority process, stakeholder objections or incomplete submissions | Consent milestone slips beyond baseline | Critical path delay, extended preliminaries and potential redesign conditions | 41 | 0.115 | 0.487 | 0.993 | 0.2 | 20 | 85 | 230 | 34.9 | A1800 | 01.09 | Consents Lead | Consent milestone slips by 30 days | Authority plan, consent tracker, early submissions, stakeholder map | Mitigate | Low | Open | Yes

## Mitigation Tracker
MITIGATION TRACKER
Owner actions, triggers and residual risk conversion.
Risk ID | Risk | Owner | Mitigation Action | Trigger | Due Gate | Status | Residual | Board | Evidence Needed
R-002 | Market escalation | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy | Index exceeds allowance by 3% | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-A01 | Operational phasing disruption | ORAT Lead | Phasing simulation, possession plan, airport ops integration board | Possession windows rejected | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-001 | Scope growth | Project Director | Freeze scope baseline, change board, value gates, client decision log | Scope change rate exceeds 2% of package value | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log
R-004 | Design maturity gap | Design Manager | Design maturity gates, independent review, assumption register | Design deliverables miss maturity gate | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log
R-006 | Productivity underperformance | Delivery Lead | Package productivity controls, daily planning, earned value cadence | SPI/CPI deteriorates for two reporting periods | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log
R-005 | Supply chain delay | Procurement Lead | Alternate suppliers, early orders, expediting, framework options | Supplier promise date slips | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log
R-A02 | Baggage / security systems integration | Systems Lead | Factory acceptance testing, integration lab, ORAT dry-runs | FAT/SAT defect trend above threshold | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log
R-008 | Interface misalignment | Integration Manager | Interface control documents, weekly interface board, accountable owners | Interface actions overdue | Next gate | Open | Low | No | Named evidence, date, owner and decision log
R-007 | Commissioning delay | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration | Test failures trend upward | Next gate | Open | Low | No | Named evidence, date, owner and decision log
R-003 | Permits / approvals delay | Consents Lead | Authority plan, consent tracker, early submissions, stakeholder map | Consent milestone slips by 30 days | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log

## Board Top 10
BOARD TOP 10 RISKS
The risks most likely to change the investment decision.
Rank | Risk | Cause | Event | Impact | Cost EMV BN | Schedule EMV Days | Board Ask
1 | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | 0.645 | 0 | Approve mitigation spend or request further evidence
2 | Operational phasing disruption | Works in or near live airport operations constrain access and sequencing | Operational restrictions reduce productive windows | Delay, night-work premiums, stakeholder disruption and ORAT pressure | 0.477 | 41.6 | Approve mitigation spend or request further evidence
3 | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | 0.477 | 26.9 | Approve mitigation spend or request further evidence
4 | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | 0.482 | 24.2 | Approve mitigation spend or request further evidence
5 | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | 0.399 | 25 | Approve mitigation spend or request further evidence
6 | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | 0.401 | 23 | Approve mitigation spend or request further evidence
7 | Baggage / security systems integration | Complex passenger systems integration and vendor interfaces uncertain | Integrated airport systems do not pass readiness testing | Commissioning delay, passenger disruption and late operational readiness | 0.341 | 24.4 | Approve mitigation spend or request further evidence
8 | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | 0.341 | 17.2 | Approve mitigation spend or request further evidence
9 | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | 0.27 | 15.9 | Approve mitigation spend or request further evidence
10 | Permits / approvals delay | Authority process, stakeholder objections or incomplete submissions | Consent milestone slips beyond baseline | Critical path delay, extended preliminaries and potential redesign conditions | 0.2 | 34.9 | Approve mitigation spend or request further evidence