## Slide 1
CASEY
Mission Control for Capital Projects
AI Data Centre Campus has been classified as Digital Infrastructure / Hyperscale Data Centre in Saudi Arabia / GCC. CASEY estimates $10.7B P50 cost, $8.6B to $13.9B range, 64 month baseline, Medium risk and 64% confidence under the Base scenario.

## Slide 2
CASEY
Board Decision Snapshot
AI Data Centre Campus | Base scenario
P50
$10.7B
P80 Cost
$16.3B
Schedule
64 months
QSRA P80
77.61 mo
Risk
Medium
Confidence
64%
Direct
$12.7B
Indirect
$1.8B
Reserve
$965M

## Slide 3
CASEY
Scenario Logic
What changed and why the outputs are not generic.
• Base selected: balanced control case for first-pass board challenge and option testing.
• Controls consequence: use this as the reference model before switching to Faster, Cheaper, Lower Risk or Premium.
• Board decision: approve further definition work, not unconditional capital commitment.

## Slide 4
CASEY
QCRA + QSRA Drivers
Separate cost and schedule risk; no mixed generic tornado.
QCRA COST TORNADO
Grid connection delay - $783M
Market escalation - $543M
Design maturity gap - $410M
Scope growth - $402M
Cooling system capacity - $358M
Supply chain delay - $341M
Productivity underperformance - $337M
QSRA SCHEDULE TORNADO
Grid connection delay - 61.9 days
Permits / approvals delay - 31.3 days
Scope growth - 25.3 days
Design maturity gap - 23.1 days
Productivity underperformance - 22.9 days
Supply chain delay - 22.7 days
Cooling system capacity - 22.5 days

## Slide 5
CASEY
Board Top Risks
Cause - Event - Impact - Mitigation.
R-D01 Grid connection delay: Critical path delay, temporary power cost, phased opening risk and revenue deferral
R-002 Market escalation: P50 cost becomes understated; commercial approvals or procurement strategy may need reset
R-004 Design maturity gap: Cost growth, quantity movement, rework and schedule resequencing
R-001 Scope growth: Additional quantities, redesign, rework, procurement churn and board contingency drawdown
R-D02 Cooling system capacity: Re-design, commissioning delay, lower IT load and resilience concern
R-006 Productivity underperformance: Extended duration, increased preliminaries and loss of float
R-005 Supply chain delay: Delayed installation, critical path movement and acceleration cost
R-008 Interface misalignment: Rework, claims, delay and fragmented accountability

## Slide 6
CASEY
Output Pack
Excel cost model, risk register workbook, XER schedule, DOCX/PDF board report, PPTX board deck and JSON audit model generated from one connected CASEY model.
✓ Selected class cost estimate only
✓ Direct / indirect / reserve cost split
✓ Risk register with cause, event, impact and mitigation
✓ Separate QCRA and QSRA curves/tornado
✓ Scenario-linked values for Base / Faster / Cheaper / Lower Risk / Premium
✓ Pricing and email conversion path