## 00 Executive Dashboard
CASEY - EXECUTIVE PROJECT CONTROLS INTELLIGENCE
Board-ready first-pass cost, schedule, risk and confidence model generated from a single connected project basis.
Project | AI Data Centre Campus | Sector | Digital Infrastructure / Hyperscale Data Centre | Scenario | Base | Generated | 2026-05-04 21:32 UTC
P10 Cost |  | P50 Cost |  | P90 Cost |  | QCRA P80
$8.6B |  | $10.7B |  | $13.9B |  | $16.3B
Schedule |  | QSRA P80 |  | Risk |  | Confidence
64 months |  | 77.61 months |  | Medium |  | 64%
Direct |  | Indirect |  | Reserve
$12.7B |  | $1.8B |  | $965M
Executive Summary
AI Data Centre Campus has been classified as Digital Infrastructure / Hyperscale Data Centre in Saudi Arabia / GCC. CASEY estimates $10.7B P50 cost, $8.6B to $13.9B range, 64 month baseline, Medium risk and 64% confidence under the Base scenario.
Board Recommendation
1 | Base selected: balanced control case for first-pass board challenge and option testing.
2 | Controls consequence: use this as the reference model before switching to Faster, Cheaper, Lower Risk or Premium.
3 | Board decision: approve further definition work, not unconditional capital commitment.
4 | Run a risk workshop to validate probability and O/M/P impacts.
5 | Confirm top five CBS cost drivers with benchmark or supplier evidence.
6 | Validate the Level 3/4 schedule logic and critical path assumptions.
7 | Prepare board decision paper with Base/Faster/Cheaper/Lower-Risk cases.
8 | Create confidence improvement plan targeting design maturity, consents and procurement evidence.
Cost Composition
Type | P50 BN
Direct | 12.652
Indirect | 1.824
Reserve | 0.965

## 01 Basis
BASIS OF ESTIMATE AND CONTROL MODEL
Traceability page: no board output should be read without understanding the class, maturity, location, scenario and assumptions.
Input | Value
Prompt | Riyadh AI Hyperscale Campus 500MW accelerated 2027 with sovereign cloud, grid connection and liquid cooling
Client | Microsoft
Mode | Earth
Sector | Digital Infrastructure / Hyperscale Data Centre
Location | Saudi Arabia / GCC
Scale | Programme
Estimate class | Class 3 Budget Authorization
Estimate maturity | 10-40% definition maturity
Schedule level | 4
Scenario | Base
Scenario rationale | Balanced reference case.
Confidence Explanation
• | Class 3 Budget Authorization: 10-40% definition maturity drives the starting confidence level.
• | Schedule Level 4: more detailed schedule logic improves QSRA traceability.
• | Base: Balanced reference case.
• | Location/space factor: Saudi Arabia / GCC applies a 1.35 delivery premium.
• | accelerated delivery compression

## 02 Cost Estimate
SELECTED CLASS COST ESTIMATE - DIRECT / INDIRECT / RESERVE
Only the selected class estimate is exported. P10 / P50 / P90 and direct / indirect / reserve are visible and auditable.
CBS | Description | Type | Basis | P10 BN | P50 BN | P90 BN | Min BN | Most Likely BN | Max BN | Scenario Impact | Evidence / Challenge
01.01 | Site Preparation / Enabling | Direct | Demolition, enabling, logistics and access | 0.515 | 0.643 | 0.836 | 0.515 | 0.643 | 0.836 | Base | Site Preparation / Enabling priced as 6.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.02 | Substructure / Foundations | Direct | Piling, groundworks, retaining and foundations | 0.686 | 0.858 | 1.115 | 0.686 | 0.858 | 1.115 | Base | Substructure / Foundations priced as 8.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.03 | Superstructure / Civil Works | Direct | Frame, civils, primary structures | 1.201 | 1.501 | 1.951 | 1.201 | 1.501 | 1.951 | Base | Superstructure / Civil Works priced as 14.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.04 | MEP / Systems / Utilities | Direct | Mechanical, electrical, controls and utilities | 1.201 | 1.501 | 1.951 | 1.201 | 1.501 | 1.951 | Base | MEP / Systems / Utilities priced as 14.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.05 | Specialist Equipment / Fit-Out | Direct | Permanent equipment and specialist fit-out | 1.029 | 1.287 | 1.673 | 1.029 | 1.287 | 1.673 | Base | Specialist Equipment / Fit-Out priced as 12.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.06 | Data Halls / White Space | Direct | Server halls, fit-out and critical rooms | 1.115 | 1.394 | 1.812 | 1.115 | 1.394 | 1.812 | Base | Data Halls / White Space priced as 13.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.07 | Power Train / Substations | Direct | HV/MV gear, UPS, generators and substations | 1.372 | 1.715 | 2.23 | 1.372 | 1.715 | 2.23 | Base | Power Train / Substations priced as 16.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.08 | Cooling Systems | Direct | Chillers, heat rejection, CRAH/CRAC, water systems | 1.029 | 1.287 | 1.673 | 1.029 | 1.287 | 1.673 | Base | Cooling Systems priced as 12.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.09 | Direct Labour | Direct | Productivity, supervision and trade labour | 0.772 | 0.965 | 1.254 | 0.772 | 0.965 | 1.254 | Base | Direct Labour priced as 9.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.10 | Direct Materials | Direct | Concrete, steel, envelope, MEP materials | 0.858 | 1.072 | 1.394 | 0.858 | 1.072 | 1.394 | Base | Direct Materials priced as 10.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.11 | Plant / Equipment | Direct | Cranes, heavy plant and site equipment | 0.343 | 0.429 | 0.558 | 0.343 | 0.429 | 0.558 | Base | Plant / Equipment priced as 4.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
02.01 | General Conditions / Prelims | Indirect | Site management, safety, offices and temporary services | 0.6 | 0.751 | 0.976 | 0.6 | 0.751 | 0.976 | Base | General Conditions / Prelims priced as 7.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
02.02 | Design / Professional Fees | Indirect | Design, QS, controls, assurance and consultants | 0.6 | 0.751 | 0.976 | 0.6 | 0.751 | 0.976 | Base | Design / Professional Fees priced as 7.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
02.03 | Permits / Insurance / Bonds | Indirect | Permits, inspections, legal, bonds and insurance | 0.257 | 0.322 | 0.418 | 0.257 | 0.322 | 0.418 | Base | Permits / Insurance / Bonds priced as 3.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
03.01 | QCRA Contingency | Reserve | Known-unknown risk allowance | 0.515 | 0.643 | 0.836 | 0.515 | 0.643 | 0.836 | Base | QCRA Contingency priced as 6.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
03.02 | Management Reserve | Reserve | Sponsor-held reserve | 0.257 | 0.322 | 0.418 | 0.257 | 0.322 | 0.418 | Base | Management Reserve priced as 3.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
Type | P50 BN | Share
Direct | 12.652
Indirect | 1.824
Reserve | 0.965

## 03 Indirects & Reserves
INDIRECTS, CONTINGENCY AND RESERVE ASSURANCE
Separates project delivery cost from sponsor-held uncertainty and contingency.
CBS | Description | Type | P10 BN | P50 BN | P90 BN | Assurance Question | Board Treatment
02.01 | General Conditions / Prelims | Indirect | 0.6 | 0.751 | 0.976 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.
02.02 | Design / Professional Fees | Indirect | 0.6 | 0.751 | 0.976 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.
02.03 | Permits / Insurance / Bonds | Indirect | 0.257 | 0.322 | 0.418 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.
03.01 | QCRA Contingency | Reserve | 0.515 | 0.643 | 0.836 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.
03.02 | Management Reserve | Reserve | 0.257 | 0.322 | 0.418 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.

## 04 QCRA
QCRA COST RISK ANALYSIS
Cost curve and separate tornado drivers. QCRA is not mixed with QSRA.
Percentile | Cost BN | Schedule Months | Rank | Driver | CBS | Mean BN | Score | Board Challenge
1 | 11.191 | 64.06 | 1 | Grid connection delay | 01.04 | 0.783 | 78.29 | Request evidence for cost range and owner-retained exposure.
5 | 12.056 | 66.47 | 2 | Market escalation | 01.07 | 0.543 | 54.32 | Request evidence for cost range and owner-retained exposure.
10 | 12.606 | 67.84 | 3 | Design maturity gap | 01.09 | 0.41 | 40.99 | Request evidence for cost range and owner-retained exposure.
20 | 13.327 | 69.63 | 4 | Scope growth | 01.06 | 0.402 | 40.22 | Request evidence for cost range and owner-retained exposure.
30 | 13.832 | 70.98 | 5 | Cooling system capacity | 01.05 | 0.358 | 35.77 | Request evidence for cost range and owner-retained exposure.
40 | 14.288 | 72.18 | 6 | Supply chain delay | 01.10 | 0.341 | 34.09 | Request evidence for cost range and owner-retained exposure.
50 | 14.734 | 73.36 | 7 | Productivity underperformance | 01.11 | 0.337 | 33.69 | Request evidence for cost range and owner-retained exposure.
60 | 15.18 | 74.63 | 8 | Interface misalignment | 02.02 | 0.282 | 28.15 | Request evidence for cost range and owner-retained exposure.
70 | 15.676 | 75.93 | 9 | Commissioning delay | 02.01 | 0.236 | 23.57 | Request evidence for cost range and owner-retained exposure.
80 | 16.266 | 77.61 | 10 | Permits / approvals delay | 01.08 | 0.16 | 16.01 | Request evidence for cost range and owner-retained exposure.
90 | 17.087 | 79.79
95 | 17.731 | 81.7
99 | 18.991 | 85.08

## 05 QSRA
QSRA SCHEDULE RISK ANALYSIS
Schedule curve and separate tornado drivers. QSRA is not mixed with QCRA.
Percentile | Schedule Months | Cost BN | Rank | Driver | Activity | Mean Days | Score | Recovery / Mitigation Challenge
1 | 64.06 | 11.191 | 1 | Grid connection delay | A1400 | 61.9 | 30.93 | Confirm critical path logic, float erosion and recovery option.
5 | 66.47 | 12.056 | 2 | Permits / approvals delay | A1800 | 31.3 | 15.65 | Confirm critical path logic, float erosion and recovery option.
10 | 67.84 | 12.606 | 3 | Scope growth | A1600 | 25.3 | 12.66 | Confirm critical path logic, float erosion and recovery option.
20 | 69.63 | 13.327 | 4 | Design maturity gap | A1900 | 23.1 | 11.55 | Confirm critical path logic, float erosion and recovery option.
30 | 70.98 | 13.832 | 5 | Productivity underperformance | A2100 | 22.9 | 11.46 | Confirm critical path logic, float erosion and recovery option.
40 | 72.18 | 14.288 | 6 | Supply chain delay | A2000 | 22.7 | 11.35 | Confirm critical path logic, float erosion and recovery option.
50 | 73.36 | 14.734 | 7 | Cooling system capacity | A1500 | 22.5 | 11.25 | Confirm critical path logic, float erosion and recovery option.
60 | 74.63 | 15.18 | 8 | Interface misalignment | P2000 | 16.6 | 8.32 | Confirm critical path logic, float erosion and recovery option.
70 | 75.93 | 15.676 | 9 | Commissioning delay | P1000 | 16 | 7.98 | Confirm critical path logic, float erosion and recovery option.
80 | 77.61 | 16.266 | 10 | Market escalation | A1700 | 0 | 0 | Confirm critical path logic, float erosion and recovery option.
90 | 79.79 | 17.087
95 | 81.7 | 17.731
99 | 85.08 | 18.991

## 06 Risk Register
RISK REGISTER PRO - CAUSE / EVENT / IMPACT / RESPONSE
Board-grade register with quantified cost and schedule exposure, owners and linked WBS/CBS.
Risk ID | Category | Title | Cause | Risk Event | Impact Description | Probability % | Cost O BN | Cost M BN | Cost P BN | Cost EMV BN | Schedule O Days | Schedule M Days | Schedule P Days | Schedule EMV Days | Activity | CBS | Owner | Trigger | Mitigation | Response Strategy | Residual | Status | Board
R-D01 | Utilities | Grid connection delay | Utility agreement, substation scope or energisation pathway not secured | Power connection or energisation milestone slips | Critical path delay, temporary power cost, phased opening risk and revenue deferral | 52 | 0.429 | 1.287 | 2.788 | 0.669 | 25 | 90 | 240 | 46.8 | A1400 | 01.04 | Utilities Lead | Grid agreement unsigned at gate | Secure grid agreement, temporary power strategy, early equipment orders | Mitigate | Medium | Open | Yes
R-002 | Commercial | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | 45 | 0.429 | 1.072 | 2.144 | 0.482 | 0 | 0 | 0 | 0 | A1700 | 01.07 | Commercial Lead | Index exceeds allowance by 3% | Early procurement, index-linked allowances, market testing, FX strategy | Mitigate | Low | Open | Yes
R-004 | Technical | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | 38 | 0.322 | 0.965 | 1.93 | 0.367 | 15 | 45 | 120 | 17.1 | A1900 | 01.09 | Design Manager | Design deliverables miss maturity gate | Design maturity gates, independent review, assumption register | Reduce | Low | Open | Yes
R-001 | Scope | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | 42 | 0.322 | 0.858 | 1.715 | 0.36 | 15 | 45 | 120 | 18.9 | A1600 | 01.06 | Project Director | Scope change rate exceeds 2% of package value | Freeze scope baseline, change board, value gates, client decision log | Reduce | Low | Open | Yes
R-D02 | Technical | Cooling system capacity | Thermal basis, water availability or cooling vendor performance uncertain | Cooling design fails capacity, redundancy or commissioning test | Re-design, commissioning delay, lower IT load and resilience concern | 36 | 0.268 | 0.858 | 1.823 | 0.309 | 10 | 45 | 130 | 16.2 | A1500 | 01.05 | MEP Lead | Cooling performance test fails | Thermal modelling, supplier validation, early performance test | Reduce | Low | Open | Yes
R-006 | Delivery | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | 35 | 0.322 | 0.858 | 1.715 | 0.3 | 15 | 50 | 130 | 17.5 | A2100 | 01.11 | Delivery Lead | SPI/CPI deteriorates for two reporting periods | Package productivity controls, daily planning, earned value cadence | Mitigate | Low | Open | Yes
R-005 | Procurement | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | 40 | 0.214 | 0.751 | 1.608 | 0.3 | 10 | 40 | 120 | 16 | A2000 | 01.10 | Procurement Lead | Supplier promise date slips | Alternate suppliers, early orders, expediting, framework options | Transfer / Mitigate | Low | Open | Yes
R-008 | Integration | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | 34 | 0.214 | 0.751 | 1.501 | 0.255 | 10 | 35 | 100 | 11.9 | P2000 | 02.02 | Integration Manager | Interface actions overdue | Interface control documents, weekly interface board, accountable owners | Mitigate | Low | Open | No
R-007 | Handover | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | 32 | 0.214 | 0.643 | 1.287 | 0.206 | 10 | 35 | 100 | 11.2 | P1000 | 02.01 | Commissioning Lead | Test failures trend upward | Commissioning readiness plan, early test packs, digital systems integration | Reduce | Low | Open | No
R-003 | Regulatory | Permits / approvals delay | Authority process, stakeholder objections or incomplete submissions | Consent milestone slips beyond baseline | Critical path delay, extended preliminaries and potential redesign conditions | 35 | 0.107 | 0.429 | 0.858 | 0.15 | 20 | 70 | 180 | 24.5 | A1800 | 01.08 | Consents Lead | Consent milestone slips by 30 days | Authority plan, consent tracker, early submissions, stakeholder map | Mitigate | Low | Open | Yes

## 07 Schedule
SCHEDULE LOGIC - LEVEL SELECTED
Linked schedule activities for QSRA and export to P6/XER.
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis | Risk Links
A1000 | Governance | Project initiation / controls setup |  | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-D01
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-D02
A1600 | Design | Detailed design / IFC development | A1300 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-001
A1700 | Procurement | Long-lead procurement | A1500 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-002
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-003
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 14 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-004
A2000 | Integration | Systems integration and testing | A1900 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-005
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-006
P1000 | Package | Grid connection | A1900 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-007
P2000 | Package | Data halls | P1000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-008
P3000 | Package | Cooling plant | P2000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4000 | Package | Power train | P3000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5000 | Package | Controls and commissioning | P4000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## 08 Scenarios
SCENARIO COMPARISON - BASE / FASTER / CHEAPER / LOWER RISK / PREMIUM
Scenario choice must change cost, schedule, risk and confidence.
Scenario | P50 Cost | Schedule | Risk | Confidence | Cost Change Logic | Schedule Change Logic | Risk Logic
base |  |  | Medium | 64 | Balanced reference case.
faster |  |  | Medium-High | 55 | Parallel design/procurement, acceleration, premium logistics and higher interface risk.
cheaper |  |  | Medium | 58 | Value engineering, tighter scope and procurement competition, with schedule/quality exposure.
lower_risk |  |  | Medium | 73 | More surveys, assurance, stage gates, contingency and schedule buffers.
premium |  |  | Medium | 76 | Best assurance, independent review, early procurement and high-confidence governance.
investor |  |  | Medium | 67 | Investment-framing case with transparent risk and commercial challenge.
survival |  |  | Medium-High | 50 | Minimum viable scope, warning-heavy, high residual risk.

## 09 Benchmarking
BENCHMARKING AND PEER CHALLENGE
Use to challenge Tier 1 contractor estimates, market rates and sponsor assumptions.
Benchmark / Peer | What to compare | Why it matters | Challenge question | Evidence required
Meta | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log
Alphabet / Google | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log
Amazon AWS | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log
Oracle | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log
Apple | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log

## 10 Assumptions
ASSUMPTIONS, LIMITATIONS AND DECISION GATES
Makes the output honest: a first-pass project controls intelligence pack, not a final tender estimate.
Area | Assumption / Limitation | Board Action
Estimate | Class 3 Budget Authorization with 10-40% definition maturity; not a contractor tender price. | Use to challenge, shortlist and frame approval gates.
Schedule | Level 4 logic; critical path and float require validation against project-specific constraints. | Run schedule risk workshop and validate dependencies.
Risk | QCRA and QSRA distributions are modelled from the generated register and selected scenario. | Replace assumptions with workshop data as evidence improves.
Scenario | Balanced reference case. | Compare Base / Faster / Cheaper / Lower Risk before board decision.
Outputs | Exports are board-preparation outputs and should be reviewed before external release. | Apply owner governance, sign-off and evidence checks.