# CASEY Executive Board Intelligence Pack

AI Data Centre Campus | Digital Infrastructure / Hyperscale Data Centre | Base scenario | Generated 2026-05-04 21:32 UTC

AI Data Centre Campus has been classified as Digital Infrastructure / Hyperscale Data Centre in Saudi Arabia / GCC. CASEY estimates $10.7B P50 cost, $8.6B to $13.9B range, 64 month baseline, Medium risk and 64% confidence under the Base scenario.

# 1. Board Decision Snapshot

| Metric | Value | Interpretation | Board Action |
| --- | --- | --- | --- |
| P50 Cost | $10.7B | Most likely first-pass cost based on selected class and scenario. | Use as initial investment control point. |
| Cost Range | $8.6B - $13.9B | Class/maturity and QCRA uncertainty range. | Do not approve without range acknowledgement. |
| QCRA P80 | $16.3B | Risk-adjusted cost confidence level. | Set funding envelope and contingency rules. |
| Baseline / QSRA P80 | 64 months / 77.61 months | Schedule risk exposure and delivery confidence. | Require critical path validation. |
| Risk / Confidence | Medium / 64% | Early-stage confidence and data quality status. | Approve evidence-improvement plan. |
| Direct / Indirect / Reserve | $12.7B / $1.8B / $965M | Prevents reserves being hidden inside direct cost. | Challenge contractor and adviser basis. |

# 2. Executive Recommendation

Base selected: balanced control case for first-pass board challenge and option testing.

Controls consequence: use this as the reference model before switching to Faster, Cheaper, Lower Risk or Premium.

Board decision: approve further definition work, not unconditional capital commitment.

Run a risk workshop to validate probability and O/M/P impacts.

Confirm top five CBS cost drivers with benchmark or supplier evidence.

Validate the Level 3/4 schedule logic and critical path assumptions.

Prepare board decision paper with Base/Faster/Cheaper/Lower-Risk cases.

Create confidence improvement plan targeting design maturity, consents and procurement evidence.

# 3. Cost Estimate - Selected Class Only

| CBS | Description | Type | P10 | P50 | P90 | Basis |
| --- | --- | --- | --- | --- | --- | --- |
| 01.01 | Site Preparation / Enabling | Direct | $515M | $643M | $836M | Site Preparation / Enabling priced as 6.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 01.02 | Substructure / Foundations | Direct | $686M | $858M | $1.1B | Substructure / Foundations priced as 8.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 01.03 | Superstructure / Civil Works | Direct | $1.2B | $1.5B | $2.0B | Superstructure / Civil Works priced as 14.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 01.04 | MEP / Systems / Utilities | Direct | $1.2B | $1.5B | $2.0B | MEP / Systems / Utilities priced as 14.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 01.05 | Specialist Equipment / Fit-Out | Direct | $1.0B | $1.3B | $1.7B | Specialist Equipment / Fit-Out priced as 12.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 01.06 | Data Halls / White Space | Direct | $1.1B | $1.4B | $1.8B | Data Halls / White Space priced as 13.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 01.07 | Power Train / Substations | Direct | $1.4B | $1.7B | $2.2B | Power Train / Substations priced as 16.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 01.08 | Cooling Systems | Direct | $1.0B | $1.3B | $1.7B | Cooling Systems priced as 12.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 01.09 | Direct Labour | Direct | $772M | $965M | $1.3B | Direct Labour priced as 9.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 01.10 | Direct Materials | Direct | $858M | $1.1B | $1.4B | Direct Materials priced as 10.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 01.11 | Plant / Equipment | Direct | $343M | $429M | $558M | Plant / Equipment priced as 4.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 02.01 | General Conditions / Prelims | Indirect | $600M | $751M | $976M | General Conditions / Prelims priced as 7.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 02.02 | Design / Professional Fees | Indirect | $600M | $751M | $976M | Design / Professional Fees priced as 7.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 02.03 | Permits / Insurance / Bonds | Indirect | $257M | $322M | $418M | Permits / Insurance / Bonds priced as 3.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 03.01 | QCRA Contingency | Reserve | $515M | $643M | $836M | QCRA Contingency priced as 6.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |
| 03.02 | Management Reserve | Reserve | $257M | $322M | $418M | Management Reserve priced as 3.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10. |

# 4. QCRA and QSRA

QCRA cost P10 / P50 / P80 / P90: $12.6B / $10.7B / $16.3B / $17.1B

QSRA schedule P10 / P50 / P80 / P90: 67.84 / 73.36 / 77.61 / 79.79 months

## 5. QCRA Tornado Drivers

Grid connection delay - 01.04 - mean exposure $783M

Market escalation - 01.07 - mean exposure $543M

Design maturity gap - 01.09 - mean exposure $410M

Scope growth - 01.06 - mean exposure $402M

Cooling system capacity - 01.05 - mean exposure $358M

Supply chain delay - 01.10 - mean exposure $341M

Productivity underperformance - 01.11 - mean exposure $337M

Interface misalignment - 02.02 - mean exposure $282M

## 6. QSRA Tornado Drivers

Grid connection delay - A1400 - mean exposure 61.9 days

Permits / approvals delay - A1800 - mean exposure 31.3 days

Scope growth - A1600 - mean exposure 25.3 days

Design maturity gap - A1900 - mean exposure 23.1 days

Productivity underperformance - A2100 - mean exposure 22.9 days

Supply chain delay - A2000 - mean exposure 22.7 days

Cooling system capacity - A1500 - mean exposure 22.5 days

Interface misalignment - P2000 - mean exposure 16.6 days

# 7. Risk Register - Board Top Risks

R-D01 Grid connection delay

Cause: Utility agreement, substation scope or energisation pathway not secured. Event: Power connection or energisation milestone slips. Impact: Critical path delay, temporary power cost, phased opening risk and revenue deferral. Mitigation: Secure grid agreement, temporary power strategy, early equipment orders. Owner: Utilities Lead.

R-002 Market escalation

Cause: Supplier market tightness, inflation, FX and long procurement window. Event: Rates exceed assumed escalation profile. Impact: P50 cost becomes understated; commercial approvals or procurement strategy may need reset. Mitigation: Early procurement, index-linked allowances, market testing, FX strategy. Owner: Commercial Lead.

R-004 Design maturity gap

Cause: Estimate is based on immature design, incomplete surveys or unresolved interfaces. Event: Design basis changes during detailed design. Impact: Cost growth, quantity movement, rework and schedule resequencing. Mitigation: Design maturity gates, independent review, assumption register. Owner: Design Manager.

R-001 Scope growth

Cause: Ambiguous requirements, immature scope freeze and late stakeholder changes. Event: Approved scope expands after estimate freeze. Impact: Additional quantities, redesign, rework, procurement churn and board contingency drawdown. Mitigation: Freeze scope baseline, change board, value gates, client decision log. Owner: Project Director.

R-D02 Cooling system capacity

Cause: Thermal basis, water availability or cooling vendor performance uncertain. Event: Cooling design fails capacity, redundancy or commissioning test. Impact: Re-design, commissioning delay, lower IT load and resilience concern. Mitigation: Thermal modelling, supplier validation, early performance test. Owner: MEP Lead.

R-006 Productivity underperformance

Cause: Access constraints, poor sequencing, labour scarcity or learning curve. Event: Actual production rates underperform plan. Impact: Extended duration, increased preliminaries and loss of float. Mitigation: Package productivity controls, daily planning, earned value cadence. Owner: Delivery Lead.

R-005 Supply chain delay

Cause: Long-lead equipment, constrained suppliers or late procurement release. Event: Supplier promise dates move right. Impact: Delayed installation, critical path movement and acceleration cost. Mitigation: Alternate suppliers, early orders, expediting, framework options. Owner: Procurement Lead.

R-008 Interface misalignment

Cause: Multiple contractors, unclear interface ownership or late design coordination. Event: Package interfaces do not align during installation/integration. Impact: Rework, claims, delay and fragmented accountability. Mitigation: Interface control documents, weekly interface board, accountable owners. Owner: Integration Manager.

R-007 Commissioning delay

Cause: Incomplete readiness, software integration issues or defects during testing. Event: Systems fail tests or require repeated commissioning cycles. Impact: Delayed handover, operational readiness slippage and liquidated damages exposure. Mitigation: Commissioning readiness plan, early test packs, digital systems integration. Owner: Commissioning Lead.

R-003 Permits / approvals delay

Cause: Authority process, stakeholder objections or incomplete submissions. Event: Consent milestone slips beyond baseline. Impact: Critical path delay, extended preliminaries and potential redesign conditions. Mitigation: Authority plan, consent tracker, early submissions, stakeholder map. Owner: Consents Lead.

# 8. Challenge Questions

What evidence supports the P50 cost and P80 confidence?

Which five risks create most contingency?

Which activities drive the QSRA finish-date risk?

What data would increase confidence before approval?

What is the fastest credible lower-risk path?

# 9. Assumptions and Limitations

This is a first-pass project controls intelligence pack. It is designed to challenge, accelerate and structure decision-making; it is not a final contractor tender or signed cost plan. Each output includes assumptions and should be validated against project-specific evidence before commitment.