## 00 Executive Dashboard
CASEY - EXECUTIVE PROJECT CONTROLS INTELLIGENCE
Board-ready first-pass cost, schedule, risk and confidence model generated from a single connected project basis.
Project | Space Base | Sector | Surface Habitat/Base | Scenario | Lower Risk | Generated | 2026-05-04 21:33 UTC
P10 Cost |  | P50 Cost |  | P90 Cost |  | QCRA P80
$158.4B |  | $198.0B |  | $257.4B |  | $273.9B
Schedule |  | QSRA P80 |  | Risk |  | Confidence
246 months |  | 267.52 months |  | High |  | 65%
Direct |  | Indirect |  | Reserve
$154.4B |  | $29.7B |  | $23.8B
Executive Summary
Space Base has been classified as Surface Habitat/Base in Moon / Lunar Surface. CASEY estimates $198.0B P50 cost, $158.4B to $257.4B range, 246 month baseline, High risk and 65% confidence under the Lower Risk scenario.
Board Recommendation
1 | Lower-risk selected: more assurance, surveys, float and contingency raise headline cost but improve confidence.
2 | Controls consequence: stronger evidence should move risk from unknown unknowns into quantified known unknowns.
3 | Board decision: approve with a confidence-improvement plan and gate evidence pack.
4 | Run a risk workshop to validate probability and O/M/P impacts.
5 | Confirm top five CBS cost drivers with benchmark or supplier evidence.
6 | Validate the Level 3/4 schedule logic and critical path assumptions.
7 | Prepare board decision paper with Base/Faster/Cheaper/Lower-Risk cases.
8 | Create confidence improvement plan targeting design maturity, consents and procurement evidence.
Cost Composition
Type | P50 BN
Direct | 154.442
Indirect | 29.7
Reserve | 23.76

## 01 Basis
BASIS OF ESTIMATE AND CONTROL MODEL
Traceability page: no board output should be read without understanding the class, maturity, location, scenario and assumptions.
Input | Value
Prompt | Lunar Base Alpha with 1000 crew, nuclear power, landing pads, life support and launch logistics
Client | Lunar Development Authority
Mode | Space
Sector | Surface Habitat/Base
Location | Moon / Lunar Surface
Scale | Project
Estimate class | Class 3 Budget Authorization
Estimate maturity | 10-40% definition maturity
Schedule level | 4
Scenario | Lower Risk
Scenario rationale | More surveys, assurance, stage gates, contingency and schedule buffers.
Confidence Explanation
• | Class 3 Budget Authorization: 10-40% definition maturity drives the starting confidence level.
• | Schedule Level 4: more detailed schedule logic improves QSRA traceability.
• | Lower Risk: More surveys, assurance, stage gates, contingency and schedule buffers.
• | Location/space factor: Moon / Lunar Surface applies a 2.90 delivery premium.
• | nuclear assurance and regulation
• | life support systems

## 02 Cost Estimate
SELECTED CLASS COST ESTIMATE - DIRECT / INDIRECT / RESERVE
Only the selected class estimate is exported. P10 / P50 / P90 and direct / indirect / reserve are visible and auditable.
CBS | Description | Type | Basis | P10 BN | P50 BN | P90 BN | Min BN | Most Likely BN | Max BN | Scenario Impact | Evidence / Challenge
01.01 | DDT&E Engineering | Direct | Engineering design, mission architecture and qualification | 14.256 | 17.82 | 23.167 | 14.256 | 17.82 | 23.167 | Lower Risk | DDT&E Engineering priced as 9.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.02 | Systems Engineering & Integration | Direct | Requirements, ICDs, verification and validation | 9.504 | 11.88 | 15.444 | 9.504 | 11.88 | 15.444 | Lower Risk | Systems Engineering & Integration priced as 6.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.03 | Structures / Habitat Shell | Direct | Pressure vessels, shielding and primary structures | 15.84 | 19.801 | 25.741 | 15.84 | 19.801 | 25.741 | Lower Risk | Structures / Habitat Shell priced as 10.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.04 | Power Generation & Distribution | Direct | Solar/nuclear source, grid and controls | 12.672 | 15.84 | 20.593 | 12.672 | 15.84 | 20.593 | Lower Risk | Power Generation & Distribution priced as 8.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.05 | ECLSS / Life Support | Direct | Air, water, waste, atmosphere and safety systems | 14.256 | 17.82 | 23.167 | 14.256 | 17.82 | 23.167 | Lower Risk | ECLSS / Life Support priced as 9.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.06 | Payload / Mission Equipment | Direct | Scientific, medical, industrial or settlement payload | 11.088 | 13.86 | 18.018 | 11.088 | 13.86 | 18.018 | Lower Risk | Payload / Mission Equipment priced as 7.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.07 | Robotics / Autonomous Construction | Direct | Robotic construction, inspection and maintenance | 9.504 | 11.88 | 15.444 | 9.504 | 11.88 | 15.444 | Lower Risk | Robotics / Autonomous Construction priced as 6.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.08 | Launch Services | Direct | Launch vehicle, manifest, payload processing | 22.177 | 27.721 | 36.037 | 22.177 | 27.721 | 36.037 | Lower Risk | Launch Services priced as 14.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.09 | Transport / Landing / Surface Logistics | Direct | Transit, landing, mobility and logistics chain | 14.256 | 17.82 | 23.167 | 14.256 | 17.82 | 23.167 | Lower Risk | Transport / Landing / Surface Logistics priced as 9.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
02.01 | Test & Qualification Facilities | Indirect | Thermal-vac, vibration, radiation and integrated testing | 7.92 | 9.9 | 12.87 | 7.92 | 9.9 | 12.87 | Lower Risk | Test & Qualification Facilities priced as 5.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
02.02 | Safety & Mission Assurance | Indirect | Quality, safety, independent review and compliance | 7.92 | 9.9 | 12.87 | 7.92 | 9.9 | 12.87 | Lower Risk | Safety & Mission Assurance priced as 5.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
02.03 | Programme Management / PMO | Indirect | Controls, reporting, commercial and integration PMO | 7.92 | 9.9 | 12.87 | 7.92 | 9.9 | 12.87 | Lower Risk | Programme Management / PMO priced as 5.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
03.01 | Risk Contingency / UFE | Reserve | Known-unknown risk allowance linked to QCRA/QSRA | 11.088 | 13.86 | 18.018 | 11.088 | 13.86 | 18.018 | Lower Risk | Risk Contingency / UFE priced as 7.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
03.02 | Management Reserve | Reserve | Sponsor-held unknown-unknown reserve | 7.92 | 9.9 | 12.87 | 7.92 | 9.9 | 12.87 | Lower Risk | Management Reserve priced as 5.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
Type | P50 BN | Share
Direct | 154.442
Indirect | 29.7
Reserve | 23.76

## 03 Indirects & Reserves
INDIRECTS, CONTINGENCY AND RESERVE ASSURANCE
Separates project delivery cost from sponsor-held uncertainty and contingency.
CBS | Description | Type | P10 BN | P50 BN | P90 BN | Assurance Question | Board Treatment
02.01 | Test & Qualification Facilities | Indirect | 7.92 | 9.9 | 12.87 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.
02.02 | Safety & Mission Assurance | Indirect | 7.92 | 9.9 | 12.87 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.
02.03 | Programme Management / PMO | Indirect | 7.92 | 9.9 | 12.87 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.
03.01 | Risk Contingency / UFE | Reserve | 11.088 | 13.86 | 18.018 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.
03.02 | Management Reserve | Reserve | 7.92 | 9.9 | 12.87 | Is this genuinely indirect/reserve, or hidden direct scope? | Show separately in board pack; do not bury in headline P50.

## 04 QCRA
QCRA COST RISK ANALYSIS
Cost curve and separate tornado drivers. QCRA is not mixed with QSRA.
Percentile | Cost BN | Schedule Months | Rank | Driver | CBS | Mean BN | Score | Board Challenge
1 | 194.226 | 237.53 | 1 | Mass growth | 01.05 | 7.366 | 736.59 | Request evidence for cost range and owner-retained exposure.
5 | 207.024 | 241.49 | 2 | Life-support reliability | 01.06 | 7.174 | 717.43 | Request evidence for cost range and owner-retained exposure.
10 | 215.625 | 244.24 | 3 | Launch manifest delay | 01.04 | 6.991 | 699.14 | Request evidence for cost range and owner-retained exposure.
20 | 226.527 | 247.93 | 4 | Market escalation | 01.08 | 5.473 | 547.33 | Request evidence for cost range and owner-retained exposure.
30 | 234.606 | 250.94 | 5 | Scope growth | 01.07 | 4.105 | 410.46 | Request evidence for cost range and owner-retained exposure.
40 | 241.754 | 253.67 | 6 | Design maturity gap | 02.01 | 4.031 | 403.11 | Request evidence for cost range and owner-retained exposure.
50 | 248.962 | 256.54 | 7 | Supply chain delay | 02.02 | 3.371 | 337.07 | Request evidence for cost range and owner-retained exposure.
60 | 256.219 | 259.65 | 8 | Productivity underperformance | 02.03 | 3.315 | 331.5 | Request evidence for cost range and owner-retained exposure.
70 | 264.257 | 263.21 | 9 | Interface misalignment | 03.02 | 2.837 | 283.68 | Request evidence for cost range and owner-retained exposure.
80 | 273.853 | 267.52 | 10 | Commissioning delay | 03.01 | 2.286 | 228.61 | Request evidence for cost range and owner-retained exposure.
90 | 287.223 | 272.92
95 | 298.693 | 276.81
99 | 321.515 | 283.03

## 05 QSRA
QSRA SCHEDULE RISK ANALYSIS
Schedule curve and separate tornado drivers. QSRA is not mixed with QCRA.
Percentile | Schedule Months | Cost BN | Rank | Driver | Activity | Mean Days | Score | Recovery / Mitigation Challenge
1 | 237.53 | 194.226 | 1 | Launch manifest delay | A1400 | 24.7 | 12.34 | Confirm critical path logic, float erosion and recovery option.
5 | 241.49 | 207.024 | 2 | Life-support reliability | A1600 | 23.1 | 11.55 | Confirm critical path logic, float erosion and recovery option.
10 | 244.24 | 215.625 | 3 | Mass growth | A1500 | 18.1 | 9.05 | Confirm critical path logic, float erosion and recovery option.
20 | 247.93 | 226.527 | 4 | Permits / approvals delay | A1900 | 17.7 | 8.87 | Confirm critical path logic, float erosion and recovery option.
30 | 250.94 | 234.606 | 5 | Scope growth | A1700 | 14.3 | 7.13 | Confirm critical path logic, float erosion and recovery option.
40 | 253.67 | 241.754 | 6 | Design maturity gap | A2000 | 12.6 | 6.32 | Confirm critical path logic, float erosion and recovery option.
50 | 256.54 | 248.962 | 7 | Productivity underperformance | P1000 | 12.5 | 6.23 | Confirm critical path logic, float erosion and recovery option.
60 | 259.65 | 256.219 | 8 | Supply chain delay | A2100 | 12.4 | 6.19 | Confirm critical path logic, float erosion and recovery option.
70 | 263.21 | 264.257 | 9 | Interface misalignment | P3000 | 9.4 | 4.69 | Confirm critical path logic, float erosion and recovery option.
80 | 267.52 | 273.853 | 10 | Commissioning delay | P2000 | 8.4 | 4.22 | Confirm critical path logic, float erosion and recovery option.
90 | 272.92 | 287.223
95 | 276.81 | 298.693
99 | 283.03 | 321.515

## 06 Risk Register
RISK REGISTER PRO - CAUSE / EVENT / IMPACT / RESPONSE
Board-grade register with quantified cost and schedule exposure, owners and linked WBS/CBS.
Risk ID | Category | Title | Cause | Risk Event | Impact Description | Probability % | Cost O BN | Cost M BN | Cost P BN | Cost EMV BN | Schedule O Days | Schedule M Days | Schedule P Days | Schedule EMV Days | Activity | CBS | Owner | Trigger | Mitigation | Response Strategy | Residual | Status | Board
R-S01 | Launch | Launch manifest delay | Launch provider capacity, weather windows, manifest priority or vehicle readiness | Confirmed launch slot moves or payload misses manifest gate | Programme delay, storage cost, resequencing and mission-readiness risk | 37 | 6.93 | 15.246 | 35.641 | 5.641 | 20 | 43 | 140 | 15.9 | A1400 | 01.04 | Launch Integration Lead | Launch slot not confirmed at L-12 months | Reserve alternate launch slot, freeze payload interface, maintain launch-readiness checklist | Mitigate | Medium | Open | Yes
R-S03 | Safety / Mission | Life-support reliability | ECLSS reliability, spares or redundancy evidence below target | Life-support system fails reliability growth or integrated test | Crew safety exposure, launch delay, redesign and mission abort risk | 27 | 11.88 | 20.791 | 47.521 | 5.613 | 25 | 58 | 172 | 15.7 | A1600 | 01.06 | Life Support Lead | Reliability growth misses target | Prototype testing, redundancy, reliability growth, independent assurance | Avoid / Reduce | Medium | Open | Yes
R-S02 | Technical | Mass growth | Design creep, shielding, redundancy or late payload additions increase mass | Payload mass exceeds launch and landing allowance | Launch cost, redesign, performance loss and mission safety exposure | 31 | 9.9 | 18.018 | 41.581 | 5.586 | 15 | 40 | 117 | 12.4 | A1500 | 01.05 | Chief Engineer | Mass margin below 8% | Mass control board, margin policy, design-to-mass reviews | Reduce | Medium | Open | Yes
R-002 | Commercial | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | 32 | 7.92 | 13.86 | 29.701 | 4.435 | 0 | 0 | 0 | 0 | A1800 | 01.08 | Commercial Lead | Index exceeds allowance by 3% | Early procurement, index-linked allowances, market testing, FX strategy | Mitigate | Medium | Open | Yes
R-004 | Technical | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | 27 | 5.94 | 12.474 | 26.731 | 3.368 | 15 | 32 | 94 | 8.6 | A2000 | 02.01 | Design Manager | Design deliverables miss maturity gate | Design maturity gates, independent review, assumption register | Reduce | Medium | Open | Yes
R-001 | Scope | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | 30 | 5.94 | 11.088 | 23.761 | 3.326 | 15 | 32 | 94 | 9.6 | A1700 | 01.07 | Project Director | Scope change rate exceeds 2% of package value | Freeze scope baseline, change board, value gates, client decision log | Reduce | Medium | Open | Yes
R-006 | Delivery | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | 25 | 5.94 | 11.088 | 23.761 | 2.772 | 15 | 36 | 101 | 9 | P1000 | 02.03 | Delivery Lead | SPI/CPI deteriorates for two reporting periods | Package productivity controls, daily planning, earned value cadence | Mitigate | Medium | Open | Yes
R-005 | Procurement | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | 28 | 3.96 | 9.702 | 22.276 | 2.717 | 10 | 29 | 94 | 8.1 | A2100 | 02.02 | Procurement Lead | Supplier promise date slips | Alternate suppliers, early orders, expediting, framework options | Transfer / Mitigate | Medium | Open | Yes
R-008 | Integration | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | 24 | 3.96 | 9.702 | 20.791 | 2.329 | 10 | 25 | 78 | 6 | P3000 | 03.02 | Integration Manager | Interface actions overdue | Interface control documents, weekly interface board, accountable owners | Mitigate | Medium | Open | Yes
R-007 | Handover | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | 23 | 3.96 | 8.316 | 17.82 | 1.913 | 10 | 25 | 78 | 5.8 | P2000 | 03.01 | Commissioning Lead | Test failures trend upward | Commissioning readiness plan, early test packs, digital systems integration | Reduce | Medium | Open | Yes
R-003 | Regulatory | Permits / approvals delay | Authority process, stakeholder objections or incomplete submissions | Consent milestone slips beyond baseline | Critical path delay, extended preliminaries and potential redesign conditions | 25 | 1.98 | 5.544 | 11.88 | 1.386 | 20 | 50 | 140 | 12.5 | A1900 | 01.09 | Consents Lead | Consent milestone slips by 30 days | Authority plan, consent tracker, early submissions, stakeholder map | Mitigate | Medium | Open | Yes

## 07 Schedule
SCHEDULE LOGIC - LEVEL SELECTED
Linked schedule activities for QSRA and export to P6/XER.
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis | Risk Links
A1000 | Governance | Project initiation / controls setup |  | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 12 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 12 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 20 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-S01
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 15 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-S02
A1600 | Design | Detailed design / IFC development | A1300 | 25 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-S03
A1700 | Procurement | Long-lead procurement | A1500 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-001
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 17 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-002
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 54 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-003
A2000 | Integration | Systems integration and testing | A1900 | 25 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-004
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 15 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-005
P1000 | Package | Launch campaign | A1900 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-006
P2000 | Package | Payload integration | P1000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-007
P3000 | Package | Power and ECLSS | P2000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic. | R-008
P4000 | Package | Surface logistics | P3000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5000 | Package | Mission operations | P4000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P6000 | Package | Robotic assembly | P5000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## 08 Scenarios
SCENARIO COMPARISON - BASE / FASTER / CHEAPER / LOWER RISK / PREMIUM
Scenario choice must change cost, schedule, risk and confidence.
Scenario | P50 Cost | Schedule | Risk | Confidence | Cost Change Logic | Schedule Change Logic | Risk Logic
base |  |  | Extreme | 46 | Balanced reference case.
faster |  |  | Extreme | 41 | Parallel design/procurement, acceleration, premium logistics and higher interface risk.
cheaper |  |  | Extreme | 40 | Value engineering, tighter scope and procurement competition, with schedule/quality exposure.
lower_risk |  |  | High | 65 | More surveys, assurance, stage gates, contingency and schedule buffers.
premium |  |  | High | 68 | Best assurance, independent review, early procurement and high-confidence governance.
investor |  |  | Very High | 55 | Investment-framing case with transparent risk and commercial challenge.
survival |  |  | Extreme | 36 | Minimum viable scope, warning-heavy, high residual risk.

## 09 Benchmarking
BENCHMARKING AND PEER CHALLENGE
Use to challenge Tier 1 contractor estimates, market rates and sponsor assumptions.
Benchmark / Peer | What to compare | Why it matters | Challenge question | Evidence required
SpaceX | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log
Blue Origin | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log
Rocket Lab | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log
ULA | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log
NASA/ESA programmes | Unit rates, schedule intensity, cost/scope normalization | Prevents blind acceptance of contractor/adviser basis | Where are we above peer norm and why? | Rate build-up, supplier quote, productivity basis, exclusions log

## 10 Assumptions
ASSUMPTIONS, LIMITATIONS AND DECISION GATES
Makes the output honest: a first-pass project controls intelligence pack, not a final tender estimate.
Area | Assumption / Limitation | Board Action
Estimate | Class 3 Budget Authorization with 10-40% definition maturity; not a contractor tender price. | Use to challenge, shortlist and frame approval gates.
Schedule | Level 4 logic; critical path and float require validation against project-specific constraints. | Run schedule risk workshop and validate dependencies.
Risk | QCRA and QSRA distributions are modelled from the generated register and selected scenario. | Replace assumptions with workshop data as evidence improves.
Scenario | More surveys, assurance, stage gates, contingency and schedule buffers. | Compare Base / Faster / Cheaper / Lower Risk before board decision.
Outputs | Exports are board-preparation outputs and should be reviewed before external release. | Apply owner governance, sign-off and evidence checks.