## Risk Dashboard
CASEY RISK REGISTER PRO
Cause - Event - Impact - Response - Quantified cost and schedule exposure.
Risks |  |  | Board Visible |  |  | QCRA P80
11 |  |  | 11 |  |  | $273.9B
QSRA P80 |  |  | Top Risk |  |  | Scenario
267.52 months |  |  | Launch manifest delay |  |  | Lower Risk
Rank | Risk | Cost EMV BN | Schedule EMV Days | Owner | Response
1 | Launch manifest delay | 5.641 | 15.9 | Launch Integration Lead | Reserve alternate launch slot, freeze payload interface, maintain launch-readiness checklist
2 | Life-support reliability | 5.613 | 15.7 | Life Support Lead | Prototype testing, redundancy, reliability growth, independent assurance
3 | Mass growth | 5.586 | 12.4 | Chief Engineer | Mass control board, margin policy, design-to-mass reviews
4 | Market escalation | 4.435 | 0 | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy
5 | Design maturity gap | 3.368 | 8.6 | Design Manager | Design maturity gates, independent review, assumption register
6 | Scope growth | 3.326 | 9.6 | Project Director | Freeze scope baseline, change board, value gates, client decision log
7 | Productivity underperformance | 2.772 | 9 | Delivery Lead | Package productivity controls, daily planning, earned value cadence
8 | Supply chain delay | 2.717 | 8.1 | Procurement Lead | Alternate suppliers, early orders, expediting, framework options
9 | Interface misalignment | 2.329 | 6 | Integration Manager | Interface control documents, weekly interface board, accountable owners
10 | Commissioning delay | 1.913 | 5.8 | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration

## Risk Register Pro
FULL RISK REGISTER PRO
Every risk has a cause, event, impact description, owner, response and quantification.
Risk ID | Category | Title | Cause | Risk Event | Impact Description | Probability % | Cost O BN | Cost M BN | Cost P BN | Cost EMV BN | Schedule O Days | Schedule M Days | Schedule P Days | Schedule EMV Days | Activity | CBS | Owner | Trigger | Mitigation | Response Strategy | Residual | Status | Board
R-S01 | Launch | Launch manifest delay | Launch provider capacity, weather windows, manifest priority or vehicle readiness | Confirmed launch slot moves or payload misses manifest gate | Programme delay, storage cost, resequencing and mission-readiness risk | 37 | 6.93 | 15.246 | 35.641 | 5.641 | 20 | 43 | 140 | 15.9 | A1400 | 01.04 | Launch Integration Lead | Launch slot not confirmed at L-12 months | Reserve alternate launch slot, freeze payload interface, maintain launch-readiness checklist | Mitigate | Medium | Open | Yes
R-S03 | Safety / Mission | Life-support reliability | ECLSS reliability, spares or redundancy evidence below target | Life-support system fails reliability growth or integrated test | Crew safety exposure, launch delay, redesign and mission abort risk | 27 | 11.88 | 20.791 | 47.521 | 5.613 | 25 | 58 | 172 | 15.7 | A1600 | 01.06 | Life Support Lead | Reliability growth misses target | Prototype testing, redundancy, reliability growth, independent assurance | Avoid / Reduce | Medium | Open | Yes
R-S02 | Technical | Mass growth | Design creep, shielding, redundancy or late payload additions increase mass | Payload mass exceeds launch and landing allowance | Launch cost, redesign, performance loss and mission safety exposure | 31 | 9.9 | 18.018 | 41.581 | 5.586 | 15 | 40 | 117 | 12.4 | A1500 | 01.05 | Chief Engineer | Mass margin below 8% | Mass control board, margin policy, design-to-mass reviews | Reduce | Medium | Open | Yes
R-002 | Commercial | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | 32 | 7.92 | 13.86 | 29.701 | 4.435 | 0 | 0 | 0 | 0 | A1800 | 01.08 | Commercial Lead | Index exceeds allowance by 3% | Early procurement, index-linked allowances, market testing, FX strategy | Mitigate | Medium | Open | Yes
R-004 | Technical | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | 27 | 5.94 | 12.474 | 26.731 | 3.368 | 15 | 32 | 94 | 8.6 | A2000 | 02.01 | Design Manager | Design deliverables miss maturity gate | Design maturity gates, independent review, assumption register | Reduce | Medium | Open | Yes
R-001 | Scope | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | 30 | 5.94 | 11.088 | 23.761 | 3.326 | 15 | 32 | 94 | 9.6 | A1700 | 01.07 | Project Director | Scope change rate exceeds 2% of package value | Freeze scope baseline, change board, value gates, client decision log | Reduce | Medium | Open | Yes
R-006 | Delivery | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | 25 | 5.94 | 11.088 | 23.761 | 2.772 | 15 | 36 | 101 | 9 | P1000 | 02.03 | Delivery Lead | SPI/CPI deteriorates for two reporting periods | Package productivity controls, daily planning, earned value cadence | Mitigate | Medium | Open | Yes
R-005 | Procurement | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | 28 | 3.96 | 9.702 | 22.276 | 2.717 | 10 | 29 | 94 | 8.1 | A2100 | 02.02 | Procurement Lead | Supplier promise date slips | Alternate suppliers, early orders, expediting, framework options | Transfer / Mitigate | Medium | Open | Yes
R-008 | Integration | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | 24 | 3.96 | 9.702 | 20.791 | 2.329 | 10 | 25 | 78 | 6 | P3000 | 03.02 | Integration Manager | Interface actions overdue | Interface control documents, weekly interface board, accountable owners | Mitigate | Medium | Open | Yes
R-007 | Handover | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | 23 | 3.96 | 8.316 | 17.82 | 1.913 | 10 | 25 | 78 | 5.8 | P2000 | 03.01 | Commissioning Lead | Test failures trend upward | Commissioning readiness plan, early test packs, digital systems integration | Reduce | Medium | Open | Yes
R-003 | Regulatory | Permits / approvals delay | Authority process, stakeholder objections or incomplete submissions | Consent milestone slips beyond baseline | Critical path delay, extended preliminaries and potential redesign conditions | 25 | 1.98 | 5.544 | 11.88 | 1.386 | 20 | 50 | 140 | 12.5 | A1900 | 01.09 | Consents Lead | Consent milestone slips by 30 days | Authority plan, consent tracker, early submissions, stakeholder map | Mitigate | Medium | Open | Yes

## Mitigation Tracker
MITIGATION TRACKER
Owner actions, triggers and residual risk conversion.
Risk ID | Risk | Owner | Mitigation Action | Trigger | Due Gate | Status | Residual | Board | Evidence Needed
R-S01 | Launch manifest delay | Launch Integration Lead | Reserve alternate launch slot, freeze payload interface, maintain launch-readiness checklist | Launch slot not confirmed at L-12 months | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-S03 | Life-support reliability | Life Support Lead | Prototype testing, redundancy, reliability growth, independent assurance | Reliability growth misses target | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-S02 | Mass growth | Chief Engineer | Mass control board, margin policy, design-to-mass reviews | Mass margin below 8% | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-002 | Market escalation | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy | Index exceeds allowance by 3% | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-004 | Design maturity gap | Design Manager | Design maturity gates, independent review, assumption register | Design deliverables miss maturity gate | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-001 | Scope growth | Project Director | Freeze scope baseline, change board, value gates, client decision log | Scope change rate exceeds 2% of package value | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-006 | Productivity underperformance | Delivery Lead | Package productivity controls, daily planning, earned value cadence | SPI/CPI deteriorates for two reporting periods | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-005 | Supply chain delay | Procurement Lead | Alternate suppliers, early orders, expediting, framework options | Supplier promise date slips | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-008 | Interface misalignment | Integration Manager | Interface control documents, weekly interface board, accountable owners | Interface actions overdue | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-007 | Commissioning delay | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration | Test failures trend upward | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-003 | Permits / approvals delay | Consents Lead | Authority plan, consent tracker, early submissions, stakeholder map | Consent milestone slips by 30 days | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log

## Board Top 10
BOARD TOP 10 RISKS
The risks most likely to change the investment decision.
Rank | Risk | Cause | Event | Impact | Cost EMV BN | Schedule EMV Days | Board Ask
1 | Launch manifest delay | Launch provider capacity, weather windows, manifest priority or vehicle readiness | Confirmed launch slot moves or payload misses manifest gate | Programme delay, storage cost, resequencing and mission-readiness risk | 5.641 | 15.9 | Approve mitigation spend or request further evidence
2 | Life-support reliability | ECLSS reliability, spares or redundancy evidence below target | Life-support system fails reliability growth or integrated test | Crew safety exposure, launch delay, redesign and mission abort risk | 5.613 | 15.7 | Approve mitigation spend or request further evidence
3 | Mass growth | Design creep, shielding, redundancy or late payload additions increase mass | Payload mass exceeds launch and landing allowance | Launch cost, redesign, performance loss and mission safety exposure | 5.586 | 12.4 | Approve mitigation spend or request further evidence
4 | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | 4.435 | 0 | Approve mitigation spend or request further evidence
5 | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | 3.368 | 8.6 | Approve mitigation spend or request further evidence
6 | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | 3.326 | 9.6 | Approve mitigation spend or request further evidence
7 | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | 2.772 | 9 | Approve mitigation spend or request further evidence
8 | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | 2.717 | 8.1 | Approve mitigation spend or request further evidence
9 | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | 2.329 | 6 | Approve mitigation spend or request further evidence
10 | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | 1.913 | 5.8 | Approve mitigation spend or request further evidence