## 00 Control Centre
CASEY v56 GLOBAL STANDARD OUTPUT PACK — Airport Infrastructure
Scenario: Faster ¦ Estimate Class: 3 ¦ Schedule Level: 5 ¦ Generated: 2026-05-05 18:08 UTC
P50 Cost |  | Cost Range | QCRA P80 | Schedule
$11.5B |  | $9.2B - $14.9B | $12.7B | 87 months
QSRA P80 |  | Risk | Confidence
91.3 months |  | Medium | 59%
Decision Engine
Use only where time value exceeds cost and interface risk.
Compresses delivery through parallel design, early procurement and acceleration premium.
Output QA Lock
✓ | Excel generated with XlsxWriter to avoid workbook repair errors
✓ | No PPTX/PDF in primary pack
✓ | Scenario visible on every workbook control sheet
✓ | All class estimates included; selected class clearly identified
✓ | All schedule levels included; selected level clearly identified
✓ | Risk register contains no zero likelihood values
✓ | QCRA and QSRA curves/tornadoes separated

## 01 Scenario Comparison
SCENARIO COMPARISON — ALL OPTIONS
Selected scenario: Faster. These values are scenario-linked and used to drive output interpretation.
Scenario | P50 Cost BN | Delta vs Selected | Schedule Months | Delta Months | Risk | Confidence | QCRA P80 BN | QSRA P80 Months | Commercial interpretation | Board decision
Base | 10.3 | -1.2 | 106 | 19 | Medium | 64 | 13.951 | 126.1 | Balanced reference case for first-pass board challenge and option testing. | Use as control baseline; approve definition, not unconditional capital.
Faster | 11.5 | 0 | 87 | 0 | Medium | 59 | 15.576 | 103.5 | Compresses delivery through parallel design, early procurement and acceleration premium. | Use only where time value exceeds cost and interface risk.
Cheaper | 9.1 | -2.4 | 114 | 27 | Medium | 58 | 12.325 | 135.6 | Reduces first cost through value engineering and tighter scope but transfers risk into delivery. | Use only if capex pressure dominates and residual risk is accepted.
Lower Risk | 11.3 | -0.2 | 117 | 30 | Low | 77 | 14.05 | 131.8 | Adds surveys, assurance, buffers and procurement validation to improve confidence. | Recommended where certainty matters more than lowest first cost.
Premium | 11.9 | 0.4 | 110 | 23 | Low | 80 | 14.796 | 124 | Strengthens suppliers, resilience, design maturity and governance for flagship delivery. | Use for mission-critical, reputational or flagship programmes.
Investor | 10.1 | -1.4 | 106 | 19 | Low | 71 | 12.558 | 119.4 | Frames the programme around capital discipline, risk transparency and investment committee challenge. | Use for sponsor, lender, partner or IC review.
Survival | 8.1 | -3.4 | 127 | 40 | Medium | 54 | 10.971 | 151.1 | Minimum viable scope and warning-heavy commercial stress case with high residual risk. | Use as a stress case only, not as the preferred baseline.

## 02 Cost Selected
SELECTED CLASS COST ESTIMATE — CLASS 3 — FASTER SCENARIO
CBS | Description | Type | Basis | P10 BN | Most Likely / P50 BN | P80 BN | P90 BN | % of P50 | Challenge Question
01.01 | Site Preparation / Enabling | Direct | Demolition, enabling, logistics and access | 0.551 | 0.689 | 0.823 | 0.896 | 0.047224 | What evidence supports Site Preparation / Enabling at $689M?
01.02 | Substructure / Foundations | Direct | Piling, groundworks, retaining and foundations | 0.735 | 0.919 | 1.098 | 1.195 | 0.062988 | What evidence supports Substructure / Foundations at $919M?
01.03 | Superstructure / Civil Works | Direct | Frame, civils, primary structures | 1.286 | 1.608 | 1.922 | 2.09 | 0.11021 | What evidence supports Superstructure / Civil Works at $1.6B?
01.04 | MEP / Systems / Utilities | Direct | Mechanical, electrical, controls and utilities | 1.286 | 1.608 | 1.922 | 2.09 | 0.11021 | What evidence supports MEP / Systems / Utilities at $1.6B?
01.05 | Specialist Equipment / Fit-Out | Direct | Permanent equipment and specialist fit-out | 1.103 | 1.379 | 1.648 | 1.793 | 0.094517 | What evidence supports Specialist Equipment / Fit-Out at $1.4B?
01.06 | Airfield Works | Direct | Runway, taxiway, apron and airfield systems | 1.286 | 1.608 | 1.922 | 2.09 | 0.11021 | What evidence supports Airfield Works at $1.6B?
01.07 | Terminal / Passenger Systems | Direct | Terminal, baggage, security and passenger systems | 0.919 | 1.149 | 1.373 | 1.494 | 0.078753 | What evidence supports Terminal / Passenger Systems at $1.1B?
01.09 | Direct Labour | Direct | Productivity, supervision and trade labour | 0.827 | 1.034 | 1.236 | 1.344 | 0.07087 | What evidence supports Direct Labour at $1.0B?
01.10 | Direct Materials | Direct | Concrete, steel, envelope, MEP materials | 0.919 | 1.149 | 1.373 | 1.494 | 0.078753 | What evidence supports Direct Materials at $1.1B?
01.11 | Plant / Equipment | Direct | Cranes, heavy plant and site equipment | 0.368 | 0.46 | 0.55 | 0.598 | 0.031528 | What evidence supports Plant / Equipment at $460M?
02.01 | General Conditions / Prelims | Indirect | Site management, safety, offices and temporary services | 0.643 | 0.804 | 0.961 | 1.045 | 0.055106 | What evidence supports General Conditions / Prelims at $804M?
02.02 | Design / Professional Fees | Indirect | Design, QS, controls, assurance and consultants | 0.643 | 0.804 | 0.961 | 1.045 | 0.055106 | What evidence supports Design / Professional Fees at $804M?
02.03 | Permits / Insurance / Bonds | Indirect | Permits, inspections, legal, bonds and insurance | 0.276 | 0.345 | 0.412 | 0.448 | 0.023646 | What evidence supports Permits / Insurance / Bonds at $345M?
03.01 | QCRA Contingency | Reserve | Known-unknown risk allowance | 0.551 | 0.689 | 0.823 | 0.896 | 0.047224 | What evidence supports QCRA Contingency at $689M?
03.02 | Management Reserve | Reserve | Sponsor-held reserve | 0.276 | 0.345 | 0.412 | 0.448 | 0.023646 | What evidence supports Management Reserve at $345M?

## 03 Cost All Classes
ALL ESTIMATE CLASS LEVELS — CLASS 1 TO 5
Class | Class Name | CBS | Description | Type | P10 BN | P50 BN | P90 BN | Maturity / Use
1 | Class 1 Definitive | 01.01 | Site Preparation / Enabling | Direct | 0.62 | 0.689 | 0.792 | Demolition, enabling, logistics and access
1 | Class 1 Definitive | 01.02 | Substructure / Foundations | Direct | 0.827 | 0.919 | 1.057 | Piling, groundworks, retaining and foundations
1 | Class 1 Definitive | 01.03 | Superstructure / Civil Works | Direct | 1.447 | 1.608 | 1.849 | Frame, civils, primary structures
1 | Class 1 Definitive | 01.04 | MEP / Systems / Utilities | Direct | 1.447 | 1.608 | 1.849 | Mechanical, electrical, controls and utilities
1 | Class 1 Definitive | 01.05 | Specialist Equipment / Fit-Out | Direct | 1.241 | 1.379 | 1.586 | Permanent equipment and specialist fit-out
1 | Class 1 Definitive | 01.06 | Airfield Works | Direct | 1.447 | 1.608 | 1.849 | Runway, taxiway, apron and airfield systems
1 | Class 1 Definitive | 01.07 | Terminal / Passenger Systems | Direct | 1.034 | 1.149 | 1.321 | Terminal, baggage, security and passenger systems
1 | Class 1 Definitive | 01.09 | Direct Labour | Direct | 0.931 | 1.034 | 1.189 | Productivity, supervision and trade labour
1 | Class 1 Definitive | 01.10 | Direct Materials | Direct | 1.034 | 1.149 | 1.321 | Concrete, steel, envelope, MEP materials
1 | Class 1 Definitive | 01.11 | Plant / Equipment | Direct | 0.414 | 0.46 | 0.529 | Cranes, heavy plant and site equipment
1 | Class 1 Definitive | 02.01 | General Conditions / Prelims | Indirect | 0.724 | 0.804 | 0.925 | Site management, safety, offices and temporary services
1 | Class 1 Definitive | 02.02 | Design / Professional Fees | Indirect | 0.724 | 0.804 | 0.925 | Design, QS, controls, assurance and consultants
1 | Class 1 Definitive | 02.03 | Permits / Insurance / Bonds | Indirect | 0.31 | 0.345 | 0.397 | Permits, inspections, legal, bonds and insurance
1 | Class 1 Definitive | 03.01 | QCRA Contingency | Reserve | 0.62 | 0.689 | 0.792 | Known-unknown risk allowance
1 | Class 1 Definitive | 03.02 | Management Reserve | Reserve | 0.31 | 0.345 | 0.397 | Sponsor-held reserve
2 | Class 2 Control | 01.01 | Site Preparation / Enabling | Direct | 0.586 | 0.689 | 0.827 | Demolition, enabling, logistics and access
2 | Class 2 Control | 01.02 | Substructure / Foundations | Direct | 0.781 | 0.919 | 1.103 | Piling, groundworks, retaining and foundations
2 | Class 2 Control | 01.03 | Superstructure / Civil Works | Direct | 1.367 | 1.608 | 1.93 | Frame, civils, primary structures
2 | Class 2 Control | 01.04 | MEP / Systems / Utilities | Direct | 1.367 | 1.608 | 1.93 | Mechanical, electrical, controls and utilities
2 | Class 2 Control | 01.05 | Specialist Equipment / Fit-Out | Direct | 1.172 | 1.379 | 1.655 | Permanent equipment and specialist fit-out
2 | Class 2 Control | 01.06 | Airfield Works | Direct | 1.367 | 1.608 | 1.93 | Runway, taxiway, apron and airfield systems
2 | Class 2 Control | 01.07 | Terminal / Passenger Systems | Direct | 0.977 | 1.149 | 1.379 | Terminal, baggage, security and passenger systems
2 | Class 2 Control | 01.09 | Direct Labour | Direct | 0.879 | 1.034 | 1.241 | Productivity, supervision and trade labour
2 | Class 2 Control | 01.10 | Direct Materials | Direct | 0.977 | 1.149 | 1.379 | Concrete, steel, envelope, MEP materials
2 | Class 2 Control | 01.11 | Plant / Equipment | Direct | 0.391 | 0.46 | 0.552 | Cranes, heavy plant and site equipment
2 | Class 2 Control | 02.01 | General Conditions / Prelims | Indirect | 0.683 | 0.804 | 0.965 | Site management, safety, offices and temporary services
2 | Class 2 Control | 02.02 | Design / Professional Fees | Indirect | 0.683 | 0.804 | 0.965 | Design, QS, controls, assurance and consultants
2 | Class 2 Control | 02.03 | Permits / Insurance / Bonds | Indirect | 0.293 | 0.345 | 0.414 | Permits, inspections, legal, bonds and insurance
2 | Class 2 Control | 03.01 | QCRA Contingency | Reserve | 0.586 | 0.689 | 0.827 | Known-unknown risk allowance
2 | Class 2 Control | 03.02 | Management Reserve | Reserve | 0.293 | 0.345 | 0.414 | Sponsor-held reserve
3 | Class 3 Budget | 01.01 | Site Preparation / Enabling | Direct | 0.551 | 0.689 | 0.896 | Demolition, enabling, logistics and access
3 | Class 3 Budget | 01.02 | Substructure / Foundations | Direct | 0.735 | 0.919 | 1.195 | Piling, groundworks, retaining and foundations
3 | Class 3 Budget | 01.03 | Superstructure / Civil Works | Direct | 1.286 | 1.608 | 2.09 | Frame, civils, primary structures
3 | Class 3 Budget | 01.04 | MEP / Systems / Utilities | Direct | 1.286 | 1.608 | 2.09 | Mechanical, electrical, controls and utilities
3 | Class 3 Budget | 01.05 | Specialist Equipment / Fit-Out | Direct | 1.103 | 1.379 | 1.793 | Permanent equipment and specialist fit-out
3 | Class 3 Budget | 01.06 | Airfield Works | Direct | 1.286 | 1.608 | 2.09 | Runway, taxiway, apron and airfield systems
3 | Class 3 Budget | 01.07 | Terminal / Passenger Systems | Direct | 0.919 | 1.149 | 1.494 | Terminal, baggage, security and passenger systems
3 | Class 3 Budget | 01.09 | Direct Labour | Direct | 0.827 | 1.034 | 1.344 | Productivity, supervision and trade labour
3 | Class 3 Budget | 01.10 | Direct Materials | Direct | 0.919 | 1.149 | 1.494 | Concrete, steel, envelope, MEP materials
3 | Class 3 Budget | 01.11 | Plant / Equipment | Direct | 0.368 | 0.46 | 0.598 | Cranes, heavy plant and site equipment
3 | Class 3 Budget | 02.01 | General Conditions / Prelims | Indirect | 0.643 | 0.804 | 1.045 | Site management, safety, offices and temporary services
3 | Class 3 Budget | 02.02 | Design / Professional Fees | Indirect | 0.643 | 0.804 | 1.045 | Design, QS, controls, assurance and consultants
3 | Class 3 Budget | 02.03 | Permits / Insurance / Bonds | Indirect | 0.276 | 0.345 | 0.448 | Permits, inspections, legal, bonds and insurance
3 | Class 3 Budget | 03.01 | QCRA Contingency | Reserve | 0.551 | 0.689 | 0.896 | Known-unknown risk allowance
3 | Class 3 Budget | 03.02 | Management Reserve | Reserve | 0.276 | 0.345 | 0.448 | Sponsor-held reserve
4 | Class 4 Feasibility | 01.01 | Site Preparation / Enabling | Direct | 0.482 | 0.689 | 1.033 | Demolition, enabling, logistics and access
4 | Class 4 Feasibility | 01.02 | Substructure / Foundations | Direct | 0.643 | 0.919 | 1.379 | Piling, groundworks, retaining and foundations
4 | Class 4 Feasibility | 01.03 | Superstructure / Civil Works | Direct | 1.126 | 1.608 | 2.412 | Frame, civils, primary structures
4 | Class 4 Feasibility | 01.04 | MEP / Systems / Utilities | Direct | 1.126 | 1.608 | 2.412 | Mechanical, electrical, controls and utilities
4 | Class 4 Feasibility | 01.05 | Specialist Equipment / Fit-Out | Direct | 0.965 | 1.379 | 2.069 | Permanent equipment and specialist fit-out
4 | Class 4 Feasibility | 01.06 | Airfield Works | Direct | 1.126 | 1.608 | 2.412 | Runway, taxiway, apron and airfield systems
4 | Class 4 Feasibility | 01.07 | Terminal / Passenger Systems | Direct | 0.804 | 1.149 | 1.724 | Terminal, baggage, security and passenger systems
4 | Class 4 Feasibility | 01.09 | Direct Labour | Direct | 0.724 | 1.034 | 1.551 | Productivity, supervision and trade labour
4 | Class 4 Feasibility | 01.10 | Direct Materials | Direct | 0.804 | 1.149 | 1.724 | Concrete, steel, envelope, MEP materials
4 | Class 4 Feasibility | 01.11 | Plant / Equipment | Direct | 0.322 | 0.46 | 0.69 | Cranes, heavy plant and site equipment
4 | Class 4 Feasibility | 02.01 | General Conditions / Prelims | Indirect | 0.563 | 0.804 | 1.206 | Site management, safety, offices and temporary services
4 | Class 4 Feasibility | 02.02 | Design / Professional Fees | Indirect | 0.563 | 0.804 | 1.206 | Design, QS, controls, assurance and consultants
4 | Class 4 Feasibility | 02.03 | Permits / Insurance / Bonds | Indirect | 0.241 | 0.345 | 0.517 | Permits, inspections, legal, bonds and insurance
4 | Class 4 Feasibility | 03.01 | QCRA Contingency | Reserve | 0.482 | 0.689 | 1.033 | Known-unknown risk allowance
4 | Class 4 Feasibility | 03.02 | Management Reserve | Reserve | 0.241 | 0.345 | 0.517 | Sponsor-held reserve
5 | Class 5 Concept | 01.01 | Site Preparation / Enabling | Direct | 0.344 | 0.689 | 1.378 | Demolition, enabling, logistics and access
5 | Class 5 Concept | 01.02 | Substructure / Foundations | Direct | 0.46 | 0.919 | 1.838 | Piling, groundworks, retaining and foundations
5 | Class 5 Concept | 01.03 | Superstructure / Civil Works | Direct | 0.804 | 1.608 | 3.216 | Frame, civils, primary structures
5 | Class 5 Concept | 01.04 | MEP / Systems / Utilities | Direct | 0.804 | 1.608 | 3.216 | Mechanical, electrical, controls and utilities
5 | Class 5 Concept | 01.05 | Specialist Equipment / Fit-Out | Direct | 0.69 | 1.379 | 2.758 | Permanent equipment and specialist fit-out
5 | Class 5 Concept | 01.06 | Airfield Works | Direct | 0.804 | 1.608 | 3.216 | Runway, taxiway, apron and airfield systems
5 | Class 5 Concept | 01.07 | Terminal / Passenger Systems | Direct | 0.575 | 1.149 | 2.298 | Terminal, baggage, security and passenger systems
5 | Class 5 Concept | 01.09 | Direct Labour | Direct | 0.517 | 1.034 | 2.068 | Productivity, supervision and trade labour
5 | Class 5 Concept | 01.10 | Direct Materials | Direct | 0.575 | 1.149 | 2.298 | Concrete, steel, envelope, MEP materials
5 | Class 5 Concept | 01.11 | Plant / Equipment | Direct | 0.23 | 0.46 | 0.92 | Cranes, heavy plant and site equipment
5 | Class 5 Concept | 02.01 | General Conditions / Prelims | Indirect | 0.402 | 0.804 | 1.608 | Site management, safety, offices and temporary services
5 | Class 5 Concept | 02.02 | Design / Professional Fees | Indirect | 0.402 | 0.804 | 1.608 | Design, QS, controls, assurance and consultants
5 | Class 5 Concept | 02.03 | Permits / Insurance / Bonds | Indirect | 0.172 | 0.345 | 0.69 | Permits, inspections, legal, bonds and insurance
5 | Class 5 Concept | 03.01 | QCRA Contingency | Reserve | 0.344 | 0.689 | 1.378 | Known-unknown risk allowance
5 | Class 5 Concept | 03.02 | Management Reserve | Reserve | 0.172 | 0.345 | 0.69 | Sponsor-held reserve

## 04 Risk Register
FULL RISK REGISTER — CAUSE / EVENT / IMPACT / MITIGATION / QUANTIFIED
ID | Category | Risk | Cause | Event | Impact | Owner | Mitigation | Trigger | Probability % | Cost O BN | Cost ML BN | Cost P BN | Schedule O Days | Schedule ML Days | Schedule P Days | Cost EMV BN | Schedule EMV Days | Status
R-001 | Scope | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | Project Director | Freeze scope baseline, change board, value gates, client decision log | Scope change rate exceeds 2% of package value | 0.49 | 0.114 | 0.253 | 0.544 | 8.1 | 18 | 40.5 | 0.153 | 11.2 | Open
R-004 | Technical | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | Design Manager | Design maturity gates, independent review, assumption register | Design deliverables miss maturity gate | 0.44 | 0.135 | 0.299 | 0.643 | 9.9 | 22 | 49.5 | 0.163 | 12.2 | Open
R-015 | Sector | Funding / approval gate delay | Investment approvals or staged funding gates not aligned with procurement | Capital release is delayed | Procurement missed windows and schedule slippage | Sponsor | Approval roadmap and early board papers | Approval date slips | 0.49 | 0.062 | 0.138 | 0.31 | 16.8 | 42 | 96.6 | 0.085 | 26.1 | Open
R-022 | Sector | Regulatory assurance delay | Regulator or authority review cycle not fully allowed | Approval takes longer than baseline | Critical path delay and extra assurance cost | Consents Lead | Regulatory roadmap and early engagement | Submission returned | 0.44 | 0.093 | 0.207 | 0.466 | 14.8 | 37 | 85.1 | 0.115 | 20.7 | Open
R-A01 | Operations | Operational phasing disruption | Works in or near live airport operations constrain access and sequencing | Operational restrictions reduce productive windows | Delay, night-work premiums, stakeholder disruption and ORAT pressure | ORAT Lead | Phasing simulation, possession plan, airport ops integration board | Possession windows rejected | 0.49 | 0.093 | 0.207 | 0.445 | 6.3 | 14 | 31.5 | 0.125 | 8.7 | Open
R-008 | Integration | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | Integration Manager | Interface control documents, weekly interface board, accountable owners | Interface actions overdue | 0.4 | 0.114 | 0.253 | 0.544 | 17.1 | 38 | 85.5 | 0.125 | 19.2 | Open
R-005 | Procurement | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | Procurement Lead | Alternate suppliers, early orders, expediting, framework options | Supplier promise date slips | 0.47 | 0.072 | 0.161 | 0.346 | 13.5 | 30 | 67.5 | 0.093 | 17.8 | Open
R-002 | Commercial | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy | Index exceeds allowance by 3% | 0.53 | 0.072 | 0.161 | 0.346 | 4.5 | 10 | 22.5 | 0.105 | 6.7 | Open
R-A02 | Systems | Baggage / security systems integration | Complex passenger systems integration and vendor interfaces uncertain | Integrated airport systems do not pass readiness testing | Commissioning delay, passenger disruption and late operational readiness | Systems Lead | Factory acceptance testing, integration lab, ORAT dry-runs | FAT/SAT defect trend above threshold | 0.4 | 0.093 | 0.207 | 0.445 | 15.3 | 34 | 76.5 | 0.102 | 17.2 | Open
R-023 | Sector | Procurement strategy misalignment | Package strategy does not match market capacity or risk transfer | Tenders return above budget or fail | Retendering, cost growth and schedule slip | Commercial Lead | Market sounding and package strategy review | Low bidder response | 0.49 | 0.031 | 0.069 | 0.155 | 16.8 | 42 | 96.6 | 0.043 | 26.1 | Open
R-007 | Handover | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration | Test failures trend upward | 0.37 | 0.135 | 0.299 | 0.643 | 2.7 | 6 | 13.5 | 0.137 | 2.8 | Open
R-014 | Sector | Stakeholder change | Sponsor, operator or authority requirements evolve late | Requirements change after baseline freeze | Scope growth, redesign and approval delays | Project Director | Decision log, change board and stakeholder gates | Late decision count increases | 0.44 | 0.047 | 0.104 | 0.233 | 14.8 | 37 | 85.1 | 0.058 | 20.7 | Open
R-021 | Sector | Utilities diversion / enabling risk | Unknown utilities, access or enabling works underestimated | Enabling works expand or delay critical start | Cost growth, access delay and resequencing | Enabling Works Lead | Surveys, trial pits and early utility agreements | Unknown utilities found | 0.39 | 0.078 | 0.173 | 0.388 | 12.8 | 32 | 73.6 | 0.085 | 15.8 | Open
R-012 | Sector | Cyber / controls integration | Operational technology and control systems interfaces immature | Controls integration fails testing | Commissioning delay, resilience issue and operational risk | Systems Lead | Early cyber review, FAT/SAT plan, integration lab | Controls defect trend increases | 0.34 | 0.093 | 0.207 | 0.466 | 10.8 | 27 | 62.1 | 0.089 | 11.7 | Open
R-006 | Delivery | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | Delivery Lead | Package productivity controls, daily planning, earned value cadence | SPI/CPI deteriorates for two reporting periods | 0.41 | 0.052 | 0.115 | 0.247 | 11.7 | 26 | 58.5 | 0.058 | 13.5 | Open
R-020 | Sector | Design change after procurement | Procurement released before design maturity is sufficient | Vendor packages require change | Variation cost, rework and programme delay | Design Manager | Design freeze gates and change impact board | IFC maturity below gate | 0.34 | 0.062 | 0.138 | 0.31 | 10.8 | 27 | 62.1 | 0.059 | 11.7 | Open
R-013 | Sector | Weather / environmental disruption | Extreme weather, environmental windows or site constraints not fully allowed | Workface access or productivity is disrupted | Delay, access cost and resequencing | Construction Manager | Weather calendars, contingency workfronts, protection strategy | Weather downtime exceeds allowance | 0.39 | 0.031 | 0.069 | 0.155 | 12.8 | 32 | 73.6 | 0.034 | 15.8 | Open
R-003 | Regulatory | Permits / approvals delay | Authority process, stakeholder objections or incomplete submissions | Consent milestone slips beyond baseline | Critical path delay, extended preliminaries and potential redesign conditions | Consents Lead | Authority plan, consent tracker, early submissions, stakeholder map | Consent milestone slips by 30 days | 0.41 | 0.052 | 0.115 | 0.247 | 4.5 | 10 | 22.5 | 0.058 | 5.2 | Open
R-011 | Sector | Quality failure / rework | Installation quality, vendor QA or inspection regime below need | Inspection failure triggers rework | Rework cost, schedule delay and confidence loss | Quality Manager | ITPs, hold points, vendor QA, right-first-time reviews | NCR trend increases | 0.29 | 0.078 | 0.173 | 0.388 | 8.8 | 22 | 50.6 | 0.063 | 8.1 | Open
R-019 | Sector | Supply chain insolvency | Tier 2/3 financial health is unknown or weak | Critical supplier fails or cannot perform | Replacement cost, procurement delay and claims exposure | Procurement Lead | Financial checks, dual sourcing, step-in rights | Supplier credit alert | 0.29 | 0.047 | 0.104 | 0.233 | 8.8 | 22 | 50.6 | 0.038 | 8.1 | Open
R-010 | Sector | Resource availability | Labour, specialist supervisors or commissioning teams constrained | Required resources are unavailable when planned | Productivity loss, resequencing and higher preliminaries | Delivery Lead | Resource loading, framework call-offs and labour strategy | Resource histogram red flag | 0.24 | 0.062 | 0.138 | 0.31 | 6.8 | 17 | 39.1 | 0.042 | 5.2 | Open
R-017 | Sector | Data / estimate basis weakness | Estimate source data, quantities or benchmarks are incomplete | Baseline cannot be defended under challenge | Confidence reduction and rework of cost plan | Cost Lead | Assumption register, benchmark evidence, quantity validation | Unknown allowance exceeds threshold | 0.19 | 0.093 | 0.207 | 0.466 | 4.8 | 12 | 27.6 | 0.05 | 2.9 | Open
R-018 | Sector | Interface ownership gap | RACI and package boundaries are unclear across packages | Interface issue has no accountable owner | Delay, claims and fragmented accountability | Integration Manager | Interface control documents and owner matrix | Interface actions overdue | 0.24 | 0.031 | 0.069 | 0.155 | 6.8 | 17 | 39.1 | 0.021 | 5.2 | Open
R-025 | Sector | Benefits realisation risk | Commercial benefits rely on optimistic demand or ramp-up | Ramp-up underperforms plan | Revenue / value case weakens | Sponsor | Benefits model validation and ramp-up sensitivity | Demand evidence weak | 0.19 | 0.062 | 0.138 | 0.31 | 4.8 | 12 | 27.6 | 0.033 | 2.9 | Open
R-009 | Sector | Commercial claims escalation | Contract ambiguity, late changes and fragmented accountability | Claims submitted above allowance | Commercial pressure, management distraction and increased outturn cost | Commercial Lead | Tight change control and dispute avoidance board | Claim volume exceeds baseline | 0.19 | 0.047 | 0.104 | 0.233 | 4.8 | 12 | 27.6 | 0.025 | 2.9 | Open
R-016 | Sector | Commissioning readiness gap | Incomplete test packs, operational readiness or training gaps | Commissioning starts without readiness | Repeated tests, handover delay and operational risk | Commissioning Lead | Readiness dashboard, integrated test plan, ORAT | Readiness score below threshold | 0.14 | 0.078 | 0.173 | 0.388 | 2.8 | 7 | 16.1 | 0.031 | 1.2 | Open
R-024 | Sector | Operational readiness shortfall | Operating model, training or maintenance strategy immature | Asset cannot enter service as planned | Delayed opening and benefit deferral | Operations Lead | ORAT/readiness plan and service transition gate | Readiness gate failed | 0.14 | 0.047 | 0.104 | 0.233 | 2.8 | 7 | 16.1 | 0.018 | 1.2 | Open

## 05 QCRA QSRA Curves
QCRA + QSRA CURVES — SEPARATE DISTRIBUTIONS
Percentile | QCRA Cost BN | QSRA Months
1 | 8.761 | 76.17
5 | 9.485 | 79.18
10 | 9.904 | 80.87
20 | 10.426 | 82.93
30 | 10.823 | 84.46
40 | 11.169 | 85.77
50 | 11.5 | 87
60 | 11.841 | 88.25
70 | 12.22 | 89.62
80 | 12.685 | 91.27
85 | 12.985 | 92.32
90 | 13.354 | 93.59
95 | 13.943 | 95.59
99 | 15.096 | 99.37

## 06 Tornado Drivers
TORNADO DRIVERS — QCRA COST AND QSRA SCHEDULE SEPARATED
Rank | QCRA Cost Driver | ID | Cost EMV BN | Owner | Mitigation | Rank | QSRA Schedule Driver | ID | Schedule EMV Days | Owner | Mitigation
1 | Design maturity gap | R-004 | 0.163 | Design Manager | Design maturity gates, independent review, assumption register | 1 | Funding / approval gate delay | R-015 | 26.1 | Sponsor | Approval roadmap and early board papers
2 | Scope growth | R-001 | 0.153 | Project Director | Freeze scope baseline, change board, value gates, client decision log | 2 | Procurement strategy misalignment | R-023 | 26.1 | Commercial Lead | Market sounding and package strategy review
3 | Commissioning delay | R-007 | 0.137 | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration | 3 | Regulatory assurance delay | R-022 | 20.7 | Consents Lead | Regulatory roadmap and early engagement
4 | Operational phasing disruption | R-A01 | 0.125 | ORAT Lead | Phasing simulation, possession plan, airport ops integration board | 4 | Stakeholder change | R-014 | 20.7 | Project Director | Decision log, change board and stakeholder gates
5 | Interface misalignment | R-008 | 0.125 | Integration Manager | Interface control documents, weekly interface board, accountable owners | 5 | Interface misalignment | R-008 | 19.2 | Integration Manager | Interface control documents, weekly interface board, accountable owners
6 | Regulatory assurance delay | R-022 | 0.115 | Consents Lead | Regulatory roadmap and early engagement | 6 | Supply chain delay | R-005 | 17.8 | Procurement Lead | Alternate suppliers, early orders, expediting, framework options
7 | Market escalation | R-002 | 0.105 | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy | 7 | Baggage / security systems integration | R-A02 | 17.2 | Systems Lead | Factory acceptance testing, integration lab, ORAT dry-runs
8 | Baggage / security systems integration | R-A02 | 0.102 | Systems Lead | Factory acceptance testing, integration lab, ORAT dry-runs | 8 | Utilities diversion / enabling risk | R-021 | 15.8 | Enabling Works Lead | Surveys, trial pits and early utility agreements
9 | Supply chain delay | R-005 | 0.093 | Procurement Lead | Alternate suppliers, early orders, expediting, framework options | 9 | Weather / environmental disruption | R-013 | 15.8 | Construction Manager | Weather calendars, contingency workfronts, protection strategy
10 | Cyber / controls integration | R-012 | 0.089 | Systems Lead | Early cyber review, FAT/SAT plan, integration lab | 10 | Productivity underperformance | R-006 | 13.5 | Delivery Lead | Package productivity controls, daily planning, earned value cadence
11 | Funding / approval gate delay | R-015 | 0.085 | Sponsor | Approval roadmap and early board papers | 11 | Design maturity gap | R-004 | 12.2 | Design Manager | Design maturity gates, independent review, assumption register
12 | Utilities diversion / enabling risk | R-021 | 0.085 | Enabling Works Lead | Surveys, trial pits and early utility agreements | 12 | Cyber / controls integration | R-012 | 11.7 | Systems Lead | Early cyber review, FAT/SAT plan, integration lab
13 | Quality failure / rework | R-011 | 0.063 | Quality Manager | ITPs, hold points, vendor QA, right-first-time reviews | 13 | Design change after procurement | R-020 | 11.7 | Design Manager | Design freeze gates and change impact board
14 | Design change after procurement | R-020 | 0.059 | Design Manager | Design freeze gates and change impact board | 14 | Scope growth | R-001 | 11.2 | Project Director | Freeze scope baseline, change board, value gates, client decision log
15 | Stakeholder change | R-014 | 0.058 | Project Director | Decision log, change board and stakeholder gates | 15 | Operational phasing disruption | R-A01 | 8.7 | ORAT Lead | Phasing simulation, possession plan, airport ops integration board

## 07 Schedule Levels
ALL SCHEDULE LEVELS — LEVEL 1 TO 5
Level | Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
1 | M100 | Milestone | Investment approval |  | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M200 | Milestone | Design complete | M100 | 17 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M300 | Milestone | Procurement complete | M200 | 13 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M400 | Milestone | Delivery complete | M300 | 35 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M500 | Milestone | Ready for operations | M400 | 13 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M600 | Milestone | Handover | M500 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1000 | Governance | Project initiation / controls setup |  | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1100 | Business Case | Strategic brief, funding and approval | A1000 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1200 | Scope | Requirements definition and scope freeze | A1100 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1300 | Design | Concept / reference architecture | A1200 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1600 | Design | Detailed design / IFC development | A1300 | 9 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1700 | Procurement | Long-lead procurement | A1500 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 19 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A2000 | Integration | Systems integration and testing | A1900 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1000 | Governance | Project initiation / controls setup |  | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1100 | Business Case | Strategic brief, funding and approval | A1000 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1200 | Scope | Requirements definition and scope freeze | A1100 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1300 | Design | Concept / reference architecture | A1200 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1600 | Design | Detailed design / IFC development | A1300 | 9 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1700 | Procurement | Long-lead procurement | A1500 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 19 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A2000 | Integration | Systems integration and testing | A1900 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1000 | Governance | Project initiation / controls setup |  | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1100 | Business Case | Strategic brief, funding and approval | A1000 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1200 | Scope | Requirements definition and scope freeze | A1100 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1300 | Design | Concept / reference architecture | A1200 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1600 | Design | Detailed design / IFC development | A1300 | 9 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1700 | Procurement | Long-lead procurement | A1500 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 19 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A2000 | Integration | Systems integration and testing | A1900 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P1000 | Package | Airfield works | A1900 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P2000 | Package | Terminal systems | P1000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P3000 | Package | Baggage/security systems | P2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P4000 | Package | ORAT | P3000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1000 | Governance | Project initiation / controls setup |  | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1100 | Business Case | Strategic brief, funding and approval | A1000 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1200 | Scope | Requirements definition and scope freeze | A1100 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1300 | Design | Concept / reference architecture | A1200 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1600 | Design | Detailed design / IFC development | A1300 | 9 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1700 | Procurement | Long-lead procurement | A1500 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 19 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A2000 | Integration | Systems integration and testing | A1900 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P1000 | Package | Airfield works | A1900 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P1100 | Activity | Airfield works - mobilise / method | A1900 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P1200 | Activity | Airfield works - execute works | P1100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P1300 | Activity | Airfield works - inspect / closeout | P1200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P2000 | Package | Terminal systems | P1000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P2100 | Activity | Terminal systems - mobilise / method | P1000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P2200 | Activity | Terminal systems - execute works | P2100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P2300 | Activity | Terminal systems - inspect / closeout | P2200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P3000 | Package | Baggage/security systems | P2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P3100 | Activity | Baggage/security systems - mobilise / method | P2000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P3200 | Activity | Baggage/security systems - execute works | P3100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P3300 | Activity | Baggage/security systems - inspect / closeout | P3200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P4000 | Package | ORAT | P3000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P4100 | Activity | ORAT - mobilise / method | P3000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P4200 | Activity | ORAT - execute works | P4100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P4300 | Activity | ORAT - inspect / closeout | P4200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## 08 Basis + Audit
BASIS, LIMITATIONS AND AUDIT
Field | Value
Scenario | Faster
Project | Airport Infrastructure
Subsector | Airport / Aviation
Location | Global / Not specified
Mode | Earth
Estimate class | 3
Schedule level | 5
Generated | 2026-05-05 18:08 UTC
Model version | v56 Global Standard
Limitation | First-pass project controls intelligence. Validate against project-specific tender, survey, design and schedule evidence before capital commitment.
Methodology | Cost is parametric/benchmark/factor-based; QCRA and QSRA are separated; risks are cause-event-impact structured; scenarios change cost, schedule, risk and confidence.
Output standard | PDF/PPTX excluded from primary output pack to avoid weak or unreadable exports. Excel, schedule and audit outputs are the source of truth.