## Board Summary
Field | Value
Generated | 2026-05-02T19:07:50.482281
Version | v23 Real Deal Edition
Title | AI Data Centre Campus
Client | Microsoft
Executive Summary | AI Data Centre Campus has been classified as Digital Infrastructure / Hyperscale Data Centre in Saudi Arabia / GCC. CASEY estimates $5.6B P50 cost, $4.5B to $7.3B range, 46 month baseline, Medium risk and 64% confidence under the Base scenario.
Mode | Earth
Subsector | Digital Infrastructure / Hyperscale Data Centre
Location | Saudi Arabia / GCC
Scenario | Base
Cost P10 | $4.5B
Cost P50 | $5.6B
Cost P90 | $7.3B
Schedule | 46 months
QCRA P80 | $8.4B
QSRA P80 | 58.08
Risk | Medium
Confidence | 64%

## Primary Cost Estimate
CBS | Description | Type | Basis | P10 BN | P50 BN | P90 BN | Impact Basis
01.01 | Site Preparation / Enabling | Direct | Demolition, enabling, logistics and access | 0.271 | 0.339 | 0.44 | Site Preparation / Enabling priced as 6.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
01.02 | Substructure / Foundations | Direct | Piling, groundworks, retaining and foundations | 0.361 | 0.451 | 0.587 | Substructure / Foundations priced as 8.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
01.03 | Superstructure / Civil Works | Direct | Frame, civils, primary structures | 0.632 | 0.79 | 1.027 | Superstructure / Civil Works priced as 14.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
01.04 | MEP / Systems / Utilities | Direct | Mechanical, electrical, controls and utilities | 0.632 | 0.79 | 1.027 | MEP / Systems / Utilities priced as 14.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
01.05 | Specialist Equipment / Fit-Out | Direct | Permanent equipment and specialist fit-out | 0.542 | 0.677 | 0.88 | Specialist Equipment / Fit-Out priced as 12.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
01.06 | Data Halls / White Space | Direct | Server halls, fit-out and critical rooms | 0.587 | 0.734 | 0.954 | Data Halls / White Space priced as 13.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
01.07 | Power Train / Substations | Direct | HV/MV gear, UPS, generators and substations | 0.722 | 0.903 | 1.174 | Power Train / Substations priced as 16.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
01.08 | Cooling Systems | Direct | Chillers, heat rejection, CRAH/CRAC, water systems | 0.542 | 0.677 | 0.88 | Cooling Systems priced as 12.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
01.09 | Direct Labour | Direct | Productivity, supervision and trade labour | 0.406 | 0.508 | 0.66 | Direct Labour priced as 9.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
01.10 | Direct Materials | Direct | Concrete, steel, envelope, MEP materials | 0.451 | 0.564 | 0.734 | Direct Materials priced as 10.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
01.11 | Plant / Equipment | Direct | Cranes, heavy plant and site equipment | 0.181 | 0.226 | 0.293 | Plant / Equipment priced as 4.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
02.01 | General Conditions / Prelims | Indirect | Site management, safety, offices and temporary services | 0.316 | 0.395 | 0.514 | General Conditions / Prelims priced as 7.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
02.02 | Design / Professional Fees | Indirect | Design, QS, controls, assurance and consultants | 0.316 | 0.395 | 0.514 | Design / Professional Fees priced as 7.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
02.03 | Permits / Insurance / Bonds | Indirect | Permits, inspections, legal, bonds and insurance | 0.135 | 0.169 | 0.22 | Permits / Insurance / Bonds priced as 3.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
03.01 | QCRA Contingency | Reserve | Known-unknown risk allowance | 0.271 | 0.339 | 0.44 | QCRA Contingency priced as 6.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.
03.02 | Management Reserve | Reserve | Sponsor-held reserve | 0.135 | 0.169 | 0.22 | Management Reserve priced as 3.0% of P50 from sector template, location factor 1.35, scale factor 1.00, complexity factor 1.10.

## Class 1 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
1 | 01.01 | Site Preparation / Enabling | 0.305 | 0.339 | 0.39 | 65-100% definition maturity
1 | 01.02 | Substructure / Foundations | 0.406 | 0.451 | 0.519 | 65-100% definition maturity
1 | 01.03 | Superstructure / Civil Works | 0.711 | 0.79 | 0.908 | 65-100% definition maturity
1 | 01.04 | MEP / Systems / Utilities | 0.711 | 0.79 | 0.908 | 65-100% definition maturity
1 | 01.05 | Specialist Equipment / Fit-Out | 0.609 | 0.677 | 0.779 | 65-100% definition maturity
1 | 01.06 | Data Halls / White Space | 0.661 | 0.734 | 0.844 | 65-100% definition maturity
1 | 01.07 | Power Train / Substations | 0.813 | 0.903 | 1.038 | 65-100% definition maturity
1 | 01.08 | Cooling Systems | 0.609 | 0.677 | 0.779 | 65-100% definition maturity
1 | 01.09 | Direct Labour | 0.457 | 0.508 | 0.584 | 65-100% definition maturity
1 | 01.10 | Direct Materials | 0.508 | 0.564 | 0.649 | 65-100% definition maturity
1 | 01.11 | Plant / Equipment | 0.203 | 0.226 | 0.26 | 65-100% definition maturity
1 | 02.01 | General Conditions / Prelims | 0.356 | 0.395 | 0.454 | 65-100% definition maturity
1 | 02.02 | Design / Professional Fees | 0.356 | 0.395 | 0.454 | 65-100% definition maturity
1 | 02.03 | Permits / Insurance / Bonds | 0.152 | 0.169 | 0.194 | 65-100% definition maturity
1 | 03.01 | QCRA Contingency | 0.305 | 0.339 | 0.39 | 65-100% definition maturity
1 | 03.02 | Management Reserve | 0.152 | 0.169 | 0.194 | 65-100% definition maturity

## Class 2 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
2 | 01.01 | Site Preparation / Enabling | 0.288 | 0.339 | 0.407 | 30-75% definition maturity
2 | 01.02 | Substructure / Foundations | 0.383 | 0.451 | 0.541 | 30-75% definition maturity
2 | 01.03 | Superstructure / Civil Works | 0.671 | 0.79 | 0.948 | 30-75% definition maturity
2 | 01.04 | MEP / Systems / Utilities | 0.671 | 0.79 | 0.948 | 30-75% definition maturity
2 | 01.05 | Specialist Equipment / Fit-Out | 0.575 | 0.677 | 0.812 | 30-75% definition maturity
2 | 01.06 | Data Halls / White Space | 0.624 | 0.734 | 0.881 | 30-75% definition maturity
2 | 01.07 | Power Train / Substations | 0.768 | 0.903 | 1.084 | 30-75% definition maturity
2 | 01.08 | Cooling Systems | 0.575 | 0.677 | 0.812 | 30-75% definition maturity
2 | 01.09 | Direct Labour | 0.432 | 0.508 | 0.61 | 30-75% definition maturity
2 | 01.10 | Direct Materials | 0.479 | 0.564 | 0.677 | 30-75% definition maturity
2 | 01.11 | Plant / Equipment | 0.192 | 0.226 | 0.271 | 30-75% definition maturity
2 | 02.01 | General Conditions / Prelims | 0.336 | 0.395 | 0.474 | 30-75% definition maturity
2 | 02.02 | Design / Professional Fees | 0.336 | 0.395 | 0.474 | 30-75% definition maturity
2 | 02.03 | Permits / Insurance / Bonds | 0.144 | 0.169 | 0.203 | 30-75% definition maturity
2 | 03.01 | QCRA Contingency | 0.288 | 0.339 | 0.407 | 30-75% definition maturity
2 | 03.02 | Management Reserve | 0.144 | 0.169 | 0.203 | 30-75% definition maturity

## Class 3 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
3 | 01.01 | Site Preparation / Enabling | 0.271 | 0.339 | 0.441 | 10-40% definition maturity
3 | 01.02 | Substructure / Foundations | 0.361 | 0.451 | 0.586 | 10-40% definition maturity
3 | 01.03 | Superstructure / Civil Works | 0.632 | 0.79 | 1.027 | 10-40% definition maturity
3 | 01.04 | MEP / Systems / Utilities | 0.632 | 0.79 | 1.027 | 10-40% definition maturity
3 | 01.05 | Specialist Equipment / Fit-Out | 0.542 | 0.677 | 0.88 | 10-40% definition maturity
3 | 01.06 | Data Halls / White Space | 0.587 | 0.734 | 0.954 | 10-40% definition maturity
3 | 01.07 | Power Train / Substations | 0.722 | 0.903 | 1.174 | 10-40% definition maturity
3 | 01.08 | Cooling Systems | 0.542 | 0.677 | 0.88 | 10-40% definition maturity
3 | 01.09 | Direct Labour | 0.406 | 0.508 | 0.66 | 10-40% definition maturity
3 | 01.10 | Direct Materials | 0.451 | 0.564 | 0.733 | 10-40% definition maturity
3 | 01.11 | Plant / Equipment | 0.181 | 0.226 | 0.294 | 10-40% definition maturity
3 | 02.01 | General Conditions / Prelims | 0.316 | 0.395 | 0.514 | 10-40% definition maturity
3 | 02.02 | Design / Professional Fees | 0.316 | 0.395 | 0.514 | 10-40% definition maturity
3 | 02.03 | Permits / Insurance / Bonds | 0.135 | 0.169 | 0.22 | 10-40% definition maturity
3 | 03.01 | QCRA Contingency | 0.271 | 0.339 | 0.441 | 10-40% definition maturity
3 | 03.02 | Management Reserve | 0.135 | 0.169 | 0.22 | 10-40% definition maturity

## Class 4 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
4 | 01.01 | Site Preparation / Enabling | 0.237 | 0.339 | 0.509 | 1-15% definition maturity
4 | 01.02 | Substructure / Foundations | 0.316 | 0.451 | 0.676 | 1-15% definition maturity
4 | 01.03 | Superstructure / Civil Works | 0.553 | 0.79 | 1.185 | 1-15% definition maturity
4 | 01.04 | MEP / Systems / Utilities | 0.553 | 0.79 | 1.185 | 1-15% definition maturity
4 | 01.05 | Specialist Equipment / Fit-Out | 0.474 | 0.677 | 1.016 | 1-15% definition maturity
4 | 01.06 | Data Halls / White Space | 0.514 | 0.734 | 1.101 | 1-15% definition maturity
4 | 01.07 | Power Train / Substations | 0.632 | 0.903 | 1.355 | 1-15% definition maturity
4 | 01.08 | Cooling Systems | 0.474 | 0.677 | 1.016 | 1-15% definition maturity
4 | 01.09 | Direct Labour | 0.356 | 0.508 | 0.762 | 1-15% definition maturity
4 | 01.10 | Direct Materials | 0.395 | 0.564 | 0.846 | 1-15% definition maturity
4 | 01.11 | Plant / Equipment | 0.158 | 0.226 | 0.339 | 1-15% definition maturity
4 | 02.01 | General Conditions / Prelims | 0.276 | 0.395 | 0.593 | 1-15% definition maturity
4 | 02.02 | Design / Professional Fees | 0.276 | 0.395 | 0.593 | 1-15% definition maturity
4 | 02.03 | Permits / Insurance / Bonds | 0.118 | 0.169 | 0.254 | 1-15% definition maturity
4 | 03.01 | QCRA Contingency | 0.237 | 0.339 | 0.509 | 1-15% definition maturity
4 | 03.02 | Management Reserve | 0.118 | 0.169 | 0.254 | 1-15% definition maturity

## Class 5 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
5 | 01.01 | Site Preparation / Enabling | 0.17 | 0.339 | 0.678 | 0-2% definition maturity
5 | 01.02 | Substructure / Foundations | 0.226 | 0.451 | 0.902 | 0-2% definition maturity
5 | 01.03 | Superstructure / Civil Works | 0.395 | 0.79 | 1.58 | 0-2% definition maturity
5 | 01.04 | MEP / Systems / Utilities | 0.395 | 0.79 | 1.58 | 0-2% definition maturity
5 | 01.05 | Specialist Equipment / Fit-Out | 0.339 | 0.677 | 1.354 | 0-2% definition maturity
5 | 01.06 | Data Halls / White Space | 0.367 | 0.734 | 1.468 | 0-2% definition maturity
5 | 01.07 | Power Train / Substations | 0.452 | 0.903 | 1.806 | 0-2% definition maturity
5 | 01.08 | Cooling Systems | 0.339 | 0.677 | 1.354 | 0-2% definition maturity
5 | 01.09 | Direct Labour | 0.254 | 0.508 | 1.016 | 0-2% definition maturity
5 | 01.10 | Direct Materials | 0.282 | 0.564 | 1.128 | 0-2% definition maturity
5 | 01.11 | Plant / Equipment | 0.113 | 0.226 | 0.452 | 0-2% definition maturity
5 | 02.01 | General Conditions / Prelims | 0.198 | 0.395 | 0.79 | 0-2% definition maturity
5 | 02.02 | Design / Professional Fees | 0.198 | 0.395 | 0.79 | 0-2% definition maturity
5 | 02.03 | Permits / Insurance / Bonds | 0.085 | 0.169 | 0.338 | 0-2% definition maturity
5 | 03.01 | QCRA Contingency | 0.17 | 0.339 | 0.678 | 0-2% definition maturity
5 | 03.02 | Management Reserve | 0.085 | 0.169 | 0.338 | 0-2% definition maturity

## Level 1 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
M100 | Milestone | Investment approval |  | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M200 | Milestone | Design complete | M100 | 9 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M300 | Milestone | Procurement complete | M200 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M400 | Milestone | Delivery complete | M300 | 18 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M500 | Milestone | Ready for operations | M400 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M600 | Milestone | Handover | M500 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 2 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 1 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 10 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 3 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 1 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 10 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 4 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 1 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 10 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1000 | Package | Grid connection | A1900 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2000 | Package | Data halls | P1000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3000 | Package | Cooling plant | P2000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4000 | Package | Power train | P3000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5000 | Package | Controls and commissioning | P4000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 5 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 1 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 10 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1000 | Package | Grid connection | A1900 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1100 | Activity | Grid connection - mobilise / method | A1900 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1200 | Activity | Grid connection - execute works | P1100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1300 | Activity | Grid connection - inspect / closeout | P1200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2000 | Package | Data halls | P1000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2100 | Activity | Data halls - mobilise / method | P1000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2200 | Activity | Data halls - execute works | P2100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2300 | Activity | Data halls - inspect / closeout | P2200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3000 | Package | Cooling plant | P2000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3100 | Activity | Cooling plant - mobilise / method | P2000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3200 | Activity | Cooling plant - execute works | P3100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3300 | Activity | Cooling plant - inspect / closeout | P3200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4000 | Package | Power train | P3000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4100 | Activity | Power train - mobilise / method | P3000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4200 | Activity | Power train - execute works | P4100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4300 | Activity | Power train - inspect / closeout | P4200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5000 | Package | Controls and commissioning | P4000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5100 | Activity | Controls and commissioning - mobilise / method | P4000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5200 | Activity | Controls and commissioning - execute works | P5100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5300 | Activity | Controls and commissioning - inspect / closeout | P5200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Risk Register
ID | Risk | Category | Probability | Activity | CBS | Sched O | Sched M | Sched P | Cost O | Cost M | Cost P | Owner | Trigger | Mitigation | Cost Basis | Schedule Basis
R-D01 | Grid connection delay | Utilities | 48 | A1400 | 01.04 | 20 | 80 | 220 | 0.169 | 0.564 | 1.241 | Utilities Lead | Grid agreement unsigned | Secure grid agreement, temporary power, early equipment orders | Cost impact derived from 01.04 MEP / Systems / Utilities exposure, project P50 $5.6B, and risk severity (3%/10%/22%). | Schedule impact mapped to A1400 Planning, regulatory and stakeholder approvals with O/M/P delay 20/80/220 days and critical path sensitivity.
R-002 | Market escalation | Commercial | 45 | A1700 | 01.07 | 0 | 0 | 0 | 0.226 | 0.564 | 1.129 | Commercial Lead | Index exceeds allowance | Early procurement, index strategy, market testing | Cost impact derived from 01.07 Power Train / Substations exposure, project P50 $5.6B, and risk severity (4%/10%/20%). | Schedule impact mapped to A1700 Long-lead procurement with O/M/P delay 0/0/0 days and critical path sensitivity.
R-004 | Design maturity gap | Technical | 38 | A1900 | 01.09 | 15 | 45 | 120 | 0.169 | 0.508 | 1.016 | Design Manager | Deliverables late | Design maturity gates and independent review | Cost impact derived from 01.09 Direct Labour exposure, project P50 $5.6B, and risk severity (3%/9%/18%). | Schedule impact mapped to A1900 Main construction / fabrication / assembly with O/M/P delay 15/45/120 days and critical path sensitivity.
R-001 | Scope growth | Scope | 42 | A1600 | 01.06 | 15 | 45 | 120 | 0.169 | 0.451 | 0.903 | Project Director | Scope change rate exceeds threshold | Freeze scope, change board, value gates | Cost impact derived from 01.06 Data Halls / White Space exposure, project P50 $5.6B, and risk severity (3%/8%/16%). | Schedule impact mapped to A1600 Detailed design / IFC development with O/M/P delay 15/45/120 days and critical path sensitivity.
R-006 | Productivity underperformance | Delivery | 35 | A2100 | 01.11 | 15 | 50 | 130 | 0.169 | 0.451 | 0.903 | Delivery Lead | SPI/CPI deteriorates | Package productivity controls and daily planning | Cost impact derived from 01.11 Plant / Equipment exposure, project P50 $5.6B, and risk severity (3%/8%/16%). | Schedule impact mapped to A2100 Commissioning, operations readiness and closeout with O/M/P delay 15/50/130 days and critical path sensitivity.
R-005 | Supply chain delay | Procurement | 40 | A2000 | 01.10 | 10 | 40 | 120 | 0.113 | 0.395 | 0.846 | Procurement Lead | Supplier promise date slips | Alternate suppliers, early orders, expediting | Cost impact derived from 01.10 Direct Materials exposure, project P50 $5.6B, and risk severity (2%/7%/15%). | Schedule impact mapped to A2000 Systems integration and testing with O/M/P delay 10/40/120 days and critical path sensitivity.
R-D02 | Cooling system capacity | Technical | 34 | A1500 | 01.05 | 10 | 40 | 120 | 0.113 | 0.395 | 0.846 | MEP Lead | Cooling tests fail | Early thermal modelling and supplier validation | Cost impact derived from 01.05 Specialist Equipment / Fit-Out exposure, project P50 $5.6B, and risk severity (2%/7%/15%). | Schedule impact mapped to A1500 Procurement strategy and tender packaging with O/M/P delay 10/40/120 days and critical path sensitivity.
R-008 | Interface misalignment | Integration | 34 | P2000 | 02.02 | 10 | 35 | 100 | 0.113 | 0.395 | 0.79 | Integration Manager | Interface actions overdue | ICDs and weekly interface board | Cost impact derived from 02.02 Design / Professional Fees exposure, project P50 $5.6B, and risk severity (2%/7%/14%). | Schedule impact mapped to P2000 Data halls with O/M/P delay 10/35/100 days and critical path sensitivity.
R-007 | Commissioning delay | Handover | 32 | P1000 | 02.01 | 10 | 35 | 100 | 0.113 | 0.339 | 0.677 | Commissioning Lead | Test failures trend upward | Commissioning readiness and early test plans | Cost impact derived from 02.01 General Conditions / Prelims exposure, project P50 $5.6B, and risk severity (2%/6%/12%). | Schedule impact mapped to P1000 Grid connection with O/M/P delay 10/35/100 days and critical path sensitivity.
R-003 | Permits / approvals delay | Regulatory | 35 | A1800 | 01.08 | 20 | 70 | 180 | 0.056 | 0.226 | 0.451 | Consents Lead | Consent milestone slips | Authority plan, consent tracker, early submissions | Cost impact derived from 01.08 Cooling Systems exposure, project P50 $5.6B, and risk severity (1%/4%/8%). | Schedule impact mapped to A1800 Site / launch integration readiness with O/M/P delay 20/70/180 days and critical path sensitivity.

## Monte Carlo P-Curve
Percentile | QCRA Cost BN | QSRA Months
1 | 5.763 | 45.69
5 | 6.225 | 47.97
10 | 6.498 | 49.27
20 | 6.864 | 50.86
30 | 7.135 | 52.11
40 | 7.389 | 53.26
50 | 7.615 | 54.34
60 | 7.857 | 55.45
70 | 8.115 | 56.71
80 | 8.409 | 58.08
90 | 8.841 | 60.27
95 | 9.197 | 61.98
99 | 9.836 | 65.03

## Tornado Drivers
Risk | Title | Activity | CBS | Cost Mean BN | Schedule Mean Days | Driver Score
R-D01 | Grid connection delay | A1400 | 01.04 | 0.313 | 50.5 | 36.37
R-002 | Market escalation | A1700 | 01.07 | 0.288 | 0 | 28.77
R-001 | Scope growth | A1600 | 01.06 | 0.216 | 25.3 | 24.17
R-004 | Design maturity gap | A1900 | 01.09 | 0.212 | 22.7 | 23.5
R-006 | Productivity underperformance | A2100 | 01.11 | 0.179 | 22.9 | 20.2
R-005 | Supply chain delay | A2000 | 01.10 | 0.178 | 22.2 | 20
R-D02 | Cooling system capacity | A1500 | 01.05 | 0.151 | 19.1 | 17.03
R-008 | Interface misalignment | P2000 | 02.02 | 0.152 | 17 | 16.88
R-007 | Commissioning delay | P1000 | 02.01 | 0.121 | 15.7 | 13.69
R-003 | Permits / approvals delay | A1800 | 01.08 | 0.086 | 31.9 | 11.76

## Scenarios
Scenario | Cost | Schedule Months | Risk | Confidence | Why
Base | $5.6B | 46 | Medium | 64 | Balanced reference case.
Faster | $6.3B | 38 | Medium | 59 | Parallel design/procurement, acceleration, premium logistics and higher interface risk.
Cheaper | $5.0B | 50 | Medium | 58 | Value engineering, tighter scope and procurement competition, with schedule/quality exposure.
Lower Risk | $6.2B | 51 | Low | 77 | More surveys, assurance, stage gates, contingency and schedule buffers.
Premium | $6.5B | 48 | Low | 80 | Best assurance, independent review, early procurement and high-confidence governance.
Investor | $5.5B | 46 | Low | 71 | Investment-framing case with transparent risk and commercial challenge.
Survival | $4.4B | 55 | Medium | 54 | Minimum viable scope, warning-heavy, high residual risk.

## Benchmarks
Metric | Value | Why
Hyperscale delivery benchmark | $8M-$18M per MW equivalent | Varies by power density, grid scope, cooling, land and regional constraints.
Schedule benchmark | 30-60 months | Driven by grid connection, long-lead electrical equipment and phased fit-out.
Top benchmark gap | Power availability | Grid connection is frequently the dominant schedule and risk driver.

## Demo Script
Step
Open with: 'Give me any project on Earth or in Space.'
Type the project into CASEY and hit Generate Full Intelligence Pack.
Show the executive dashboard: cost, schedule, risk, confidence and top drivers.
Switch to Monte Carlo: show QCRA/QSRA P-curves and tornado drivers linked to activities.
Show scenarios: Faster, Cheaper, Lower Risk and Premium with why each changed.
Open Output Centre: Excel, Risk CSV, XER, Word, PDF, PPTX and ZIP are ready.
Close with: 'Traditional advisory takes weeks. CASEY gives the first board-grade view in seconds.'