# CASEY TITAN X Board Report

AI Data Centre Campus has been classified as Digital Infrastructure / Hyperscale Data Centre in Saudi Arabia / GCC. CASEY estimates $5.6B P50 cost, $4.5B to $7.3B range, 46 month baseline, Medium risk and 64% confidence under the Base scenario.

| Metric | Value |
| --- | --- |
| Cost P50 | $5.6B |
| Cost Range | $4.5B - $7.3B |
| Schedule | 46 months |
| QCRA P80 | $8.4B |
| QSRA P80 | 58.08 months |
| Risk | Medium |
| Confidence | 64% |

# Why Confidence

Class 3 Budget Authorization: 10-40% definition maturity drives the starting confidence level.

Schedule Level 4: more detailed schedule logic improves QSRA traceability.

Base: Balanced reference case.

Location/space factor: Saudi Arabia / GCC applies a 1.35 delivery premium.

accelerated delivery compression

# Top Red Flags

Confidence below board-comfort threshold: improve scope definition, benchmark evidence and supplier quotes.

Data centre: grid connection and cooling basis must be validated early.

# Board Challenge Questions

What evidence supports the P50 cost and P80 confidence?

Which five risks create most contingency?

Which activities drive the QSRA finish-date risk?

What data would increase confidence before approval?

What is the fastest credible lower-risk path?

# Next Best Actions

Run a risk workshop to validate probability and O/M/P impacts.

Confirm top five CBS cost drivers with benchmark or supplier evidence.

Validate the Level 3/4 schedule logic and critical path assumptions.

Prepare board decision paper with Base/Faster/Cheaper/Lower-Risk cases.

Create confidence improvement plan targeting design maturity, consents and procurement evidence.

# Top Risk Drivers

R-D01 Grid connection delay — A1400 / 01.04: Schedule impact mapped to A1400 Planning, regulatory and stakeholder approvals with O/M/P delay 20/80/220 days and critical path sensitivity.

R-002 Market escalation — A1700 / 01.07: Schedule impact mapped to A1700 Long-lead procurement with O/M/P delay 0/0/0 days and critical path sensitivity.

R-004 Design maturity gap — A1900 / 01.09: Schedule impact mapped to A1900 Main construction / fabrication / assembly with O/M/P delay 15/45/120 days and critical path sensitivity.

R-001 Scope growth — A1600 / 01.06: Schedule impact mapped to A1600 Detailed design / IFC development with O/M/P delay 15/45/120 days and critical path sensitivity.

R-006 Productivity underperformance — A2100 / 01.11: Schedule impact mapped to A2100 Commissioning, operations readiness and closeout with O/M/P delay 15/50/130 days and critical path sensitivity.

R-005 Supply chain delay — A2000 / 01.10: Schedule impact mapped to A2000 Systems integration and testing with O/M/P delay 10/40/120 days and critical path sensitivity.

R-D02 Cooling system capacity — A1500 / 01.05: Schedule impact mapped to A1500 Procurement strategy and tender packaging with O/M/P delay 10/40/120 days and critical path sensitivity.

R-008 Interface misalignment — P2000 / 02.02: Schedule impact mapped to P2000 Data halls with O/M/P delay 10/35/100 days and critical path sensitivity.