## Board Summary
Field | Value
Generated | 2026-05-02T20:00:51.659712
Version | v23 Real Deal Edition
Title | Life Sciences Campus
Client | ChipCo
Executive Summary | Life Sciences Campus has been classified as Life Sciences / Pharma in Global / Not specified. CASEY estimates $3.0B P50 cost, $2.4B to $3.9B range, 74 month baseline, Medium risk and 64% confidence under the Base scenario.
Mode | Earth
Subsector | Life Sciences / Pharma
Location | Global / Not specified
Scenario | Base
Cost P10 | $2.4B
Cost P50 | $3.0B
Cost P90 | $3.9B
Schedule | 74 months
QCRA P80 | $4.2B
QSRA P80 | 84.85
Risk | Medium
Confidence | 64%

## Primary Cost Estimate
CBS | Description | Type | Basis | P10 BN | P50 BN | P90 BN | Impact Basis
01.01 | Site Preparation / Enabling | Direct | Demolition, enabling, logistics and access | 0.144 | 0.18 | 0.234 | Site Preparation / Enabling priced as 6.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
01.02 | Substructure / Foundations | Direct | Piling, groundworks, retaining and foundations | 0.192 | 0.24 | 0.312 | Substructure / Foundations priced as 8.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
01.03 | Superstructure / Civil Works | Direct | Frame, civils, primary structures | 0.336 | 0.42 | 0.546 | Superstructure / Civil Works priced as 14.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
01.04 | MEP / Systems / Utilities | Direct | Mechanical, electrical, controls and utilities | 0.336 | 0.42 | 0.546 | MEP / Systems / Utilities priced as 14.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
01.05 | Specialist Equipment / Fit-Out | Direct | Permanent equipment and specialist fit-out | 0.288 | 0.36 | 0.468 | Specialist Equipment / Fit-Out priced as 12.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
01.06 | Cleanroom Envelope | Direct | Cleanroom partitions, finishes and GMP envelope | 0.288 | 0.36 | 0.468 | Cleanroom Envelope priced as 12.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
01.07 | Process Utilities | Direct | WFI, gases, clean steam and process utilities | 0.312 | 0.39 | 0.507 | Process Utilities priced as 13.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
01.08 | Validation / Qualification | Indirect | IQ/OQ/PQ and GMP readiness | 0.12 | 0.15 | 0.195 | Validation / Qualification priced as 5.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
01.09 | Direct Labour | Direct | Productivity, supervision and trade labour | 0.216 | 0.27 | 0.351 | Direct Labour priced as 9.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
01.10 | Direct Materials | Direct | Concrete, steel, envelope, MEP materials | 0.24 | 0.3 | 0.39 | Direct Materials priced as 10.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
01.11 | Plant / Equipment | Direct | Cranes, heavy plant and site equipment | 0.096 | 0.12 | 0.156 | Plant / Equipment priced as 4.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
02.01 | General Conditions / Prelims | Indirect | Site management, safety, offices and temporary services | 0.168 | 0.21 | 0.273 | General Conditions / Prelims priced as 7.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
02.02 | Design / Professional Fees | Indirect | Design, QS, controls, assurance and consultants | 0.168 | 0.21 | 0.273 | Design / Professional Fees priced as 7.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
02.03 | Permits / Insurance / Bonds | Indirect | Permits, inspections, legal, bonds and insurance | 0.072 | 0.09 | 0.117 | Permits / Insurance / Bonds priced as 3.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
03.01 | QCRA Contingency | Reserve | Known-unknown risk allowance | 0.144 | 0.18 | 0.234 | QCRA Contingency priced as 6.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.
03.02 | Management Reserve | Reserve | Sponsor-held reserve | 0.072 | 0.09 | 0.117 | Management Reserve priced as 3.0% of P50 from sector template, location factor 1.00, scale factor 1.00, complexity factor 1.25.

## Class 1 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
1 | 01.01 | Site Preparation / Enabling | 0.162 | 0.18 | 0.207 | 65-100% definition maturity
1 | 01.02 | Substructure / Foundations | 0.216 | 0.24 | 0.276 | 65-100% definition maturity
1 | 01.03 | Superstructure / Civil Works | 0.378 | 0.42 | 0.483 | 65-100% definition maturity
1 | 01.04 | MEP / Systems / Utilities | 0.378 | 0.42 | 0.483 | 65-100% definition maturity
1 | 01.05 | Specialist Equipment / Fit-Out | 0.324 | 0.36 | 0.414 | 65-100% definition maturity
1 | 01.06 | Cleanroom Envelope | 0.324 | 0.36 | 0.414 | 65-100% definition maturity
1 | 01.07 | Process Utilities | 0.351 | 0.39 | 0.448 | 65-100% definition maturity
1 | 01.08 | Validation / Qualification | 0.135 | 0.15 | 0.172 | 65-100% definition maturity
1 | 01.09 | Direct Labour | 0.243 | 0.27 | 0.31 | 65-100% definition maturity
1 | 01.10 | Direct Materials | 0.27 | 0.3 | 0.345 | 65-100% definition maturity
1 | 01.11 | Plant / Equipment | 0.108 | 0.12 | 0.138 | 65-100% definition maturity
1 | 02.01 | General Conditions / Prelims | 0.189 | 0.21 | 0.241 | 65-100% definition maturity
1 | 02.02 | Design / Professional Fees | 0.189 | 0.21 | 0.241 | 65-100% definition maturity
1 | 02.03 | Permits / Insurance / Bonds | 0.081 | 0.09 | 0.103 | 65-100% definition maturity
1 | 03.01 | QCRA Contingency | 0.162 | 0.18 | 0.207 | 65-100% definition maturity
1 | 03.02 | Management Reserve | 0.081 | 0.09 | 0.103 | 65-100% definition maturity

## Class 2 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
2 | 01.01 | Site Preparation / Enabling | 0.153 | 0.18 | 0.216 | 30-75% definition maturity
2 | 01.02 | Substructure / Foundations | 0.204 | 0.24 | 0.288 | 30-75% definition maturity
2 | 01.03 | Superstructure / Civil Works | 0.357 | 0.42 | 0.504 | 30-75% definition maturity
2 | 01.04 | MEP / Systems / Utilities | 0.357 | 0.42 | 0.504 | 30-75% definition maturity
2 | 01.05 | Specialist Equipment / Fit-Out | 0.306 | 0.36 | 0.432 | 30-75% definition maturity
2 | 01.06 | Cleanroom Envelope | 0.306 | 0.36 | 0.432 | 30-75% definition maturity
2 | 01.07 | Process Utilities | 0.332 | 0.39 | 0.468 | 30-75% definition maturity
2 | 01.08 | Validation / Qualification | 0.128 | 0.15 | 0.18 | 30-75% definition maturity
2 | 01.09 | Direct Labour | 0.23 | 0.27 | 0.324 | 30-75% definition maturity
2 | 01.10 | Direct Materials | 0.255 | 0.3 | 0.36 | 30-75% definition maturity
2 | 01.11 | Plant / Equipment | 0.102 | 0.12 | 0.144 | 30-75% definition maturity
2 | 02.01 | General Conditions / Prelims | 0.178 | 0.21 | 0.252 | 30-75% definition maturity
2 | 02.02 | Design / Professional Fees | 0.178 | 0.21 | 0.252 | 30-75% definition maturity
2 | 02.03 | Permits / Insurance / Bonds | 0.076 | 0.09 | 0.108 | 30-75% definition maturity
2 | 03.01 | QCRA Contingency | 0.153 | 0.18 | 0.216 | 30-75% definition maturity
2 | 03.02 | Management Reserve | 0.076 | 0.09 | 0.108 | 30-75% definition maturity

## Class 3 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
3 | 01.01 | Site Preparation / Enabling | 0.144 | 0.18 | 0.234 | 10-40% definition maturity
3 | 01.02 | Substructure / Foundations | 0.192 | 0.24 | 0.312 | 10-40% definition maturity
3 | 01.03 | Superstructure / Civil Works | 0.336 | 0.42 | 0.546 | 10-40% definition maturity
3 | 01.04 | MEP / Systems / Utilities | 0.336 | 0.42 | 0.546 | 10-40% definition maturity
3 | 01.05 | Specialist Equipment / Fit-Out | 0.288 | 0.36 | 0.468 | 10-40% definition maturity
3 | 01.06 | Cleanroom Envelope | 0.288 | 0.36 | 0.468 | 10-40% definition maturity
3 | 01.07 | Process Utilities | 0.312 | 0.39 | 0.507 | 10-40% definition maturity
3 | 01.08 | Validation / Qualification | 0.12 | 0.15 | 0.195 | 10-40% definition maturity
3 | 01.09 | Direct Labour | 0.216 | 0.27 | 0.351 | 10-40% definition maturity
3 | 01.10 | Direct Materials | 0.24 | 0.3 | 0.39 | 10-40% definition maturity
3 | 01.11 | Plant / Equipment | 0.096 | 0.12 | 0.156 | 10-40% definition maturity
3 | 02.01 | General Conditions / Prelims | 0.168 | 0.21 | 0.273 | 10-40% definition maturity
3 | 02.02 | Design / Professional Fees | 0.168 | 0.21 | 0.273 | 10-40% definition maturity
3 | 02.03 | Permits / Insurance / Bonds | 0.072 | 0.09 | 0.117 | 10-40% definition maturity
3 | 03.01 | QCRA Contingency | 0.144 | 0.18 | 0.234 | 10-40% definition maturity
3 | 03.02 | Management Reserve | 0.072 | 0.09 | 0.117 | 10-40% definition maturity

## Class 4 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
4 | 01.01 | Site Preparation / Enabling | 0.126 | 0.18 | 0.27 | 1-15% definition maturity
4 | 01.02 | Substructure / Foundations | 0.168 | 0.24 | 0.36 | 1-15% definition maturity
4 | 01.03 | Superstructure / Civil Works | 0.294 | 0.42 | 0.63 | 1-15% definition maturity
4 | 01.04 | MEP / Systems / Utilities | 0.294 | 0.42 | 0.63 | 1-15% definition maturity
4 | 01.05 | Specialist Equipment / Fit-Out | 0.252 | 0.36 | 0.54 | 1-15% definition maturity
4 | 01.06 | Cleanroom Envelope | 0.252 | 0.36 | 0.54 | 1-15% definition maturity
4 | 01.07 | Process Utilities | 0.273 | 0.39 | 0.585 | 1-15% definition maturity
4 | 01.08 | Validation / Qualification | 0.105 | 0.15 | 0.225 | 1-15% definition maturity
4 | 01.09 | Direct Labour | 0.189 | 0.27 | 0.405 | 1-15% definition maturity
4 | 01.10 | Direct Materials | 0.21 | 0.3 | 0.45 | 1-15% definition maturity
4 | 01.11 | Plant / Equipment | 0.084 | 0.12 | 0.18 | 1-15% definition maturity
4 | 02.01 | General Conditions / Prelims | 0.147 | 0.21 | 0.315 | 1-15% definition maturity
4 | 02.02 | Design / Professional Fees | 0.147 | 0.21 | 0.315 | 1-15% definition maturity
4 | 02.03 | Permits / Insurance / Bonds | 0.063 | 0.09 | 0.135 | 1-15% definition maturity
4 | 03.01 | QCRA Contingency | 0.126 | 0.18 | 0.27 | 1-15% definition maturity
4 | 03.02 | Management Reserve | 0.063 | 0.09 | 0.135 | 1-15% definition maturity

## Class 5 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
5 | 01.01 | Site Preparation / Enabling | 0.09 | 0.18 | 0.36 | 0-2% definition maturity
5 | 01.02 | Substructure / Foundations | 0.12 | 0.24 | 0.48 | 0-2% definition maturity
5 | 01.03 | Superstructure / Civil Works | 0.21 | 0.42 | 0.84 | 0-2% definition maturity
5 | 01.04 | MEP / Systems / Utilities | 0.21 | 0.42 | 0.84 | 0-2% definition maturity
5 | 01.05 | Specialist Equipment / Fit-Out | 0.18 | 0.36 | 0.72 | 0-2% definition maturity
5 | 01.06 | Cleanroom Envelope | 0.18 | 0.36 | 0.72 | 0-2% definition maturity
5 | 01.07 | Process Utilities | 0.195 | 0.39 | 0.78 | 0-2% definition maturity
5 | 01.08 | Validation / Qualification | 0.075 | 0.15 | 0.3 | 0-2% definition maturity
5 | 01.09 | Direct Labour | 0.135 | 0.27 | 0.54 | 0-2% definition maturity
5 | 01.10 | Direct Materials | 0.15 | 0.3 | 0.6 | 0-2% definition maturity
5 | 01.11 | Plant / Equipment | 0.06 | 0.12 | 0.24 | 0-2% definition maturity
5 | 02.01 | General Conditions / Prelims | 0.105 | 0.21 | 0.42 | 0-2% definition maturity
5 | 02.02 | Design / Professional Fees | 0.105 | 0.21 | 0.42 | 0-2% definition maturity
5 | 02.03 | Permits / Insurance / Bonds | 0.045 | 0.09 | 0.18 | 0-2% definition maturity
5 | 03.01 | QCRA Contingency | 0.09 | 0.18 | 0.36 | 0-2% definition maturity
5 | 03.02 | Management Reserve | 0.045 | 0.09 | 0.18 | 0-2% definition maturity

## Level 1 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
M100 | Milestone | Investment approval |  | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M200 | Milestone | Design complete | M100 | 15 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M300 | Milestone | Procurement complete | M200 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M400 | Milestone | Delivery complete | M300 | 30 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M500 | Milestone | Ready for operations | M400 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M600 | Milestone | Handover | M500 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 2 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 7 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 7 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 16 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 7 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 3 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 7 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 7 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 16 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 7 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 4 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 7 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 7 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 16 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 7 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1000 | Package | Civil / structural package | A1900 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2000 | Package | MEP / systems package | P1000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3000 | Package | Specialist equipment package | P2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4000 | Package | Utilities / interfaces package | P3000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5000 | Package | Testing and commissioning package | P4000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 5 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 7 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 7 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 16 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 7 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1000 | Package | Civil / structural package | A1900 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1100 | Activity | Civil / structural package - mobilise / method | A1900 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1200 | Activity | Civil / structural package - execute works | P1100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1300 | Activity | Civil / structural package - inspect / closeout | P1200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2000 | Package | MEP / systems package | P1000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2100 | Activity | MEP / systems package - mobilise / method | P1000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2200 | Activity | MEP / systems package - execute works | P2100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2300 | Activity | MEP / systems package - inspect / closeout | P2200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3000 | Package | Specialist equipment package | P2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3100 | Activity | Specialist equipment package - mobilise / method | P2000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3200 | Activity | Specialist equipment package - execute works | P3100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3300 | Activity | Specialist equipment package - inspect / closeout | P3200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4000 | Package | Utilities / interfaces package | P3000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4100 | Activity | Utilities / interfaces package - mobilise / method | P3000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4200 | Activity | Utilities / interfaces package - execute works | P4100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4300 | Activity | Utilities / interfaces package - inspect / closeout | P4200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5000 | Package | Testing and commissioning package | P4000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5100 | Activity | Testing and commissioning package - mobilise / method | P4000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5200 | Activity | Testing and commissioning package - execute works | P5100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5300 | Activity | Testing and commissioning package - inspect / closeout | P5200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Risk Register
ID | Risk | Category | Probability | Activity | CBS | Sched O | Sched M | Sched P | Cost O | Cost M | Cost P | Owner | Trigger | Mitigation | Cost Basis | Schedule Basis
R-002 | Market escalation | Commercial | 45 | A1500 | 01.05 | 0 | 0 | 0 | 0.12 | 0.3 | 0.6 | Commercial Lead | Index exceeds allowance | Early procurement, index strategy, market testing | Cost impact derived from 01.05 Specialist Equipment / Fit-Out exposure, project P50 $3.0B, and risk severity (4%/10%/20%). | Schedule impact mapped to A1500 Procurement strategy and tender packaging with O/M/P delay 0/0/0 days and critical path sensitivity.
R-001 | Scope growth | Scope | 42 | A1400 | 01.04 | 15 | 45 | 120 | 0.09 | 0.24 | 0.48 | Project Director | Scope change rate exceeds threshold | Freeze scope, change board, value gates | Cost impact derived from 01.04 MEP / Systems / Utilities exposure, project P50 $3.0B, and risk severity (3%/8%/16%). | Schedule impact mapped to A1400 Planning, regulatory and stakeholder approvals with O/M/P delay 15/45/120 days and critical path sensitivity.
R-004 | Design maturity gap | Technical | 38 | A1700 | 01.07 | 15 | 45 | 120 | 0.09 | 0.27 | 0.54 | Design Manager | Deliverables late | Design maturity gates and independent review | Cost impact derived from 01.07 Process Utilities exposure, project P50 $3.0B, and risk severity (3%/9%/18%). | Schedule impact mapped to A1700 Long-lead procurement with O/M/P delay 15/45/120 days and critical path sensitivity.
R-006 | Productivity underperformance | Delivery | 35 | A1900 | 01.09 | 15 | 50 | 130 | 0.09 | 0.24 | 0.48 | Delivery Lead | SPI/CPI deteriorates | Package productivity controls and daily planning | Cost impact derived from 01.09 Direct Labour exposure, project P50 $3.0B, and risk severity (3%/8%/16%). | Schedule impact mapped to A1900 Main construction / fabrication / assembly with O/M/P delay 15/50/130 days and critical path sensitivity.
R-005 | Supply chain delay | Procurement | 40 | A1800 | 01.08 | 10 | 40 | 120 | 0.06 | 0.21 | 0.45 | Procurement Lead | Supplier promise date slips | Alternate suppliers, early orders, expediting | Cost impact derived from 01.08 Validation / Qualification exposure, project P50 $3.0B, and risk severity (2%/7%/15%). | Schedule impact mapped to A1800 Site / launch integration readiness with O/M/P delay 10/40/120 days and critical path sensitivity.
R-008 | Interface misalignment | Integration | 34 | A2100 | 01.11 | 10 | 35 | 100 | 0.06 | 0.21 | 0.42 | Integration Manager | Interface actions overdue | ICDs and weekly interface board | Cost impact derived from 01.11 Plant / Equipment exposure, project P50 $3.0B, and risk severity (2%/7%/14%). | Schedule impact mapped to A2100 Commissioning, operations readiness and closeout with O/M/P delay 10/35/100 days and critical path sensitivity.
R-007 | Commissioning delay | Handover | 32 | A2000 | 01.10 | 10 | 35 | 100 | 0.06 | 0.18 | 0.36 | Commissioning Lead | Test failures trend upward | Commissioning readiness and early test plans | Cost impact derived from 01.10 Direct Materials exposure, project P50 $3.0B, and risk severity (2%/6%/12%). | Schedule impact mapped to A2000 Systems integration and testing with O/M/P delay 10/35/100 days and critical path sensitivity.
R-003 | Permits / approvals delay | Regulatory | 35 | A1600 | 01.06 | 20 | 70 | 180 | 0.03 | 0.12 | 0.24 | Consents Lead | Consent milestone slips | Authority plan, consent tracker, early submissions | Cost impact derived from 01.06 Cleanroom Envelope exposure, project P50 $3.0B, and risk severity (1%/4%/8%). | Schedule impact mapped to A1600 Detailed design / IFC development with O/M/P delay 20/70/180 days and critical path sensitivity.

## Monte Carlo P-Curve
Percentile | QCRA Cost BN | QSRA Months
1 | 2.937 | 71.35
5 | 3.149 | 73.56
10 | 3.278 | 75.04
20 | 3.438 | 76.79
30 | 3.566 | 78.18
40 | 3.686 | 79.41
50 | 3.795 | 80.62
60 | 3.907 | 81.84
70 | 4.027 | 83.15
80 | 4.175 | 84.85
90 | 4.374 | 87
95 | 4.536 | 88.73
99 | 4.856 | 92.07

## Tornado Drivers
Risk | Title | Activity | CBS | Cost Mean BN | Schedule Mean Days | Driver Score
R-002 | Market escalation | A1500 | 01.05 | 0.155 | 0 | 15.48
R-001 | Scope growth | A1400 | 01.04 | 0.112 | 25 | 13.72
R-004 | Design maturity gap | A1700 | 01.07 | 0.112 | 22.2 | 13.46
R-006 | Productivity underperformance | A1900 | 01.09 | 0.095 | 23 | 11.83
R-005 | Supply chain delay | A1800 | 01.08 | 0.095 | 22.6 | 11.8
R-008 | Interface misalignment | A2100 | 01.11 | 0.075 | 15.8 | 9.05
R-007 | Commissioning delay | A2000 | 01.10 | 0.064 | 15.2 | 7.93
R-003 | Permits / approvals delay | A1600 | 01.06 | 0.046 | 31.3 | 7.73

## Scenarios
Scenario | Cost | Schedule Months | Risk | Confidence | Why
Base | $3.0B | 74 | Medium | 64 | Balanced reference case.
Faster | $3.3B | 61 | Medium | 59 | Parallel design/procurement, acceleration, premium logistics and higher interface risk.
Cheaper | $2.6B | 80 | Medium | 58 | Value engineering, tighter scope and procurement competition, with schedule/quality exposure.
Lower Risk | $3.3B | 81 | Low | 77 | More surveys, assurance, stage gates, contingency and schedule buffers.
Premium | $3.4B | 77 | Low | 80 | Best assurance, independent review, early procurement and high-confidence governance.
Investor | $2.9B | 74 | Low | 71 | Investment-framing case with transparent risk and commercial challenge.
Survival | $2.3B | 89 | Medium | 54 | Minimum viable scope, warning-heavy, high residual risk.

## Benchmarks
Metric | Value | Why
Capital project benchmark | Sector-adjusted range | Selected based on project type, location, maturity and scale.
Schedule benchmark | 59-96 months | Derived from maturity and delivery complexity.

## Demo Script
Step
Open with: 'Give me any project on Earth or in Space.'
Type the project into CASEY and hit Generate Full Intelligence Pack.
Show the executive dashboard: cost, schedule, risk, confidence and top drivers.
Switch to Monte Carlo: show QCRA/QSRA P-curves and tornado drivers linked to activities.
Show scenarios: Faster, Cheaper, Lower Risk and Premium with why each changed.
Open Output Centre: Excel, Risk CSV, XER, Word, PDF, PPTX and ZIP are ready.
Close with: 'Traditional advisory takes weeks. CASEY gives the first board-grade view in seconds.'