# CASEY TITAN X Board Report

Life Sciences Campus has been classified as Life Sciences / Pharma in United States. CASEY estimates $9.5B P50 cost, $7.6B to $12.4B range, 108 month baseline, Medium-High risk and 60% confidence under the Base scenario.

| Metric | Value |
| --- | --- |
| Cost P50 | $9.5B |
| Cost Range | $7.6B - $12.4B |
| Schedule | 108 months |
| QCRA P80 | $13.2B |
| QSRA P80 | 120.72 months |
| Risk | Medium-High |
| Confidence | 60% |

# Why Confidence

Class 3 Budget Authorization: 10-40% definition maturity drives the starting confidence level.

Schedule Level 4: more detailed schedule logic improves QSRA traceability.

Base: Balanced reference case.

Location/space factor: United States applies a 1.08 delivery premium.

accelerated delivery compression

live environment

GMP cleanroom

GMP validation

# Top Red Flags

Confidence below board-comfort threshold: improve scope definition, benchmark evidence and supplier quotes.

# Board Challenge Questions

What evidence supports the P50 cost and P80 confidence?

Which five risks create most contingency?

Which activities drive the QSRA finish-date risk?

What data would increase confidence before approval?

What is the fastest credible lower-risk path?

# Next Best Actions

Run a risk workshop to validate probability and O/M/P impacts.

Confirm top five CBS cost drivers with benchmark or supplier evidence.

Validate the Level 3/4 schedule logic and critical path assumptions.

Prepare board decision paper with Base/Faster/Cheaper/Lower-Risk cases.

Create confidence improvement plan targeting design maturity, consents and procurement evidence.

# Top Risk Drivers

R-002 Market escalation — A1500 / 01.05: Schedule impact mapped to A1500 Procurement strategy and tender packaging with O/M/P delay 0/0/0 days and critical path sensitivity.

R-004 Design maturity gap — A1700 / 01.07: Schedule impact mapped to A1700 Long-lead procurement with O/M/P delay 15/45/120 days and critical path sensitivity.

R-001 Scope growth — A1400 / 01.04: Schedule impact mapped to A1400 Planning, regulatory and stakeholder approvals with O/M/P delay 15/45/120 days and critical path sensitivity.

R-006 Productivity underperformance — A1900 / 01.09: Schedule impact mapped to A1900 Main construction / fabrication / assembly with O/M/P delay 15/50/130 days and critical path sensitivity.

R-005 Supply chain delay — A1800 / 01.08: Schedule impact mapped to A1800 Site / launch integration readiness with O/M/P delay 10/40/120 days and critical path sensitivity.

R-008 Interface misalignment — A2100 / 01.11: Schedule impact mapped to A2100 Commissioning, operations readiness and closeout with O/M/P delay 10/35/100 days and critical path sensitivity.

R-007 Commissioning delay — A2000 / 01.10: Schedule impact mapped to A2000 Systems integration and testing with O/M/P delay 10/35/100 days and critical path sensitivity.

R-003 Permits / approvals delay — A1600 / 01.06: Schedule impact mapped to A1600 Detailed design / IFC development with O/M/P delay 20/70/180 days and critical path sensitivity.