## Board Summary
Field | Value
Generated | 2026-05-02T20:00:50.348849
Version | v23 Real Deal Edition
Title | Life Sciences Campus
Client | Global Pharma
Executive Summary | Life Sciences Campus has been classified as Life Sciences / Pharma in United States. CASEY estimates $9.5B P50 cost, $7.6B to $12.4B range, 108 month baseline, Medium-High risk and 60% confidence under the Base scenario.
Mode | Earth
Subsector | Life Sciences / Pharma
Location | United States
Scenario | Base
Cost P10 | $7.6B
Cost P50 | $9.5B
Cost P90 | $12.4B
Schedule | 108 months
QCRA P80 | $13.2B
QSRA P80 | 120.72
Risk | Medium-High
Confidence | 60%

## Primary Cost Estimate
CBS | Description | Type | Basis | P10 BN | P50 BN | P90 BN | Impact Basis
01.01 | Site Preparation / Enabling | Direct | Demolition, enabling, logistics and access | 0.456 | 0.57 | 0.741 | Site Preparation / Enabling priced as 6.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
01.02 | Substructure / Foundations | Direct | Piling, groundworks, retaining and foundations | 0.608 | 0.76 | 0.988 | Substructure / Foundations priced as 8.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
01.03 | Superstructure / Civil Works | Direct | Frame, civils, primary structures | 1.064 | 1.33 | 1.729 | Superstructure / Civil Works priced as 14.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
01.04 | MEP / Systems / Utilities | Direct | Mechanical, electrical, controls and utilities | 1.064 | 1.33 | 1.729 | MEP / Systems / Utilities priced as 14.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
01.05 | Specialist Equipment / Fit-Out | Direct | Permanent equipment and specialist fit-out | 0.912 | 1.14 | 1.482 | Specialist Equipment / Fit-Out priced as 12.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
01.06 | Cleanroom Envelope | Direct | Cleanroom partitions, finishes and GMP envelope | 0.912 | 1.14 | 1.482 | Cleanroom Envelope priced as 12.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
01.07 | Process Utilities | Direct | WFI, gases, clean steam and process utilities | 0.988 | 1.235 | 1.606 | Process Utilities priced as 13.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
01.08 | Validation / Qualification | Indirect | IQ/OQ/PQ and GMP readiness | 0.38 | 0.475 | 0.618 | Validation / Qualification priced as 5.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
01.09 | Direct Labour | Direct | Productivity, supervision and trade labour | 0.684 | 0.855 | 1.112 | Direct Labour priced as 9.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
01.10 | Direct Materials | Direct | Concrete, steel, envelope, MEP materials | 0.76 | 0.95 | 1.235 | Direct Materials priced as 10.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
01.11 | Plant / Equipment | Direct | Cranes, heavy plant and site equipment | 0.304 | 0.38 | 0.494 | Plant / Equipment priced as 4.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
02.01 | General Conditions / Prelims | Indirect | Site management, safety, offices and temporary services | 0.532 | 0.665 | 0.865 | General Conditions / Prelims priced as 7.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
02.02 | Design / Professional Fees | Indirect | Design, QS, controls, assurance and consultants | 0.532 | 0.665 | 0.865 | Design / Professional Fees priced as 7.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
02.03 | Permits / Insurance / Bonds | Indirect | Permits, inspections, legal, bonds and insurance | 0.228 | 0.285 | 0.371 | Permits / Insurance / Bonds priced as 3.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
03.01 | QCRA Contingency | Reserve | Known-unknown risk allowance | 0.456 | 0.57 | 0.741 | QCRA Contingency priced as 6.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.
03.02 | Management Reserve | Reserve | Sponsor-held reserve | 0.228 | 0.285 | 0.371 | Management Reserve priced as 3.0% of P50 from sector template, location factor 1.08, scale factor 1.90, complexity factor 1.93.

## Class 1 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
1 | 01.01 | Site Preparation / Enabling | 0.513 | 0.57 | 0.655 | 65-100% definition maturity
1 | 01.02 | Substructure / Foundations | 0.684 | 0.76 | 0.874 | 65-100% definition maturity
1 | 01.03 | Superstructure / Civil Works | 1.197 | 1.33 | 1.529 | 65-100% definition maturity
1 | 01.04 | MEP / Systems / Utilities | 1.197 | 1.33 | 1.529 | 65-100% definition maturity
1 | 01.05 | Specialist Equipment / Fit-Out | 1.026 | 1.14 | 1.311 | 65-100% definition maturity
1 | 01.06 | Cleanroom Envelope | 1.026 | 1.14 | 1.311 | 65-100% definition maturity
1 | 01.07 | Process Utilities | 1.112 | 1.235 | 1.42 | 65-100% definition maturity
1 | 01.08 | Validation / Qualification | 0.427 | 0.475 | 0.546 | 65-100% definition maturity
1 | 01.09 | Direct Labour | 0.769 | 0.855 | 0.983 | 65-100% definition maturity
1 | 01.10 | Direct Materials | 0.855 | 0.95 | 1.092 | 65-100% definition maturity
1 | 01.11 | Plant / Equipment | 0.342 | 0.38 | 0.437 | 65-100% definition maturity
1 | 02.01 | General Conditions / Prelims | 0.599 | 0.665 | 0.765 | 65-100% definition maturity
1 | 02.02 | Design / Professional Fees | 0.599 | 0.665 | 0.765 | 65-100% definition maturity
1 | 02.03 | Permits / Insurance / Bonds | 0.257 | 0.285 | 0.328 | 65-100% definition maturity
1 | 03.01 | QCRA Contingency | 0.513 | 0.57 | 0.655 | 65-100% definition maturity
1 | 03.02 | Management Reserve | 0.257 | 0.285 | 0.328 | 65-100% definition maturity

## Class 2 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
2 | 01.01 | Site Preparation / Enabling | 0.484 | 0.57 | 0.684 | 30-75% definition maturity
2 | 01.02 | Substructure / Foundations | 0.646 | 0.76 | 0.912 | 30-75% definition maturity
2 | 01.03 | Superstructure / Civil Works | 1.131 | 1.33 | 1.596 | 30-75% definition maturity
2 | 01.04 | MEP / Systems / Utilities | 1.131 | 1.33 | 1.596 | 30-75% definition maturity
2 | 01.05 | Specialist Equipment / Fit-Out | 0.969 | 1.14 | 1.368 | 30-75% definition maturity
2 | 01.06 | Cleanroom Envelope | 0.969 | 1.14 | 1.368 | 30-75% definition maturity
2 | 01.07 | Process Utilities | 1.05 | 1.235 | 1.482 | 30-75% definition maturity
2 | 01.08 | Validation / Qualification | 0.404 | 0.475 | 0.57 | 30-75% definition maturity
2 | 01.09 | Direct Labour | 0.727 | 0.855 | 1.026 | 30-75% definition maturity
2 | 01.10 | Direct Materials | 0.807 | 0.95 | 1.14 | 30-75% definition maturity
2 | 01.11 | Plant / Equipment | 0.323 | 0.38 | 0.456 | 30-75% definition maturity
2 | 02.01 | General Conditions / Prelims | 0.565 | 0.665 | 0.798 | 30-75% definition maturity
2 | 02.02 | Design / Professional Fees | 0.565 | 0.665 | 0.798 | 30-75% definition maturity
2 | 02.03 | Permits / Insurance / Bonds | 0.242 | 0.285 | 0.342 | 30-75% definition maturity
2 | 03.01 | QCRA Contingency | 0.484 | 0.57 | 0.684 | 30-75% definition maturity
2 | 03.02 | Management Reserve | 0.242 | 0.285 | 0.342 | 30-75% definition maturity

## Class 3 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
3 | 01.01 | Site Preparation / Enabling | 0.456 | 0.57 | 0.741 | 10-40% definition maturity
3 | 01.02 | Substructure / Foundations | 0.608 | 0.76 | 0.988 | 10-40% definition maturity
3 | 01.03 | Superstructure / Civil Works | 1.064 | 1.33 | 1.729 | 10-40% definition maturity
3 | 01.04 | MEP / Systems / Utilities | 1.064 | 1.33 | 1.729 | 10-40% definition maturity
3 | 01.05 | Specialist Equipment / Fit-Out | 0.912 | 1.14 | 1.482 | 10-40% definition maturity
3 | 01.06 | Cleanroom Envelope | 0.912 | 1.14 | 1.482 | 10-40% definition maturity
3 | 01.07 | Process Utilities | 0.988 | 1.235 | 1.606 | 10-40% definition maturity
3 | 01.08 | Validation / Qualification | 0.38 | 0.475 | 0.617 | 10-40% definition maturity
3 | 01.09 | Direct Labour | 0.684 | 0.855 | 1.111 | 10-40% definition maturity
3 | 01.10 | Direct Materials | 0.76 | 0.95 | 1.235 | 10-40% definition maturity
3 | 01.11 | Plant / Equipment | 0.304 | 0.38 | 0.494 | 10-40% definition maturity
3 | 02.01 | General Conditions / Prelims | 0.532 | 0.665 | 0.865 | 10-40% definition maturity
3 | 02.02 | Design / Professional Fees | 0.532 | 0.665 | 0.865 | 10-40% definition maturity
3 | 02.03 | Permits / Insurance / Bonds | 0.228 | 0.285 | 0.37 | 10-40% definition maturity
3 | 03.01 | QCRA Contingency | 0.456 | 0.57 | 0.741 | 10-40% definition maturity
3 | 03.02 | Management Reserve | 0.228 | 0.285 | 0.37 | 10-40% definition maturity

## Class 4 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
4 | 01.01 | Site Preparation / Enabling | 0.399 | 0.57 | 0.855 | 1-15% definition maturity
4 | 01.02 | Substructure / Foundations | 0.532 | 0.76 | 1.14 | 1-15% definition maturity
4 | 01.03 | Superstructure / Civil Works | 0.931 | 1.33 | 1.995 | 1-15% definition maturity
4 | 01.04 | MEP / Systems / Utilities | 0.931 | 1.33 | 1.995 | 1-15% definition maturity
4 | 01.05 | Specialist Equipment / Fit-Out | 0.798 | 1.14 | 1.71 | 1-15% definition maturity
4 | 01.06 | Cleanroom Envelope | 0.798 | 1.14 | 1.71 | 1-15% definition maturity
4 | 01.07 | Process Utilities | 0.865 | 1.235 | 1.853 | 1-15% definition maturity
4 | 01.08 | Validation / Qualification | 0.332 | 0.475 | 0.712 | 1-15% definition maturity
4 | 01.09 | Direct Labour | 0.598 | 0.855 | 1.282 | 1-15% definition maturity
4 | 01.10 | Direct Materials | 0.665 | 0.95 | 1.425 | 1-15% definition maturity
4 | 01.11 | Plant / Equipment | 0.266 | 0.38 | 0.57 | 1-15% definition maturity
4 | 02.01 | General Conditions / Prelims | 0.465 | 0.665 | 0.998 | 1-15% definition maturity
4 | 02.02 | Design / Professional Fees | 0.465 | 0.665 | 0.998 | 1-15% definition maturity
4 | 02.03 | Permits / Insurance / Bonds | 0.199 | 0.285 | 0.427 | 1-15% definition maturity
4 | 03.01 | QCRA Contingency | 0.399 | 0.57 | 0.855 | 1-15% definition maturity
4 | 03.02 | Management Reserve | 0.199 | 0.285 | 0.427 | 1-15% definition maturity

## Class 5 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
5 | 01.01 | Site Preparation / Enabling | 0.285 | 0.57 | 1.14 | 0-2% definition maturity
5 | 01.02 | Substructure / Foundations | 0.38 | 0.76 | 1.52 | 0-2% definition maturity
5 | 01.03 | Superstructure / Civil Works | 0.665 | 1.33 | 2.66 | 0-2% definition maturity
5 | 01.04 | MEP / Systems / Utilities | 0.665 | 1.33 | 2.66 | 0-2% definition maturity
5 | 01.05 | Specialist Equipment / Fit-Out | 0.57 | 1.14 | 2.28 | 0-2% definition maturity
5 | 01.06 | Cleanroom Envelope | 0.57 | 1.14 | 2.28 | 0-2% definition maturity
5 | 01.07 | Process Utilities | 0.618 | 1.235 | 2.47 | 0-2% definition maturity
5 | 01.08 | Validation / Qualification | 0.237 | 0.475 | 0.95 | 0-2% definition maturity
5 | 01.09 | Direct Labour | 0.427 | 0.855 | 1.71 | 0-2% definition maturity
5 | 01.10 | Direct Materials | 0.475 | 0.95 | 1.9 | 0-2% definition maturity
5 | 01.11 | Plant / Equipment | 0.19 | 0.38 | 0.76 | 0-2% definition maturity
5 | 02.01 | General Conditions / Prelims | 0.333 | 0.665 | 1.33 | 0-2% definition maturity
5 | 02.02 | Design / Professional Fees | 0.333 | 0.665 | 1.33 | 0-2% definition maturity
5 | 02.03 | Permits / Insurance / Bonds | 0.142 | 0.285 | 0.57 | 0-2% definition maturity
5 | 03.01 | QCRA Contingency | 0.285 | 0.57 | 1.14 | 0-2% definition maturity
5 | 03.02 | Management Reserve | 0.142 | 0.285 | 0.57 | 0-2% definition maturity

## Level 1 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
M100 | Milestone | Investment approval |  | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M200 | Milestone | Design complete | M100 | 22 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M300 | Milestone | Procurement complete | M200 | 16 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M400 | Milestone | Delivery complete | M300 | 43 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M500 | Milestone | Ready for operations | M400 | 16 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M600 | Milestone | Handover | M500 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 2 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 9 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 10 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 10 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 8 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 24 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 11 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 3 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 9 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 10 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 10 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 8 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 24 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 11 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 4 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 9 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 10 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 10 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 8 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 24 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 11 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1000 | Package | Civil / structural package | A1900 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2000 | Package | MEP / systems package | P1000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3000 | Package | Specialist equipment package | P2000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4000 | Package | Utilities / interfaces package | P3000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5000 | Package | Testing and commissioning package | P4000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 5 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 9 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 10 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 10 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 8 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 24 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 11 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1000 | Package | Civil / structural package | A1900 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1100 | Activity | Civil / structural package - mobilise / method | A1900 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1200 | Activity | Civil / structural package - execute works | P1100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1300 | Activity | Civil / structural package - inspect / closeout | P1200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2000 | Package | MEP / systems package | P1000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2100 | Activity | MEP / systems package - mobilise / method | P1000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2200 | Activity | MEP / systems package - execute works | P2100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2300 | Activity | MEP / systems package - inspect / closeout | P2200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3000 | Package | Specialist equipment package | P2000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3100 | Activity | Specialist equipment package - mobilise / method | P2000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3200 | Activity | Specialist equipment package - execute works | P3100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3300 | Activity | Specialist equipment package - inspect / closeout | P3200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4000 | Package | Utilities / interfaces package | P3000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4100 | Activity | Utilities / interfaces package - mobilise / method | P3000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4200 | Activity | Utilities / interfaces package - execute works | P4100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4300 | Activity | Utilities / interfaces package - inspect / closeout | P4200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5000 | Package | Testing and commissioning package | P4000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5100 | Activity | Testing and commissioning package - mobilise / method | P4000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5200 | Activity | Testing and commissioning package - execute works | P5100 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5300 | Activity | Testing and commissioning package - inspect / closeout | P5200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Risk Register
ID | Risk | Category | Probability | Activity | CBS | Sched O | Sched M | Sched P | Cost O | Cost M | Cost P | Owner | Trigger | Mitigation | Cost Basis | Schedule Basis
R-002 | Market escalation | Commercial | 45 | A1500 | 01.05 | 0 | 0 | 0 | 0.38 | 0.95 | 1.9 | Commercial Lead | Index exceeds allowance | Early procurement, index strategy, market testing | Cost impact derived from 01.05 Specialist Equipment / Fit-Out exposure, project P50 $9.5B, and risk severity (4%/10%/20%). | Schedule impact mapped to A1500 Procurement strategy and tender packaging with O/M/P delay 0/0/0 days and critical path sensitivity.
R-004 | Design maturity gap | Technical | 38 | A1700 | 01.07 | 15 | 45 | 120 | 0.285 | 0.855 | 1.71 | Design Manager | Deliverables late | Design maturity gates and independent review | Cost impact derived from 01.07 Process Utilities exposure, project P50 $9.5B, and risk severity (3%/9%/18%). | Schedule impact mapped to A1700 Long-lead procurement with O/M/P delay 15/45/120 days and critical path sensitivity.
R-001 | Scope growth | Scope | 42 | A1400 | 01.04 | 15 | 45 | 120 | 0.285 | 0.76 | 1.52 | Project Director | Scope change rate exceeds threshold | Freeze scope, change board, value gates | Cost impact derived from 01.04 MEP / Systems / Utilities exposure, project P50 $9.5B, and risk severity (3%/8%/16%). | Schedule impact mapped to A1400 Planning, regulatory and stakeholder approvals with O/M/P delay 15/45/120 days and critical path sensitivity.
R-006 | Productivity underperformance | Delivery | 35 | A1900 | 01.09 | 15 | 50 | 130 | 0.285 | 0.76 | 1.52 | Delivery Lead | SPI/CPI deteriorates | Package productivity controls and daily planning | Cost impact derived from 01.09 Direct Labour exposure, project P50 $9.5B, and risk severity (3%/8%/16%). | Schedule impact mapped to A1900 Main construction / fabrication / assembly with O/M/P delay 15/50/130 days and critical path sensitivity.
R-005 | Supply chain delay | Procurement | 40 | A1800 | 01.08 | 10 | 40 | 120 | 0.19 | 0.665 | 1.425 | Procurement Lead | Supplier promise date slips | Alternate suppliers, early orders, expediting | Cost impact derived from 01.08 Validation / Qualification exposure, project P50 $9.5B, and risk severity (2%/7%/15%). | Schedule impact mapped to A1800 Site / launch integration readiness with O/M/P delay 10/40/120 days and critical path sensitivity.
R-008 | Interface misalignment | Integration | 34 | A2100 | 01.11 | 10 | 35 | 100 | 0.19 | 0.665 | 1.33 | Integration Manager | Interface actions overdue | ICDs and weekly interface board | Cost impact derived from 01.11 Plant / Equipment exposure, project P50 $9.5B, and risk severity (2%/7%/14%). | Schedule impact mapped to A2100 Commissioning, operations readiness and closeout with O/M/P delay 10/35/100 days and critical path sensitivity.
R-007 | Commissioning delay | Handover | 32 | A2000 | 01.10 | 10 | 35 | 100 | 0.19 | 0.57 | 1.14 | Commissioning Lead | Test failures trend upward | Commissioning readiness and early test plans | Cost impact derived from 01.10 Direct Materials exposure, project P50 $9.5B, and risk severity (2%/6%/12%). | Schedule impact mapped to A2000 Systems integration and testing with O/M/P delay 10/35/100 days and critical path sensitivity.
R-003 | Permits / approvals delay | Regulatory | 35 | A1600 | 01.06 | 20 | 70 | 180 | 0.095 | 0.38 | 0.76 | Consents Lead | Consent milestone slips | Authority plan, consent tracker, early submissions | Cost impact derived from 01.06 Cleanroom Envelope exposure, project P50 $9.5B, and risk severity (1%/4%/8%). | Schedule impact mapped to A1600 Detailed design / IFC development with O/M/P delay 20/70/180 days and critical path sensitivity.

## Monte Carlo P-Curve
Percentile | QCRA Cost BN | QSRA Months
1 | 9.326 | 103.75
5 | 10.022 | 106.41
10 | 10.434 | 108.21
20 | 10.96 | 110.44
30 | 11.341 | 112.08
40 | 11.678 | 113.67
50 | 12.018 | 115.23
60 | 12.36 | 116.86
70 | 12.741 | 118.62
80 | 13.167 | 120.72
90 | 13.793 | 123.48
95 | 14.313 | 125.7
99 | 15.402 | 129.22

## Tornado Drivers
Risk | Title | Activity | CBS | Cost Mean BN | Schedule Mean Days | Driver Score
R-002 | Market escalation | A1500 | 01.05 | 0.479 | 0 | 47.89
R-001 | Scope growth | A1400 | 01.04 | 0.358 | 25.3 | 38.31
R-004 | Design maturity gap | A1700 | 01.07 | 0.354 | 22.6 | 37.62
R-005 | Supply chain delay | A1800 | 01.08 | 0.306 | 22.9 | 32.86
R-006 | Productivity underperformance | A1900 | 01.09 | 0.298 | 22.5 | 32.05
R-008 | Interface misalignment | A2100 | 01.11 | 0.25 | 17 | 26.7
R-007 | Commissioning delay | A2000 | 01.10 | 0.197 | 15.2 | 21.27
R-003 | Permits / approvals delay | A1600 | 01.06 | 0.143 | 31.5 | 17.45

## Scenarios
Scenario | Cost | Schedule Months | Risk | Confidence | Why
Base | $9.5B | 108 | Medium-High | 60 | Balanced reference case.
Faster | $10.5B | 89 | High | 51 | Parallel design/procurement, acceleration, premium logistics and higher interface risk.
Cheaper | $8.4B | 117 | Medium-High | 54 | Value engineering, tighter scope and procurement competition, with schedule/quality exposure.
Lower Risk | $10.4B | 119 | Medium | 73 | More surveys, assurance, stage gates, contingency and schedule buffers.
Premium | $10.9B | 112 | Medium | 76 | Best assurance, independent review, early procurement and high-confidence governance.
Investor | $9.3B | 108 | Medium-High | 63 | Investment-framing case with transparent risk and commercial challenge.
Survival | $7.4B | 130 | High | 46 | Minimum viable scope, warning-heavy, high residual risk.

## Benchmarks
Metric | Value | Why
Capital project benchmark | Sector-adjusted range | Selected based on project type, location, maturity and scale.
Schedule benchmark | 86-140 months | Derived from maturity and delivery complexity.

## Demo Script
Step
Open with: 'Give me any project on Earth or in Space.'
Type the project into CASEY and hit Generate Full Intelligence Pack.
Show the executive dashboard: cost, schedule, risk, confidence and top drivers.
Switch to Monte Carlo: show QCRA/QSRA P-curves and tornado drivers linked to activities.
Show scenarios: Faster, Cheaper, Lower Risk and Premium with why each changed.
Open Output Centre: Excel, Risk CSV, XER, Word, PDF, PPTX and ZIP are ready.
Close with: 'Traditional advisory takes weeks. CASEY gives the first board-grade view in seconds.'