## Board Summary
Field | Value
Generated | 2026-05-02T20:00:49.211473
Version | v23 Real Deal Edition
Title | AI Data Centre Campus
Client | Microsoft
Executive Summary | AI Data Centre Campus has been classified as Digital Infrastructure / Hyperscale Data Centre in Saudi Arabia / GCC. CASEY estimates $10.7B P50 cost, $8.6B to $13.9B range, 64 month baseline, Medium risk and 64% confidence under the Base scenario.
Mode | Earth
Subsector | Digital Infrastructure / Hyperscale Data Centre
Location | Saudi Arabia / GCC
Scenario | Base
Cost P10 | $8.6B
Cost P50 | $10.7B
Cost P90 | $13.9B
Schedule | 64 months
QCRA P80 | $16.0B
QSRA P80 | 76.91
Risk | Medium
Confidence | 64%

## Primary Cost Estimate
CBS | Description | Type | Basis | P10 BN | P50 BN | P90 BN | Impact Basis
01.01 | Site Preparation / Enabling | Direct | Demolition, enabling, logistics and access | 0.515 | 0.643 | 0.836 | Site Preparation / Enabling priced as 6.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.02 | Substructure / Foundations | Direct | Piling, groundworks, retaining and foundations | 0.686 | 0.858 | 1.115 | Substructure / Foundations priced as 8.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.03 | Superstructure / Civil Works | Direct | Frame, civils, primary structures | 1.201 | 1.501 | 1.951 | Superstructure / Civil Works priced as 14.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.04 | MEP / Systems / Utilities | Direct | Mechanical, electrical, controls and utilities | 1.201 | 1.501 | 1.951 | MEP / Systems / Utilities priced as 14.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.05 | Specialist Equipment / Fit-Out | Direct | Permanent equipment and specialist fit-out | 1.029 | 1.287 | 1.673 | Specialist Equipment / Fit-Out priced as 12.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.06 | Data Halls / White Space | Direct | Server halls, fit-out and critical rooms | 1.115 | 1.394 | 1.812 | Data Halls / White Space priced as 13.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.07 | Power Train / Substations | Direct | HV/MV gear, UPS, generators and substations | 1.372 | 1.715 | 2.23 | Power Train / Substations priced as 16.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.08 | Cooling Systems | Direct | Chillers, heat rejection, CRAH/CRAC, water systems | 1.029 | 1.287 | 1.673 | Cooling Systems priced as 12.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.09 | Direct Labour | Direct | Productivity, supervision and trade labour | 0.772 | 0.965 | 1.254 | Direct Labour priced as 9.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.10 | Direct Materials | Direct | Concrete, steel, envelope, MEP materials | 0.858 | 1.072 | 1.394 | Direct Materials priced as 10.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
01.11 | Plant / Equipment | Direct | Cranes, heavy plant and site equipment | 0.343 | 0.429 | 0.558 | Plant / Equipment priced as 4.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
02.01 | General Conditions / Prelims | Indirect | Site management, safety, offices and temporary services | 0.6 | 0.751 | 0.976 | General Conditions / Prelims priced as 7.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
02.02 | Design / Professional Fees | Indirect | Design, QS, controls, assurance and consultants | 0.6 | 0.751 | 0.976 | Design / Professional Fees priced as 7.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
02.03 | Permits / Insurance / Bonds | Indirect | Permits, inspections, legal, bonds and insurance | 0.257 | 0.322 | 0.418 | Permits / Insurance / Bonds priced as 3.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
03.01 | QCRA Contingency | Reserve | Known-unknown risk allowance | 0.515 | 0.643 | 0.836 | QCRA Contingency priced as 6.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.
03.02 | Management Reserve | Reserve | Sponsor-held reserve | 0.257 | 0.322 | 0.418 | Management Reserve priced as 3.0% of P50 from sector template, location factor 1.35, scale factor 1.90, complexity factor 1.10.

## Class 1 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
1 | 01.01 | Site Preparation / Enabling | 0.579 | 0.643 | 0.739 | 65-100% definition maturity
1 | 01.02 | Substructure / Foundations | 0.772 | 0.858 | 0.987 | 65-100% definition maturity
1 | 01.03 | Superstructure / Civil Works | 1.351 | 1.501 | 1.726 | 65-100% definition maturity
1 | 01.04 | MEP / Systems / Utilities | 1.351 | 1.501 | 1.726 | 65-100% definition maturity
1 | 01.05 | Specialist Equipment / Fit-Out | 1.158 | 1.287 | 1.48 | 65-100% definition maturity
1 | 01.06 | Data Halls / White Space | 1.255 | 1.394 | 1.603 | 65-100% definition maturity
1 | 01.07 | Power Train / Substations | 1.544 | 1.715 | 1.972 | 65-100% definition maturity
1 | 01.08 | Cooling Systems | 1.158 | 1.287 | 1.48 | 65-100% definition maturity
1 | 01.09 | Direct Labour | 0.868 | 0.965 | 1.11 | 65-100% definition maturity
1 | 01.10 | Direct Materials | 0.965 | 1.072 | 1.233 | 65-100% definition maturity
1 | 01.11 | Plant / Equipment | 0.386 | 0.429 | 0.493 | 65-100% definition maturity
1 | 02.01 | General Conditions / Prelims | 0.676 | 0.751 | 0.864 | 65-100% definition maturity
1 | 02.02 | Design / Professional Fees | 0.676 | 0.751 | 0.864 | 65-100% definition maturity
1 | 02.03 | Permits / Insurance / Bonds | 0.29 | 0.322 | 0.37 | 65-100% definition maturity
1 | 03.01 | QCRA Contingency | 0.579 | 0.643 | 0.739 | 65-100% definition maturity
1 | 03.02 | Management Reserve | 0.29 | 0.322 | 0.37 | 65-100% definition maturity

## Class 2 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
2 | 01.01 | Site Preparation / Enabling | 0.547 | 0.643 | 0.772 | 30-75% definition maturity
2 | 01.02 | Substructure / Foundations | 0.729 | 0.858 | 1.03 | 30-75% definition maturity
2 | 01.03 | Superstructure / Civil Works | 1.276 | 1.501 | 1.801 | 30-75% definition maturity
2 | 01.04 | MEP / Systems / Utilities | 1.276 | 1.501 | 1.801 | 30-75% definition maturity
2 | 01.05 | Specialist Equipment / Fit-Out | 1.094 | 1.287 | 1.544 | 30-75% definition maturity
2 | 01.06 | Data Halls / White Space | 1.185 | 1.394 | 1.673 | 30-75% definition maturity
2 | 01.07 | Power Train / Substations | 1.458 | 1.715 | 2.058 | 30-75% definition maturity
2 | 01.08 | Cooling Systems | 1.094 | 1.287 | 1.544 | 30-75% definition maturity
2 | 01.09 | Direct Labour | 0.82 | 0.965 | 1.158 | 30-75% definition maturity
2 | 01.10 | Direct Materials | 0.911 | 1.072 | 1.286 | 30-75% definition maturity
2 | 01.11 | Plant / Equipment | 0.365 | 0.429 | 0.515 | 30-75% definition maturity
2 | 02.01 | General Conditions / Prelims | 0.638 | 0.751 | 0.901 | 30-75% definition maturity
2 | 02.02 | Design / Professional Fees | 0.638 | 0.751 | 0.901 | 30-75% definition maturity
2 | 02.03 | Permits / Insurance / Bonds | 0.274 | 0.322 | 0.386 | 30-75% definition maturity
2 | 03.01 | QCRA Contingency | 0.547 | 0.643 | 0.772 | 30-75% definition maturity
2 | 03.02 | Management Reserve | 0.274 | 0.322 | 0.386 | 30-75% definition maturity

## Class 3 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
3 | 01.01 | Site Preparation / Enabling | 0.514 | 0.643 | 0.836 | 10-40% definition maturity
3 | 01.02 | Substructure / Foundations | 0.686 | 0.858 | 1.115 | 10-40% definition maturity
3 | 01.03 | Superstructure / Civil Works | 1.201 | 1.501 | 1.951 | 10-40% definition maturity
3 | 01.04 | MEP / Systems / Utilities | 1.201 | 1.501 | 1.951 | 10-40% definition maturity
3 | 01.05 | Specialist Equipment / Fit-Out | 1.03 | 1.287 | 1.673 | 10-40% definition maturity
3 | 01.06 | Data Halls / White Space | 1.115 | 1.394 | 1.812 | 10-40% definition maturity
3 | 01.07 | Power Train / Substations | 1.372 | 1.715 | 2.23 | 10-40% definition maturity
3 | 01.08 | Cooling Systems | 1.03 | 1.287 | 1.673 | 10-40% definition maturity
3 | 01.09 | Direct Labour | 0.772 | 0.965 | 1.254 | 10-40% definition maturity
3 | 01.10 | Direct Materials | 0.858 | 1.072 | 1.394 | 10-40% definition maturity
3 | 01.11 | Plant / Equipment | 0.343 | 0.429 | 0.558 | 10-40% definition maturity
3 | 02.01 | General Conditions / Prelims | 0.601 | 0.751 | 0.976 | 10-40% definition maturity
3 | 02.02 | Design / Professional Fees | 0.601 | 0.751 | 0.976 | 10-40% definition maturity
3 | 02.03 | Permits / Insurance / Bonds | 0.258 | 0.322 | 0.419 | 10-40% definition maturity
3 | 03.01 | QCRA Contingency | 0.514 | 0.643 | 0.836 | 10-40% definition maturity
3 | 03.02 | Management Reserve | 0.258 | 0.322 | 0.419 | 10-40% definition maturity

## Class 4 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
4 | 01.01 | Site Preparation / Enabling | 0.45 | 0.643 | 0.965 | 1-15% definition maturity
4 | 01.02 | Substructure / Foundations | 0.601 | 0.858 | 1.287 | 1-15% definition maturity
4 | 01.03 | Superstructure / Civil Works | 1.051 | 1.501 | 2.252 | 1-15% definition maturity
4 | 01.04 | MEP / Systems / Utilities | 1.051 | 1.501 | 2.252 | 1-15% definition maturity
4 | 01.05 | Specialist Equipment / Fit-Out | 0.901 | 1.287 | 1.93 | 1-15% definition maturity
4 | 01.06 | Data Halls / White Space | 0.976 | 1.394 | 2.091 | 1-15% definition maturity
4 | 01.07 | Power Train / Substations | 1.2 | 1.715 | 2.573 | 1-15% definition maturity
4 | 01.08 | Cooling Systems | 0.901 | 1.287 | 1.93 | 1-15% definition maturity
4 | 01.09 | Direct Labour | 0.675 | 0.965 | 1.448 | 1-15% definition maturity
4 | 01.10 | Direct Materials | 0.75 | 1.072 | 1.608 | 1-15% definition maturity
4 | 01.11 | Plant / Equipment | 0.3 | 0.429 | 0.643 | 1-15% definition maturity
4 | 02.01 | General Conditions / Prelims | 0.526 | 0.751 | 1.127 | 1-15% definition maturity
4 | 02.02 | Design / Professional Fees | 0.526 | 0.751 | 1.127 | 1-15% definition maturity
4 | 02.03 | Permits / Insurance / Bonds | 0.225 | 0.322 | 0.483 | 1-15% definition maturity
4 | 03.01 | QCRA Contingency | 0.45 | 0.643 | 0.965 | 1-15% definition maturity
4 | 03.02 | Management Reserve | 0.225 | 0.322 | 0.483 | 1-15% definition maturity

## Class 5 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
5 | 01.01 | Site Preparation / Enabling | 0.322 | 0.643 | 1.286 | 0-2% definition maturity
5 | 01.02 | Substructure / Foundations | 0.429 | 0.858 | 1.716 | 0-2% definition maturity
5 | 01.03 | Superstructure / Civil Works | 0.75 | 1.501 | 3.002 | 0-2% definition maturity
5 | 01.04 | MEP / Systems / Utilities | 0.75 | 1.501 | 3.002 | 0-2% definition maturity
5 | 01.05 | Specialist Equipment / Fit-Out | 0.643 | 1.287 | 2.574 | 0-2% definition maturity
5 | 01.06 | Data Halls / White Space | 0.697 | 1.394 | 2.788 | 0-2% definition maturity
5 | 01.07 | Power Train / Substations | 0.858 | 1.715 | 3.43 | 0-2% definition maturity
5 | 01.08 | Cooling Systems | 0.643 | 1.287 | 2.574 | 0-2% definition maturity
5 | 01.09 | Direct Labour | 0.482 | 0.965 | 1.93 | 0-2% definition maturity
5 | 01.10 | Direct Materials | 0.536 | 1.072 | 2.144 | 0-2% definition maturity
5 | 01.11 | Plant / Equipment | 0.214 | 0.429 | 0.858 | 0-2% definition maturity
5 | 02.01 | General Conditions / Prelims | 0.376 | 0.751 | 1.502 | 0-2% definition maturity
5 | 02.02 | Design / Professional Fees | 0.376 | 0.751 | 1.502 | 0-2% definition maturity
5 | 02.03 | Permits / Insurance / Bonds | 0.161 | 0.322 | 0.644 | 0-2% definition maturity
5 | 03.01 | QCRA Contingency | 0.322 | 0.643 | 1.286 | 0-2% definition maturity
5 | 03.02 | Management Reserve | 0.161 | 0.322 | 0.644 | 0-2% definition maturity

## Level 1 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
M100 | Milestone | Investment approval |  | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M200 | Milestone | Design complete | M100 | 13 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M300 | Milestone | Procurement complete | M200 | 10 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M400 | Milestone | Delivery complete | M300 | 26 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M500 | Milestone | Ready for operations | M400 | 10 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M600 | Milestone | Handover | M500 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 2 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 14 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 3 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 14 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 4 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 14 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1000 | Package | Grid connection | A1900 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2000 | Package | Data halls | P1000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3000 | Package | Cooling plant | P2000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4000 | Package | Power train | P3000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5000 | Package | Controls and commissioning | P4000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 5 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 6 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 14 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 6 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1000 | Package | Grid connection | A1900 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1100 | Activity | Grid connection - mobilise / method | A1900 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1200 | Activity | Grid connection - execute works | P1100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1300 | Activity | Grid connection - inspect / closeout | P1200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2000 | Package | Data halls | P1000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2100 | Activity | Data halls - mobilise / method | P1000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2200 | Activity | Data halls - execute works | P2100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2300 | Activity | Data halls - inspect / closeout | P2200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3000 | Package | Cooling plant | P2000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3100 | Activity | Cooling plant - mobilise / method | P2000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3200 | Activity | Cooling plant - execute works | P3100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3300 | Activity | Cooling plant - inspect / closeout | P3200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4000 | Package | Power train | P3000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4100 | Activity | Power train - mobilise / method | P3000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4200 | Activity | Power train - execute works | P4100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4300 | Activity | Power train - inspect / closeout | P4200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5000 | Package | Controls and commissioning | P4000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5100 | Activity | Controls and commissioning - mobilise / method | P4000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5200 | Activity | Controls and commissioning - execute works | P5100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5300 | Activity | Controls and commissioning - inspect / closeout | P5200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Risk Register
ID | Risk | Category | Probability | Activity | CBS | Sched O | Sched M | Sched P | Cost O | Cost M | Cost P | Owner | Trigger | Mitigation | Cost Basis | Schedule Basis
R-D01 | Grid connection delay | Utilities | 48 | A1400 | 01.04 | 20 | 80 | 220 | 0.322 | 1.072 | 2.359 | Utilities Lead | Grid agreement unsigned | Secure grid agreement, temporary power, early equipment orders | Cost impact derived from 01.04 MEP / Systems / Utilities exposure, project P50 $10.7B, and risk severity (3%/10%/22%). | Schedule impact mapped to A1400 Planning, regulatory and stakeholder approvals with O/M/P delay 20/80/220 days and critical path sensitivity.
R-002 | Market escalation | Commercial | 45 | A1700 | 01.07 | 0 | 0 | 0 | 0.429 | 1.072 | 2.144 | Commercial Lead | Index exceeds allowance | Early procurement, index strategy, market testing | Cost impact derived from 01.07 Power Train / Substations exposure, project P50 $10.7B, and risk severity (4%/10%/20%). | Schedule impact mapped to A1700 Long-lead procurement with O/M/P delay 0/0/0 days and critical path sensitivity.
R-004 | Design maturity gap | Technical | 38 | A1900 | 01.09 | 15 | 45 | 120 | 0.322 | 0.965 | 1.93 | Design Manager | Deliverables late | Design maturity gates and independent review | Cost impact derived from 01.09 Direct Labour exposure, project P50 $10.7B, and risk severity (3%/9%/18%). | Schedule impact mapped to A1900 Main construction / fabrication / assembly with O/M/P delay 15/45/120 days and critical path sensitivity.
R-001 | Scope growth | Scope | 42 | A1600 | 01.06 | 15 | 45 | 120 | 0.322 | 0.858 | 1.715 | Project Director | Scope change rate exceeds threshold | Freeze scope, change board, value gates | Cost impact derived from 01.06 Data Halls / White Space exposure, project P50 $10.7B, and risk severity (3%/8%/16%). | Schedule impact mapped to A1600 Detailed design / IFC development with O/M/P delay 15/45/120 days and critical path sensitivity.
R-006 | Productivity underperformance | Delivery | 35 | A2100 | 01.11 | 15 | 50 | 130 | 0.322 | 0.858 | 1.715 | Delivery Lead | SPI/CPI deteriorates | Package productivity controls and daily planning | Cost impact derived from 01.11 Plant / Equipment exposure, project P50 $10.7B, and risk severity (3%/8%/16%). | Schedule impact mapped to A2100 Commissioning, operations readiness and closeout with O/M/P delay 15/50/130 days and critical path sensitivity.
R-005 | Supply chain delay | Procurement | 40 | A2000 | 01.10 | 10 | 40 | 120 | 0.214 | 0.751 | 1.608 | Procurement Lead | Supplier promise date slips | Alternate suppliers, early orders, expediting | Cost impact derived from 01.10 Direct Materials exposure, project P50 $10.7B, and risk severity (2%/7%/15%). | Schedule impact mapped to A2000 Systems integration and testing with O/M/P delay 10/40/120 days and critical path sensitivity.
R-D02 | Cooling system capacity | Technical | 34 | A1500 | 01.05 | 10 | 40 | 120 | 0.214 | 0.751 | 1.608 | MEP Lead | Cooling tests fail | Early thermal modelling and supplier validation | Cost impact derived from 01.05 Specialist Equipment / Fit-Out exposure, project P50 $10.7B, and risk severity (2%/7%/15%). | Schedule impact mapped to A1500 Procurement strategy and tender packaging with O/M/P delay 10/40/120 days and critical path sensitivity.
R-008 | Interface misalignment | Integration | 34 | P2000 | 02.02 | 10 | 35 | 100 | 0.214 | 0.751 | 1.501 | Integration Manager | Interface actions overdue | ICDs and weekly interface board | Cost impact derived from 02.02 Design / Professional Fees exposure, project P50 $10.7B, and risk severity (2%/7%/14%). | Schedule impact mapped to P2000 Data halls with O/M/P delay 10/35/100 days and critical path sensitivity.
R-007 | Commissioning delay | Handover | 32 | P1000 | 02.01 | 10 | 35 | 100 | 0.214 | 0.643 | 1.287 | Commissioning Lead | Test failures trend upward | Commissioning readiness and early test plans | Cost impact derived from 02.01 General Conditions / Prelims exposure, project P50 $10.7B, and risk severity (2%/6%/12%). | Schedule impact mapped to P1000 Grid connection with O/M/P delay 10/35/100 days and critical path sensitivity.
R-003 | Permits / approvals delay | Regulatory | 35 | A1800 | 01.08 | 20 | 70 | 180 | 0.107 | 0.429 | 0.858 | Consents Lead | Consent milestone slips | Authority plan, consent tracker, early submissions | Cost impact derived from 01.08 Cooling Systems exposure, project P50 $10.7B, and risk severity (1%/4%/8%). | Schedule impact mapped to A1800 Site / launch integration readiness with O/M/P delay 20/70/180 days and critical path sensitivity.

## Monte Carlo P-Curve
Percentile | QCRA Cost BN | QSRA Months
1 | 10.921 | 63.18
5 | 11.817 | 65.52
10 | 12.361 | 66.94
20 | 13.057 | 68.78
30 | 13.57 | 70.21
40 | 14.022 | 71.51
50 | 14.43 | 72.69
60 | 14.883 | 73.97
70 | 15.368 | 75.29
80 | 15.975 | 76.91
90 | 16.76 | 79.11
95 | 17.405 | 80.91
99 | 18.554 | 84.59

## Tornado Drivers
Risk | Title | Activity | CBS | Cost Mean BN | Schedule Mean Days | Driver Score
R-D01 | Grid connection delay | A1400 | 01.04 | 0.603 | 50.9 | 65.41
R-002 | Market escalation | A1700 | 01.07 | 0.538 | 0 | 53.76
R-004 | Design maturity gap | A1900 | 01.09 | 0.408 | 22.9 | 43.13
R-001 | Scope growth | A1600 | 01.06 | 0.402 | 25 | 42.74
R-005 | Supply chain delay | A2000 | 01.10 | 0.348 | 23 | 37.13
R-006 | Productivity underperformance | A2100 | 01.11 | 0.331 | 22.3 | 35.3
R-D02 | Cooling system capacity | A1500 | 01.05 | 0.289 | 19.2 | 30.83
R-008 | Interface misalignment | P2000 | 02.02 | 0.273 | 16.3 | 28.93
R-007 | Commissioning delay | P1000 | 02.01 | 0.228 | 15.6 | 24.37
R-003 | Permits / approvals delay | A1800 | 01.08 | 0.162 | 31.4 | 19.3

## Scenarios
Scenario | Cost | Schedule Months | Risk | Confidence | Why
Base | $10.7B | 64 | Medium | 64 | Balanced reference case.
Faster | $11.9B | 52 | Medium-High | 55 | Parallel design/procurement, acceleration, premium logistics and higher interface risk.
Cheaper | $9.4B | 69 | Medium | 58 | Value engineering, tighter scope and procurement competition, with schedule/quality exposure.
Lower Risk | $11.7B | 70 | Medium | 73 | More surveys, assurance, stage gates, contingency and schedule buffers.
Premium | $12.3B | 67 | Medium | 76 | Best assurance, independent review, early procurement and high-confidence governance.
Investor | $10.5B | 64 | Medium | 67 | Investment-framing case with transparent risk and commercial challenge.
Survival | $8.4B | 77 | Medium-High | 50 | Minimum viable scope, warning-heavy, high residual risk.

## Benchmarks
Metric | Value | Why
Hyperscale delivery benchmark | $8M-$18M per MW equivalent | Varies by power density, grid scope, cooling, land and regional constraints.
Schedule benchmark | 30-60 months | Driven by grid connection, long-lead electrical equipment and phased fit-out.
Top benchmark gap | Power availability | Grid connection is frequently the dominant schedule and risk driver.

## Demo Script
Step
Open with: 'Give me any project on Earth or in Space.'
Type the project into CASEY and hit Generate Full Intelligence Pack.
Show the executive dashboard: cost, schedule, risk, confidence and top drivers.
Switch to Monte Carlo: show QCRA/QSRA P-curves and tornado drivers linked to activities.
Show scenarios: Faster, Cheaper, Lower Risk and Premium with why each changed.
Open Output Centre: Excel, Risk CSV, XER, Word, PDF, PPTX and ZIP are ready.
Close with: 'Traditional advisory takes weeks. CASEY gives the first board-grade view in seconds.'