## Board Summary
Field | Value
Generated | 2026-05-02T20:00:52.540077
Version | v23 Real Deal Edition
Title | Space Base
Client | Lunar Development Authority
Executive Summary | Space Base has been classified as Surface Habitat/Base in Moon / Lunar Surface. CASEY estimates $181.7B P50 cost, $145.3B to $236.2B range, 224 month baseline, Extreme risk and 46% confidence under the Base scenario.
Mode | Space
Subsector | Surface Habitat/Base
Location | Moon / Lunar Surface
Scenario | Base
Cost P10 | $145.3B
Cost P50 | $181.7B
Cost P90 | $236.2B
Schedule | 224 months
QCRA P80 | $288.3B
QSRA P80 | 247.48
Risk | Extreme
Confidence | 46%

## Primary Cost Estimate
CBS | Description | Type | Basis | P10 BN | P50 BN | P90 BN | Impact Basis
01.01 | DDT&E Engineering | Direct | Engineering design, mission architecture and qualification | 13.079 | 16.349 | 21.254 | DDT&E Engineering priced as 9.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.02 | Systems Engineering & Integration | Direct | Requirements, ICDs, verification and validation | 8.719 | 10.899 | 14.169 | Systems Engineering & Integration priced as 6.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.03 | Structures / Habitat Shell | Direct | Pressure vessels, shielding and primary structures | 14.532 | 18.166 | 23.615 | Structures / Habitat Shell priced as 10.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.04 | Power Generation & Distribution | Direct | Solar/nuclear source, grid and controls | 11.626 | 14.532 | 18.892 | Power Generation & Distribution priced as 8.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.05 | ECLSS / Life Support | Direct | Air, water, waste, atmosphere and safety systems | 13.079 | 16.349 | 21.254 | ECLSS / Life Support priced as 9.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.06 | Payload / Mission Equipment | Direct | Scientific, medical, industrial or settlement payload | 10.173 | 12.716 | 16.531 | Payload / Mission Equipment priced as 7.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.07 | Robotics / Autonomous Construction | Direct | Robotic construction, inspection and maintenance | 8.719 | 10.899 | 14.169 | Robotics / Autonomous Construction priced as 6.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.08 | Launch Services | Direct | Launch vehicle, manifest, payload processing | 20.345 | 25.432 | 33.061 | Launch Services priced as 14.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
01.09 | Transport / Landing / Surface Logistics | Direct | Transit, landing, mobility and logistics chain | 13.079 | 16.349 | 21.254 | Transport / Landing / Surface Logistics priced as 9.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
02.01 | Test & Qualification Facilities | Indirect | Thermal-vac, vibration, radiation and integrated testing | 7.266 | 9.083 | 11.808 | Test & Qualification Facilities priced as 5.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
02.02 | Safety & Mission Assurance | Indirect | Quality, safety, independent review and compliance | 7.266 | 9.083 | 11.808 | Safety & Mission Assurance priced as 5.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
02.03 | Programme Management / PMO | Indirect | Controls, reporting, commercial and integration PMO | 7.266 | 9.083 | 11.808 | Programme Management / PMO priced as 5.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
03.01 | Risk Contingency / UFE | Reserve | Known-unknown risk allowance linked to QCRA/QSRA | 10.173 | 12.716 | 16.531 | Risk Contingency / UFE priced as 7.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.
03.02 | Management Reserve | Reserve | Sponsor-held unknown-unknown reserve | 7.266 | 9.083 | 11.808 | Management Reserve priced as 5.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96.

## Class 1 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
1 | 01.01 | DDT&E Engineering | 14.714 | 16.349 | 18.801 | 65-100% definition maturity
1 | 01.02 | Systems Engineering & Integration | 9.809 | 10.899 | 12.534 | 65-100% definition maturity
1 | 01.03 | Structures / Habitat Shell | 16.349 | 18.166 | 20.891 | 65-100% definition maturity
1 | 01.04 | Power Generation & Distribution | 13.079 | 14.532 | 16.712 | 65-100% definition maturity
1 | 01.05 | ECLSS / Life Support | 14.714 | 16.349 | 18.801 | 65-100% definition maturity
1 | 01.06 | Payload / Mission Equipment | 11.444 | 12.716 | 14.623 | 65-100% definition maturity
1 | 01.07 | Robotics / Autonomous Construction | 9.809 | 10.899 | 12.534 | 65-100% definition maturity
1 | 01.08 | Launch Services | 22.889 | 25.432 | 29.247 | 65-100% definition maturity
1 | 01.09 | Transport / Landing / Surface Logistics | 14.714 | 16.349 | 18.801 | 65-100% definition maturity
1 | 02.01 | Test & Qualification Facilities | 8.175 | 9.083 | 10.445 | 65-100% definition maturity
1 | 02.02 | Safety & Mission Assurance | 8.175 | 9.083 | 10.445 | 65-100% definition maturity
1 | 02.03 | Programme Management / PMO | 8.175 | 9.083 | 10.445 | 65-100% definition maturity
1 | 03.01 | Risk Contingency / UFE | 11.444 | 12.716 | 14.623 | 65-100% definition maturity
1 | 03.02 | Management Reserve | 8.175 | 9.083 | 10.445 | 65-100% definition maturity

## Class 2 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
2 | 01.01 | DDT&E Engineering | 13.897 | 16.349 | 19.619 | 30-75% definition maturity
2 | 01.02 | Systems Engineering & Integration | 9.264 | 10.899 | 13.079 | 30-75% definition maturity
2 | 01.03 | Structures / Habitat Shell | 15.441 | 18.166 | 21.799 | 30-75% definition maturity
2 | 01.04 | Power Generation & Distribution | 12.352 | 14.532 | 17.438 | 30-75% definition maturity
2 | 01.05 | ECLSS / Life Support | 13.897 | 16.349 | 19.619 | 30-75% definition maturity
2 | 01.06 | Payload / Mission Equipment | 10.809 | 12.716 | 15.259 | 30-75% definition maturity
2 | 01.07 | Robotics / Autonomous Construction | 9.264 | 10.899 | 13.079 | 30-75% definition maturity
2 | 01.08 | Launch Services | 21.617 | 25.432 | 30.518 | 30-75% definition maturity
2 | 01.09 | Transport / Landing / Surface Logistics | 13.897 | 16.349 | 19.619 | 30-75% definition maturity
2 | 02.01 | Test & Qualification Facilities | 7.721 | 9.083 | 10.9 | 30-75% definition maturity
2 | 02.02 | Safety & Mission Assurance | 7.721 | 9.083 | 10.9 | 30-75% definition maturity
2 | 02.03 | Programme Management / PMO | 7.721 | 9.083 | 10.9 | 30-75% definition maturity
2 | 03.01 | Risk Contingency / UFE | 10.809 | 12.716 | 15.259 | 30-75% definition maturity
2 | 03.02 | Management Reserve | 7.721 | 9.083 | 10.9 | 30-75% definition maturity

## Class 3 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
3 | 01.01 | DDT&E Engineering | 13.079 | 16.349 | 21.254 | 10-40% definition maturity
3 | 01.02 | Systems Engineering & Integration | 8.719 | 10.899 | 14.169 | 10-40% definition maturity
3 | 01.03 | Structures / Habitat Shell | 14.533 | 18.166 | 23.616 | 10-40% definition maturity
3 | 01.04 | Power Generation & Distribution | 11.626 | 14.532 | 18.892 | 10-40% definition maturity
3 | 01.05 | ECLSS / Life Support | 13.079 | 16.349 | 21.254 | 10-40% definition maturity
3 | 01.06 | Payload / Mission Equipment | 10.173 | 12.716 | 16.531 | 10-40% definition maturity
3 | 01.07 | Robotics / Autonomous Construction | 8.719 | 10.899 | 14.169 | 10-40% definition maturity
3 | 01.08 | Launch Services | 20.346 | 25.432 | 33.062 | 10-40% definition maturity
3 | 01.09 | Transport / Landing / Surface Logistics | 13.079 | 16.349 | 21.254 | 10-40% definition maturity
3 | 02.01 | Test & Qualification Facilities | 7.266 | 9.083 | 11.808 | 10-40% definition maturity
3 | 02.02 | Safety & Mission Assurance | 7.266 | 9.083 | 11.808 | 10-40% definition maturity
3 | 02.03 | Programme Management / PMO | 7.266 | 9.083 | 11.808 | 10-40% definition maturity
3 | 03.01 | Risk Contingency / UFE | 10.173 | 12.716 | 16.531 | 10-40% definition maturity
3 | 03.02 | Management Reserve | 7.266 | 9.083 | 11.808 | 10-40% definition maturity

## Class 4 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
4 | 01.01 | DDT&E Engineering | 11.444 | 16.349 | 24.523 | 1-15% definition maturity
4 | 01.02 | Systems Engineering & Integration | 7.629 | 10.899 | 16.348 | 1-15% definition maturity
4 | 01.03 | Structures / Habitat Shell | 12.716 | 18.166 | 27.249 | 1-15% definition maturity
4 | 01.04 | Power Generation & Distribution | 10.172 | 14.532 | 21.798 | 1-15% definition maturity
4 | 01.05 | ECLSS / Life Support | 11.444 | 16.349 | 24.523 | 1-15% definition maturity
4 | 01.06 | Payload / Mission Equipment | 8.901 | 12.716 | 19.074 | 1-15% definition maturity
4 | 01.07 | Robotics / Autonomous Construction | 7.629 | 10.899 | 16.348 | 1-15% definition maturity
4 | 01.08 | Launch Services | 17.802 | 25.432 | 38.148 | 1-15% definition maturity
4 | 01.09 | Transport / Landing / Surface Logistics | 11.444 | 16.349 | 24.523 | 1-15% definition maturity
4 | 02.01 | Test & Qualification Facilities | 6.358 | 9.083 | 13.625 | 1-15% definition maturity
4 | 02.02 | Safety & Mission Assurance | 6.358 | 9.083 | 13.625 | 1-15% definition maturity
4 | 02.03 | Programme Management / PMO | 6.358 | 9.083 | 13.625 | 1-15% definition maturity
4 | 03.01 | Risk Contingency / UFE | 8.901 | 12.716 | 19.074 | 1-15% definition maturity
4 | 03.02 | Management Reserve | 6.358 | 9.083 | 13.625 | 1-15% definition maturity

## Class 5 Estimate
Class | CBS | Description | P10 | P50 | P90 | Maturity
5 | 01.01 | DDT&E Engineering | 8.175 | 16.349 | 32.698 | 0-2% definition maturity
5 | 01.02 | Systems Engineering & Integration | 5.449 | 10.899 | 21.798 | 0-2% definition maturity
5 | 01.03 | Structures / Habitat Shell | 9.083 | 18.166 | 36.332 | 0-2% definition maturity
5 | 01.04 | Power Generation & Distribution | 7.266 | 14.532 | 29.064 | 0-2% definition maturity
5 | 01.05 | ECLSS / Life Support | 8.175 | 16.349 | 32.698 | 0-2% definition maturity
5 | 01.06 | Payload / Mission Equipment | 6.358 | 12.716 | 25.432 | 0-2% definition maturity
5 | 01.07 | Robotics / Autonomous Construction | 5.449 | 10.899 | 21.798 | 0-2% definition maturity
5 | 01.08 | Launch Services | 12.716 | 25.432 | 50.864 | 0-2% definition maturity
5 | 01.09 | Transport / Landing / Surface Logistics | 8.175 | 16.349 | 32.698 | 0-2% definition maturity
5 | 02.01 | Test & Qualification Facilities | 4.542 | 9.083 | 18.166 | 0-2% definition maturity
5 | 02.02 | Safety & Mission Assurance | 4.542 | 9.083 | 18.166 | 0-2% definition maturity
5 | 02.03 | Programme Management / PMO | 4.542 | 9.083 | 18.166 | 0-2% definition maturity
5 | 03.01 | Risk Contingency / UFE | 6.358 | 12.716 | 25.432 | 0-2% definition maturity
5 | 03.02 | Management Reserve | 4.542 | 9.083 | 18.166 | 0-2% definition maturity

## Level 1 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
M100 | Milestone | Investment approval |  | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M200 | Milestone | Design complete | M100 | 45 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M300 | Milestone | Procurement complete | M200 | 34 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M400 | Milestone | Delivery complete | M300 | 90 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M500 | Milestone | Ready for operations | M400 | 34 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
M600 | Milestone | Handover | M500 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 2 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 18 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 20 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 13 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 22 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 20 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 16 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 49 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 13 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 3 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 18 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 20 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 13 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 22 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 20 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 16 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 49 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 13 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 4 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 18 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 20 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 13 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 22 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 20 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 16 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 49 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 13 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1000 | Package | Launch campaign | A1900 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2000 | Package | Payload integration | P1000 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3000 | Package | Power and ECLSS | P2000 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4000 | Package | Surface logistics | P3000 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5000 | Package | Mission operations | P4000 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P6000 | Package | Robotic assembly | P5000 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Level 5 Schedule
Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
A1000 | Governance | Project initiation / controls setup |  | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1100 | Business Case | Strategic brief, funding and approval | A1000 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1200 | Scope | Requirements definition and scope freeze | A1100 | 11 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1300 | Design | Concept / reference architecture | A1200 | 18 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 20 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 13 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1600 | Design | Detailed design / IFC development | A1300 | 22 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1700 | Procurement | Long-lead procurement | A1500 | 20 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 16 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 49 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2000 | Integration | Systems integration and testing | A1900 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 13 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1000 | Package | Launch campaign | A1900 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1100 | Activity | Launch campaign - mobilise / method | A1900 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1200 | Activity | Launch campaign - execute works | P1100 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P1300 | Activity | Launch campaign - inspect / closeout | P1200 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2000 | Package | Payload integration | P1000 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2100 | Activity | Payload integration - mobilise / method | P1000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2200 | Activity | Payload integration - execute works | P2100 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P2300 | Activity | Payload integration - inspect / closeout | P2200 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3000 | Package | Power and ECLSS | P2000 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3100 | Activity | Power and ECLSS - mobilise / method | P2000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3200 | Activity | Power and ECLSS - execute works | P3100 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P3300 | Activity | Power and ECLSS - inspect / closeout | P3200 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4000 | Package | Surface logistics | P3000 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4100 | Activity | Surface logistics - mobilise / method | P3000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4200 | Activity | Surface logistics - execute works | P4100 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P4300 | Activity | Surface logistics - inspect / closeout | P4200 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5000 | Package | Mission operations | P4000 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5100 | Activity | Mission operations - mobilise / method | P4000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5200 | Activity | Mission operations - execute works | P5100 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P5300 | Activity | Mission operations - inspect / closeout | P5200 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P6000 | Package | Robotic assembly | P5000 | 8 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P6100 | Activity | Robotic assembly - mobilise / method | P5000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P6200 | Activity | Robotic assembly - execute works | P6100 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
P6300 | Activity | Robotic assembly - inspect / closeout | P6200 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## Risk Register
ID | Risk | Category | Probability | Activity | CBS | Sched O | Sched M | Sched P | Cost O | Cost M | Cost P | Owner | Trigger | Mitigation | Cost Basis | Schedule Basis
R-S02 | Mass growth | Technical | 42 | A1500 | 01.05 | 15 | 50 | 140 | 7.266 | 19.982 | 43.597 | Chief Engineer | Mass margin below threshold | Mass control board and margin policy | Cost impact derived from 01.05 ECLSS / Life Support exposure, project P50 $181.7B, and risk severity (4%/11%/24%). | Schedule impact mapped to A1500 Procurement strategy and tender packaging with O/M/P delay 15/50/140 days and critical path sensitivity.
R-002 | Market escalation | Commercial | 45 | A1800 | 01.08 | 0 | 0 | 0 | 7.266 | 18.166 | 36.331 | Commercial Lead | Index exceeds allowance | Early procurement, index strategy, market testing | Cost impact derived from 01.08 Launch Services exposure, project P50 $181.7B, and risk severity (4%/10%/20%). | Schedule impact mapped to A1800 Site / launch integration readiness with O/M/P delay 0/0/0 days and critical path sensitivity.
R-S03 | Life-support reliability | Technical | 36 | A1600 | 01.06 | 20 | 70 | 180 | 9.083 | 21.799 | 50.864 | Life Support Lead | Reliability growth misses target | Prototype testing, redundancy, reliability growth | Cost impact derived from 01.06 Payload / Mission Equipment exposure, project P50 $181.7B, and risk severity (5%/12%/28%). | Schedule impact mapped to A1600 Detailed design / IFC development with O/M/P delay 20/70/180 days and critical path sensitivity.
R-S01 | Launch manifest delay | Launch | 48 | A1400 | 01.04 | 15 | 45 | 120 | 5.45 | 16.349 | 36.331 | Launch Integration Lead | Launch slot not confirmed | Reserve alternate slots, freeze payload interfaces | Cost impact derived from 01.04 Power Generation & Distribution exposure, project P50 $181.7B, and risk severity (3%/9%/20%). | Schedule impact mapped to A1400 Planning, regulatory and stakeholder approvals with O/M/P delay 15/45/120 days and critical path sensitivity.
R-004 | Design maturity gap | Technical | 38 | A2000 | 02.01 | 15 | 45 | 120 | 5.45 | 16.349 | 32.698 | Design Manager | Deliverables late | Design maturity gates and independent review | Cost impact derived from 02.01 Test & Qualification Facilities exposure, project P50 $181.7B, and risk severity (3%/9%/18%). | Schedule impact mapped to A2000 Systems integration and testing with O/M/P delay 15/45/120 days and critical path sensitivity.
R-001 | Scope growth | Scope | 42 | A1700 | 01.07 | 15 | 45 | 120 | 5.45 | 14.532 | 29.065 | Project Director | Scope change rate exceeds threshold | Freeze scope, change board, value gates | Cost impact derived from 01.07 Robotics / Autonomous Construction exposure, project P50 $181.7B, and risk severity (3%/8%/16%). | Schedule impact mapped to A1700 Long-lead procurement with O/M/P delay 15/45/120 days and critical path sensitivity.
R-006 | Productivity underperformance | Delivery | 35 | P1000 | 02.03 | 15 | 50 | 130 | 5.45 | 14.532 | 29.065 | Delivery Lead | SPI/CPI deteriorates | Package productivity controls and daily planning | Cost impact derived from 02.03 Programme Management / PMO exposure, project P50 $181.7B, and risk severity (3%/8%/16%). | Schedule impact mapped to P1000 Launch campaign with O/M/P delay 15/50/130 days and critical path sensitivity.
R-005 | Supply chain delay | Procurement | 40 | A2100 | 02.02 | 10 | 40 | 120 | 3.633 | 12.716 | 27.248 | Procurement Lead | Supplier promise date slips | Alternate suppliers, early orders, expediting | Cost impact derived from 02.02 Safety & Mission Assurance exposure, project P50 $181.7B, and risk severity (2%/7%/15%). | Schedule impact mapped to A2100 Commissioning, operations readiness and closeout with O/M/P delay 10/40/120 days and critical path sensitivity.
R-008 | Interface misalignment | Integration | 34 | P3000 | 03.02 | 10 | 35 | 100 | 3.633 | 12.716 | 25.432 | Integration Manager | Interface actions overdue | ICDs and weekly interface board | Cost impact derived from 03.02 Management Reserve exposure, project P50 $181.7B, and risk severity (2%/7%/14%). | Schedule impact mapped to P3000 Power and ECLSS with O/M/P delay 10/35/100 days and critical path sensitivity.
R-007 | Commissioning delay | Handover | 32 | P2000 | 03.01 | 10 | 35 | 100 | 3.633 | 10.899 | 21.799 | Commissioning Lead | Test failures trend upward | Commissioning readiness and early test plans | Cost impact derived from 03.01 Risk Contingency / UFE exposure, project P50 $181.7B, and risk severity (2%/6%/12%). | Schedule impact mapped to P2000 Payload integration with O/M/P delay 10/35/100 days and critical path sensitivity.
R-003 | Permits / approvals delay | Regulatory | 35 | A1900 | 01.09 | 20 | 70 | 180 | 1.817 | 7.266 | 14.532 | Consents Lead | Consent milestone slips | Authority plan, consent tracker, early submissions | Cost impact derived from 01.09 Transport / Landing / Surface Logistics exposure, project P50 $181.7B, and risk severity (1%/4%/8%). | Schedule impact mapped to A1900 Main construction / fabrication / assembly with O/M/P delay 20/70/180 days and critical path sensitivity.

## Monte Carlo P-Curve
Percentile | QCRA Cost BN | QSRA Months
1 | 189.826 | 214.8
5 | 208.117 | 219.51
10 | 218.092 | 222.9
20 | 231.458 | 227.22
30 | 241.625 | 230.46
40 | 250.109 | 233.34
50 | 258.463 | 236.37
60 | 267.318 | 239.58
70 | 277.031 | 243.23
80 | 288.283 | 247.48
90 | 304.575 | 253.12
95 | 317.194 | 257.18
99 | 344.164 | 263.71

## Tornado Drivers
Risk | Title | Activity | CBS | Cost Mean BN | Schedule Mean Days | Driver Score
R-S03 | Life-support reliability | A1600 | 01.06 | 9.791 | 32.2 | 982.37
R-S02 | Mass growth | A1500 | 01.05 | 9.707 | 28.5 | 973.57
R-002 | Market escalation | A1800 | 01.08 | 9.356 | 0 | 935.62
R-S01 | Launch manifest delay | A1400 | 01.04 | 9.312 | 28.9 | 934.04
R-004 | Design maturity gap | A2000 | 02.01 | 6.927 | 22.9 | 695.01
R-001 | Scope growth | A1700 | 01.07 | 6.923 | 25.2 | 694.79
R-005 | Supply chain delay | A2100 | 02.02 | 5.853 | 22.6 | 587.55
R-006 | Productivity underperformance | P1000 | 02.03 | 5.718 | 22.6 | 574.01
R-008 | Interface misalignment | P3000 | 03.02 | 4.695 | 16.3 | 471.17
R-007 | Commissioning delay | P2000 | 03.01 | 3.953 | 15.8 | 396.89
R-003 | Permits / approvals delay | A1900 | 01.09 | 2.755 | 31.7 | 278.65

## Scenarios
Scenario | Cost | Schedule Months | Risk | Confidence | Why
Base | $181.7B | 224 | Extreme | 46 | Balanced reference case.
Faster | $201.6B | 184 | Extreme | 41 | Parallel design/procurement, acceleration, premium logistics and higher interface risk.
Cheaper | $159.9B | 242 | Extreme | 40 | Value engineering, tighter scope and procurement competition, with schedule/quality exposure.
Lower Risk | $198.0B | 246 | High | 65 | More surveys, assurance, stage gates, contingency and schedule buffers.
Premium | $208.9B | 233 | High | 68 | Best assurance, independent review, early procurement and high-confidence governance.
Investor | $178.0B | 224 | Very High | 55 | Investment-framing case with transparent risk and commercial challenge.
Survival | $141.7B | 269 | Extreme | 36 | Minimum viable scope, warning-heavy, high residual risk.

## Benchmarks
Metric | Value | Why
Launch/logistics premium | 2.5x-4.3x Earth analogue | Remote operations, mass constraints, launch windows and harsh environment.
Programme duration benchmark | 190-280 months | Qualification, launch integration and commissioning sequence.
Top benchmark gap | TRL / reliability maturity | Space confidence improves fastest through test evidence and heritage.

## Demo Script
Step
Open with: 'Give me any project on Earth or in Space.'
Type the project into CASEY and hit Generate Full Intelligence Pack.
Show the executive dashboard: cost, schedule, risk, confidence and top drivers.
Switch to Monte Carlo: show QCRA/QSRA P-curves and tornado drivers linked to activities.
Show scenarios: Faster, Cheaper, Lower Risk and Premium with why each changed.
Open Output Centre: Excel, Risk CSV, XER, Word, PDF, PPTX and ZIP are ready.
Close with: 'Traditional advisory takes weeks. CASEY gives the first board-grade view in seconds.'