## Slide 1
CASEY
Mission Control for Capital Projects
Airport Infrastructure has been classified as Airport / Aviation in Global / Not specified. CASEY estimates $11.5B P50 cost, $9.2B to $14.9B range, 85 month baseline, Medium risk and 59% confidence under the Faster scenario.

## Slide 2
CASEY
Board Decision Snapshot
Airport Infrastructure | Faster scenario
P50
$11.5B
P80 Cost
$17.9B
Schedule
85 months
QSRA P80
102.19 mo
Risk
Medium
Confidence
59%
Direct
$11.6B
Indirect
$2.0B
Reserve
$1.0B

## Slide 3
CASEY
Scenario Logic
What changed and why the outputs are not generic.
• Acceleration selected: schedule compression is funded through logistics premium, parallel procurement and higher delivery intensity.
• Controls consequence: QSRA risk should be watched closely because interface density and commissioning pressure rise.
• Board decision: approve acceleration only with package-level recovery plan and explicit acceleration cost allowance.

## Slide 4
CASEY
QCRA + QSRA Drivers
Separate cost and schedule risk; no mixed generic tornado.
QCRA COST TORNADO
Market escalation - $735M
Operational phasing disruption - $567M
Scope growth - $541M
Design maturity gap - $532M
Supply chain delay - $463M
Productivity underperformance - $453M
Baggage / security systems integration - $396M
QSRA SCHEDULE TORNADO
Operational phasing disruption - 50.9 days
Permits / approvals delay - 45.4 days
Scope growth - 37.0 days
Supply chain delay - 33.5 days
Productivity underperformance - 33.2 days
Design maturity gap - 32.4 days
Baggage / security systems integration - 30.8 days

## Slide 5
CASEY
Board Top Risks
Cause - Event - Impact - Mitigation.
R-002 Market escalation: P50 cost becomes understated; commercial approvals or procurement strategy may need reset
R-A01 Operational phasing disruption: Delay, night-work premiums, stakeholder disruption and ORAT pressure
R-001 Scope growth: Additional quantities, redesign, rework, procurement churn and board contingency drawdown
R-004 Design maturity gap: Cost growth, quantity movement, rework and schedule resequencing
R-006 Productivity underperformance: Extended duration, increased preliminaries and loss of float
R-005 Supply chain delay: Delayed installation, critical path movement and acceleration cost
R-A02 Baggage / security systems integration: Commissioning delay, passenger disruption and late operational readiness
R-008 Interface misalignment: Rework, claims, delay and fragmented accountability

## Slide 6
CASEY
Output Pack
Excel cost model, risk register workbook, XER schedule, DOCX/PDF board report, PPTX board deck and JSON audit model generated from one connected CASEY model.
✓ Selected class cost estimate only
✓ Direct / indirect / reserve cost split
✓ Risk register with cause, event, impact and mitigation
✓ Separate QCRA and QSRA curves/tornado
✓ Scenario-linked values for Base / Faster / Cheaper / Lower Risk / Premium
✓ Pricing and email conversion path