## Risk Dashboard
CASEY RISK REGISTER PRO
Cause - Event - Impact - Response - Quantified cost and schedule exposure.
Risks |  |  | Board Visible |  |  | QCRA P80
10 |  |  | 8 |  |  | $16.3B
QSRA P80 |  |  | Top Risk |  |  | Scenario
77.61 months |  |  | Grid connection delay |  |  | Base
Rank | Risk | Cost EMV BN | Schedule EMV Days | Owner | Response
1 | Grid connection delay | 0.669 | 46.8 | Utilities Lead | Secure grid agreement, temporary power strategy, early equipment orders
2 | Market escalation | 0.482 | 0 | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy
3 | Design maturity gap | 0.367 | 17.1 | Design Manager | Design maturity gates, independent review, assumption register
4 | Scope growth | 0.36 | 18.9 | Project Director | Freeze scope baseline, change board, value gates, client decision log
5 | Cooling system capacity | 0.309 | 16.2 | MEP Lead | Thermal modelling, supplier validation, early performance test
6 | Productivity underperformance | 0.3 | 17.5 | Delivery Lead | Package productivity controls, daily planning, earned value cadence
7 | Supply chain delay | 0.3 | 16 | Procurement Lead | Alternate suppliers, early orders, expediting, framework options
8 | Interface misalignment | 0.255 | 11.9 | Integration Manager | Interface control documents, weekly interface board, accountable owners
9 | Commissioning delay | 0.206 | 11.2 | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration
10 | Permits / approvals delay | 0.15 | 24.5 | Consents Lead | Authority plan, consent tracker, early submissions, stakeholder map

## Risk Register Pro
FULL RISK REGISTER PRO
Every risk has a cause, event, impact description, owner, response and quantification.
Risk ID | Category | Title | Cause | Risk Event | Impact Description | Probability % | Cost O BN | Cost M BN | Cost P BN | Cost EMV BN | Schedule O Days | Schedule M Days | Schedule P Days | Schedule EMV Days | Activity | CBS | Owner | Trigger | Mitigation | Response Strategy | Residual | Status | Board
R-D01 | Utilities | Grid connection delay | Utility agreement, substation scope or energisation pathway not secured | Power connection or energisation milestone slips | Critical path delay, temporary power cost, phased opening risk and revenue deferral | 52 | 0.429 | 1.287 | 2.788 | 0.669 | 25 | 90 | 240 | 46.8 | A1400 | 01.04 | Utilities Lead | Grid agreement unsigned at gate | Secure grid agreement, temporary power strategy, early equipment orders | Mitigate | Medium | Open | Yes
R-002 | Commercial | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | 45 | 0.429 | 1.072 | 2.144 | 0.482 | 0 | 0 | 0 | 0 | A1700 | 01.07 | Commercial Lead | Index exceeds allowance by 3% | Early procurement, index-linked allowances, market testing, FX strategy | Mitigate | Low | Open | Yes
R-004 | Technical | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | 38 | 0.322 | 0.965 | 1.93 | 0.367 | 15 | 45 | 120 | 17.1 | A1900 | 01.09 | Design Manager | Design deliverables miss maturity gate | Design maturity gates, independent review, assumption register | Reduce | Low | Open | Yes
R-001 | Scope | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | 42 | 0.322 | 0.858 | 1.715 | 0.36 | 15 | 45 | 120 | 18.9 | A1600 | 01.06 | Project Director | Scope change rate exceeds 2% of package value | Freeze scope baseline, change board, value gates, client decision log | Reduce | Low | Open | Yes
R-D02 | Technical | Cooling system capacity | Thermal basis, water availability or cooling vendor performance uncertain | Cooling design fails capacity, redundancy or commissioning test | Re-design, commissioning delay, lower IT load and resilience concern | 36 | 0.268 | 0.858 | 1.823 | 0.309 | 10 | 45 | 130 | 16.2 | A1500 | 01.05 | MEP Lead | Cooling performance test fails | Thermal modelling, supplier validation, early performance test | Reduce | Low | Open | Yes
R-006 | Delivery | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | 35 | 0.322 | 0.858 | 1.715 | 0.3 | 15 | 50 | 130 | 17.5 | A2100 | 01.11 | Delivery Lead | SPI/CPI deteriorates for two reporting periods | Package productivity controls, daily planning, earned value cadence | Mitigate | Low | Open | Yes
R-005 | Procurement | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | 40 | 0.214 | 0.751 | 1.608 | 0.3 | 10 | 40 | 120 | 16 | A2000 | 01.10 | Procurement Lead | Supplier promise date slips | Alternate suppliers, early orders, expediting, framework options | Transfer / Mitigate | Low | Open | Yes
R-008 | Integration | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | 34 | 0.214 | 0.751 | 1.501 | 0.255 | 10 | 35 | 100 | 11.9 | P2000 | 02.02 | Integration Manager | Interface actions overdue | Interface control documents, weekly interface board, accountable owners | Mitigate | Low | Open | No
R-007 | Handover | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | 32 | 0.214 | 0.643 | 1.287 | 0.206 | 10 | 35 | 100 | 11.2 | P1000 | 02.01 | Commissioning Lead | Test failures trend upward | Commissioning readiness plan, early test packs, digital systems integration | Reduce | Low | Open | No
R-003 | Regulatory | Permits / approvals delay | Authority process, stakeholder objections or incomplete submissions | Consent milestone slips beyond baseline | Critical path delay, extended preliminaries and potential redesign conditions | 35 | 0.107 | 0.429 | 0.858 | 0.15 | 20 | 70 | 180 | 24.5 | A1800 | 01.08 | Consents Lead | Consent milestone slips by 30 days | Authority plan, consent tracker, early submissions, stakeholder map | Mitigate | Low | Open | Yes

## Mitigation Tracker
MITIGATION TRACKER
Owner actions, triggers and residual risk conversion.
Risk ID | Risk | Owner | Mitigation Action | Trigger | Due Gate | Status | Residual | Board | Evidence Needed
R-D01 | Grid connection delay | Utilities Lead | Secure grid agreement, temporary power strategy, early equipment orders | Grid agreement unsigned at gate | Next gate | Open | Medium | Yes | Named evidence, date, owner and decision log
R-002 | Market escalation | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy | Index exceeds allowance by 3% | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log
R-004 | Design maturity gap | Design Manager | Design maturity gates, independent review, assumption register | Design deliverables miss maturity gate | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log
R-001 | Scope growth | Project Director | Freeze scope baseline, change board, value gates, client decision log | Scope change rate exceeds 2% of package value | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log
R-D02 | Cooling system capacity | MEP Lead | Thermal modelling, supplier validation, early performance test | Cooling performance test fails | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log
R-006 | Productivity underperformance | Delivery Lead | Package productivity controls, daily planning, earned value cadence | SPI/CPI deteriorates for two reporting periods | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log
R-005 | Supply chain delay | Procurement Lead | Alternate suppliers, early orders, expediting, framework options | Supplier promise date slips | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log
R-008 | Interface misalignment | Integration Manager | Interface control documents, weekly interface board, accountable owners | Interface actions overdue | Next gate | Open | Low | No | Named evidence, date, owner and decision log
R-007 | Commissioning delay | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration | Test failures trend upward | Next gate | Open | Low | No | Named evidence, date, owner and decision log
R-003 | Permits / approvals delay | Consents Lead | Authority plan, consent tracker, early submissions, stakeholder map | Consent milestone slips by 30 days | Next gate | Open | Low | Yes | Named evidence, date, owner and decision log

## Board Top 10
BOARD TOP 10 RISKS
The risks most likely to change the investment decision.
Rank | Risk | Cause | Event | Impact | Cost EMV BN | Schedule EMV Days | Board Ask
1 | Grid connection delay | Utility agreement, substation scope or energisation pathway not secured | Power connection or energisation milestone slips | Critical path delay, temporary power cost, phased opening risk and revenue deferral | 0.669 | 46.8 | Approve mitigation spend or request further evidence
2 | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | 0.482 | 0 | Approve mitigation spend or request further evidence
3 | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | 0.367 | 17.1 | Approve mitigation spend or request further evidence
4 | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | 0.36 | 18.9 | Approve mitigation spend or request further evidence
5 | Cooling system capacity | Thermal basis, water availability or cooling vendor performance uncertain | Cooling design fails capacity, redundancy or commissioning test | Re-design, commissioning delay, lower IT load and resilience concern | 0.309 | 16.2 | Approve mitigation spend or request further evidence
6 | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | 0.3 | 17.5 | Approve mitigation spend or request further evidence
7 | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | 0.3 | 16 | Approve mitigation spend or request further evidence
8 | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | 0.255 | 11.9 | Approve mitigation spend or request further evidence
9 | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | 0.206 | 11.2 | Approve mitigation spend or request further evidence
10 | Permits / approvals delay | Authority process, stakeholder objections or incomplete submissions | Consent milestone slips beyond baseline | Critical path delay, extended preliminaries and potential redesign conditions | 0.15 | 24.5 | Approve mitigation spend or request further evidence