# CASEY Executive Board Intelligence Pack

Space Base | Surface Habitat/Base | Lower Risk scenario | Generated 2026-05-04 21:33 UTC

Space Base has been classified as Surface Habitat/Base in Moon / Lunar Surface. CASEY estimates $198.0B P50 cost, $158.4B to $257.4B range, 246 month baseline, High risk and 65% confidence under the Lower Risk scenario.

# 1. Board Decision Snapshot

| Metric | Value | Interpretation | Board Action |
| --- | --- | --- | --- |
| P50 Cost | $198.0B | Most likely first-pass cost based on selected class and scenario. | Use as initial investment control point. |
| Cost Range | $158.4B - $257.4B | Class/maturity and QCRA uncertainty range. | Do not approve without range acknowledgement. |
| QCRA P80 | $273.9B | Risk-adjusted cost confidence level. | Set funding envelope and contingency rules. |
| Baseline / QSRA P80 | 246 months / 267.52 months | Schedule risk exposure and delivery confidence. | Require critical path validation. |
| Risk / Confidence | High / 65% | Early-stage confidence and data quality status. | Approve evidence-improvement plan. |
| Direct / Indirect / Reserve | $154.4B / $29.7B / $23.8B | Prevents reserves being hidden inside direct cost. | Challenge contractor and adviser basis. |

# 2. Executive Recommendation

Lower-risk selected: more assurance, surveys, float and contingency raise headline cost but improve confidence.

Controls consequence: stronger evidence should move risk from unknown unknowns into quantified known unknowns.

Board decision: approve with a confidence-improvement plan and gate evidence pack.

Run a risk workshop to validate probability and O/M/P impacts.

Confirm top five CBS cost drivers with benchmark or supplier evidence.

Validate the Level 3/4 schedule logic and critical path assumptions.

Prepare board decision paper with Base/Faster/Cheaper/Lower-Risk cases.

Create confidence improvement plan targeting design maturity, consents and procurement evidence.

# 3. Cost Estimate - Selected Class Only

| CBS | Description | Type | P10 | P50 | P90 | Basis |
| --- | --- | --- | --- | --- | --- | --- |
| 01.01 | DDT&E Engineering | Direct | $14.3B | $17.8B | $23.2B | DDT&E Engineering priced as 9.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 01.02 | Systems Engineering & Integration | Direct | $9.5B | $11.9B | $15.4B | Systems Engineering & Integration priced as 6.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 01.03 | Structures / Habitat Shell | Direct | $15.8B | $19.8B | $25.7B | Structures / Habitat Shell priced as 10.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 01.04 | Power Generation & Distribution | Direct | $12.7B | $15.8B | $20.6B | Power Generation & Distribution priced as 8.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 01.05 | ECLSS / Life Support | Direct | $14.3B | $17.8B | $23.2B | ECLSS / Life Support priced as 9.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 01.06 | Payload / Mission Equipment | Direct | $11.1B | $13.9B | $18.0B | Payload / Mission Equipment priced as 7.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 01.07 | Robotics / Autonomous Construction | Direct | $9.5B | $11.9B | $15.4B | Robotics / Autonomous Construction priced as 6.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 01.08 | Launch Services | Direct | $22.2B | $27.7B | $36.0B | Launch Services priced as 14.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 01.09 | Transport / Landing / Surface Logistics | Direct | $14.3B | $17.8B | $23.2B | Transport / Landing / Surface Logistics priced as 9.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 02.01 | Test & Qualification Facilities | Indirect | $7.9B | $9.9B | $12.9B | Test & Qualification Facilities priced as 5.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 02.02 | Safety & Mission Assurance | Indirect | $7.9B | $9.9B | $12.9B | Safety & Mission Assurance priced as 5.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 02.03 | Programme Management / PMO | Indirect | $7.9B | $9.9B | $12.9B | Programme Management / PMO priced as 5.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 03.01 | Risk Contingency / UFE | Reserve | $11.1B | $13.9B | $18.0B | Risk Contingency / UFE priced as 7.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |
| 03.02 | Management Reserve | Reserve | $7.9B | $9.9B | $12.9B | Management Reserve priced as 5.0% of P50 from sector template, location factor 2.90, scale factor 1.00, complexity factor 1.96. |

# 4. QCRA and QSRA

QCRA cost P10 / P50 / P80 / P90: $215.6B / $198.0B / $273.9B / $287.2B

QSRA schedule P10 / P50 / P80 / P90: 244.24 / 256.54 / 267.52 / 272.92 months

## 5. QCRA Tornado Drivers

Mass growth - 01.05 - mean exposure $7.4B

Life-support reliability - 01.06 - mean exposure $7.2B

Launch manifest delay - 01.04 - mean exposure $7.0B

Market escalation - 01.08 - mean exposure $5.5B

Scope growth - 01.07 - mean exposure $4.1B

Design maturity gap - 02.01 - mean exposure $4.0B

Supply chain delay - 02.02 - mean exposure $3.4B

Productivity underperformance - 02.03 - mean exposure $3.3B

## 6. QSRA Tornado Drivers

Launch manifest delay - A1400 - mean exposure 24.7 days

Life-support reliability - A1600 - mean exposure 23.1 days

Mass growth - A1500 - mean exposure 18.1 days

Permits / approvals delay - A1900 - mean exposure 17.7 days

Scope growth - A1700 - mean exposure 14.3 days

Design maturity gap - A2000 - mean exposure 12.6 days

Productivity underperformance - P1000 - mean exposure 12.5 days

Supply chain delay - A2100 - mean exposure 12.4 days

# 7. Risk Register - Board Top Risks

R-S01 Launch manifest delay

Cause: Launch provider capacity, weather windows, manifest priority or vehicle readiness. Event: Confirmed launch slot moves or payload misses manifest gate. Impact: Programme delay, storage cost, resequencing and mission-readiness risk. Mitigation: Reserve alternate launch slot, freeze payload interface, maintain launch-readiness checklist. Owner: Launch Integration Lead.

R-S03 Life-support reliability

Cause: ECLSS reliability, spares or redundancy evidence below target. Event: Life-support system fails reliability growth or integrated test. Impact: Crew safety exposure, launch delay, redesign and mission abort risk. Mitigation: Prototype testing, redundancy, reliability growth, independent assurance. Owner: Life Support Lead.

R-S02 Mass growth

Cause: Design creep, shielding, redundancy or late payload additions increase mass. Event: Payload mass exceeds launch and landing allowance. Impact: Launch cost, redesign, performance loss and mission safety exposure. Mitigation: Mass control board, margin policy, design-to-mass reviews. Owner: Chief Engineer.

R-002 Market escalation

Cause: Supplier market tightness, inflation, FX and long procurement window. Event: Rates exceed assumed escalation profile. Impact: P50 cost becomes understated; commercial approvals or procurement strategy may need reset. Mitigation: Early procurement, index-linked allowances, market testing, FX strategy. Owner: Commercial Lead.

R-004 Design maturity gap

Cause: Estimate is based on immature design, incomplete surveys or unresolved interfaces. Event: Design basis changes during detailed design. Impact: Cost growth, quantity movement, rework and schedule resequencing. Mitigation: Design maturity gates, independent review, assumption register. Owner: Design Manager.

R-001 Scope growth

Cause: Ambiguous requirements, immature scope freeze and late stakeholder changes. Event: Approved scope expands after estimate freeze. Impact: Additional quantities, redesign, rework, procurement churn and board contingency drawdown. Mitigation: Freeze scope baseline, change board, value gates, client decision log. Owner: Project Director.

R-006 Productivity underperformance

Cause: Access constraints, poor sequencing, labour scarcity or learning curve. Event: Actual production rates underperform plan. Impact: Extended duration, increased preliminaries and loss of float. Mitigation: Package productivity controls, daily planning, earned value cadence. Owner: Delivery Lead.

R-005 Supply chain delay

Cause: Long-lead equipment, constrained suppliers or late procurement release. Event: Supplier promise dates move right. Impact: Delayed installation, critical path movement and acceleration cost. Mitigation: Alternate suppliers, early orders, expediting, framework options. Owner: Procurement Lead.

R-008 Interface misalignment

Cause: Multiple contractors, unclear interface ownership or late design coordination. Event: Package interfaces do not align during installation/integration. Impact: Rework, claims, delay and fragmented accountability. Mitigation: Interface control documents, weekly interface board, accountable owners. Owner: Integration Manager.

R-007 Commissioning delay

Cause: Incomplete readiness, software integration issues or defects during testing. Event: Systems fail tests or require repeated commissioning cycles. Impact: Delayed handover, operational readiness slippage and liquidated damages exposure. Mitigation: Commissioning readiness plan, early test packs, digital systems integration. Owner: Commissioning Lead.

# 8. Challenge Questions

What evidence supports the P50 cost and P80 confidence?

Which five risks create most contingency?

Which activities drive the QSRA finish-date risk?

What data would increase confidence before approval?

What is the fastest credible lower-risk path?

What flight heritage, TRL and qualification evidence supports the space assumptions?

# 9. Assumptions and Limitations

This is a first-pass project controls intelligence pack. It is designed to challenge, accelerate and structure decision-making; it is not a final contractor tender or signed cost plan. Each output includes assumptions and should be validated against project-specific evidence before commitment.