## 00 Control Centre
CASEY v56 GLOBAL STANDARD OUTPUT PACK — AI Data Centre Campus
Scenario: Base ¦ Estimate Class: 3 ¦ Schedule Level: 5 ¦ Generated: 2026-05-05 18:08 UTC
P50 Cost |  | Cost Range | QCRA P80 | Schedule
$5.6B |  | $4.5B - $7.3B | $6.2B | 48 months
QSRA P80 |  | Risk | Confidence
50.4 months |  | Medium | 64%
Decision Engine
Use as control baseline; approve definition, not unconditional capital.
Balanced reference case for first-pass board challenge and option testing.
Output QA Lock
✓ | Excel generated with XlsxWriter to avoid workbook repair errors
✓ | No PPTX/PDF in primary pack
✓ | Scenario visible on every workbook control sheet
✓ | All class estimates included; selected class clearly identified
✓ | All schedule levels included; selected level clearly identified
✓ | Risk register contains no zero likelihood values
✓ | QCRA and QSRA curves/tornadoes separated

## 01 Scenario Comparison
SCENARIO COMPARISON — ALL OPTIONS
Selected scenario: Base. These values are scenario-linked and used to drive output interpretation.
Scenario | P50 Cost BN | Delta vs Selected | Schedule Months | Delta Months | Risk | Confidence | QCRA P80 BN | QSRA P80 Months | Commercial interpretation | Board decision
Base | 5.6 | 0 | 48 | 0 | Medium | 64 | 7.585 | 57.1 | Balanced reference case for first-pass board challenge and option testing. | Use as control baseline; approve definition, not unconditional capital.
Faster | 6.3 | 0.7 | 39 | -9 | Medium | 59 | 8.533 | 46.4 | Compresses delivery through parallel design, early procurement and acceleration premium. | Use only where time value exceeds cost and interface risk.
Cheaper | 5 | -0.6 | 52 | 4 | Medium | 58 | 6.772 | 61.8 | Reduces first cost through value engineering and tighter scope but transfers risk into delivery. | Use only if capex pressure dominates and residual risk is accepted.
Lower Risk | 6.2 | 0.6 | 53 | 5 | Low | 77 | 7.709 | 59.7 | Adds surveys, assurance, buffers and procurement validation to improve confidence. | Recommended where certainty matters more than lowest first cost.
Premium | 6.5 | 0.9 | 50 | 2 | Low | 80 | 8.082 | 56.3 | Strengthens suppliers, resilience, design maturity and governance for flagship delivery. | Use for mission-critical, reputational or flagship programmes.
Investor | 5.5 | -0.1 | 48 | 0 | Low | 71 | 6.838 | 54.1 | Frames the programme around capital discipline, risk transparency and investment committee challenge. | Use for sponsor, lender, partner or IC review.
Survival | 4.4 | -1.2 | 58 | 10 | Medium | 54 | 5.96 | 69 | Minimum viable scope and warning-heavy commercial stress case with high residual risk. | Use as a stress case only, not as the preferred baseline.

## 02 Cost Selected
SELECTED CLASS COST ESTIMATE — CLASS 3 — BASE SCENARIO
CBS | Description | Type | Basis | P10 BN | Most Likely / P50 BN | P80 BN | P90 BN | % of P50 | Challenge Question
01.01 | Site Preparation / Enabling | Direct | Demolition, enabling, logistics and access | 0.271 | 0.339 | 0.405 | 0.441 | 0.041718 | What evidence supports Site Preparation / Enabling at $339M?
01.02 | Substructure / Foundations | Direct | Piling, groundworks, retaining and foundations | 0.361 | 0.451 | 0.539 | 0.586 | 0.055501 | What evidence supports Substructure / Foundations at $451M?
01.03 | Superstructure / Civil Works | Direct | Frame, civils, primary structures | 0.632 | 0.79 | 0.944 | 1.027 | 0.097219 | What evidence supports Superstructure / Civil Works at $790M?
01.04 | MEP / Systems / Utilities | Direct | Mechanical, electrical, controls and utilities | 0.632 | 0.79 | 0.944 | 1.027 | 0.097219 | What evidence supports MEP / Systems / Utilities at $790M?
01.05 | Specialist Equipment / Fit-Out | Direct | Permanent equipment and specialist fit-out | 0.542 | 0.677 | 0.809 | 0.88 | 0.083313 | What evidence supports Specialist Equipment / Fit-Out at $677M?
01.06 | Data Halls / White Space | Direct | Server halls, fit-out and critical rooms | 0.587 | 0.734 | 0.877 | 0.954 | 0.090327 | What evidence supports Data Halls / White Space at $734M?
01.07 | Power Train / Substations | Direct | HV/MV gear, UPS, generators and substations | 0.722 | 0.903 | 1.079 | 1.174 | 0.11112 | What evidence supports Power Train / Substations at $903M?
01.08 | Cooling Systems | Direct | Chillers, heat rejection, CRAH/CRAC, water systems | 0.542 | 0.677 | 0.809 | 0.88 | 0.083313 | What evidence supports Cooling Systems at $677M?
01.09 | Direct Labour | Direct | Productivity, supervision and trade labour | 0.406 | 0.508 | 0.607 | 0.66 | 0.062515 | What evidence supports Direct Labour at $508M?
01.10 | Direct Materials | Direct | Concrete, steel, envelope, MEP materials | 0.451 | 0.564 | 0.674 | 0.733 | 0.069407 | What evidence supports Direct Materials at $564M?
01.11 | Plant / Equipment | Direct | Cranes, heavy plant and site equipment | 0.181 | 0.226 | 0.27 | 0.294 | 0.027812 | What evidence supports Plant / Equipment at $226M?
02.01 | General Conditions / Prelims | Indirect | Site management, safety, offices and temporary services | 0.316 | 0.395 | 0.472 | 0.514 | 0.048609 | What evidence supports General Conditions / Prelims at $395M?
02.02 | Design / Professional Fees | Indirect | Design, QS, controls, assurance and consultants | 0.316 | 0.395 | 0.472 | 0.514 | 0.048609 | What evidence supports Design / Professional Fees at $395M?
02.03 | Permits / Insurance / Bonds | Indirect | Permits, inspections, legal, bonds and insurance | 0.135 | 0.169 | 0.202 | 0.22 | 0.020797 | What evidence supports Permits / Insurance / Bonds at $169M?
03.01 | QCRA Contingency | Reserve | Known-unknown risk allowance | 0.271 | 0.339 | 0.405 | 0.441 | 0.041718 | What evidence supports QCRA Contingency at $339M?
03.02 | Management Reserve | Reserve | Sponsor-held reserve | 0.135 | 0.169 | 0.202 | 0.22 | 0.020797 | What evidence supports Management Reserve at $169M?

## 03 Cost All Classes
ALL ESTIMATE CLASS LEVELS — CLASS 1 TO 5
Class | Class Name | CBS | Description | Type | P10 BN | P50 BN | P90 BN | Maturity / Use
1 | Class 1 Definitive | 01.01 | Site Preparation / Enabling | Direct | 0.305 | 0.339 | 0.39 | Demolition, enabling, logistics and access
1 | Class 1 Definitive | 01.02 | Substructure / Foundations | Direct | 0.406 | 0.451 | 0.519 | Piling, groundworks, retaining and foundations
1 | Class 1 Definitive | 01.03 | Superstructure / Civil Works | Direct | 0.711 | 0.79 | 0.908 | Frame, civils, primary structures
1 | Class 1 Definitive | 01.04 | MEP / Systems / Utilities | Direct | 0.711 | 0.79 | 0.908 | Mechanical, electrical, controls and utilities
1 | Class 1 Definitive | 01.05 | Specialist Equipment / Fit-Out | Direct | 0.609 | 0.677 | 0.779 | Permanent equipment and specialist fit-out
1 | Class 1 Definitive | 01.06 | Data Halls / White Space | Direct | 0.661 | 0.734 | 0.844 | Server halls, fit-out and critical rooms
1 | Class 1 Definitive | 01.07 | Power Train / Substations | Direct | 0.813 | 0.903 | 1.038 | HV/MV gear, UPS, generators and substations
1 | Class 1 Definitive | 01.08 | Cooling Systems | Direct | 0.609 | 0.677 | 0.779 | Chillers, heat rejection, CRAH/CRAC, water systems
1 | Class 1 Definitive | 01.09 | Direct Labour | Direct | 0.457 | 0.508 | 0.584 | Productivity, supervision and trade labour
1 | Class 1 Definitive | 01.10 | Direct Materials | Direct | 0.508 | 0.564 | 0.649 | Concrete, steel, envelope, MEP materials
1 | Class 1 Definitive | 01.11 | Plant / Equipment | Direct | 0.203 | 0.226 | 0.26 | Cranes, heavy plant and site equipment
1 | Class 1 Definitive | 02.01 | General Conditions / Prelims | Indirect | 0.356 | 0.395 | 0.454 | Site management, safety, offices and temporary services
1 | Class 1 Definitive | 02.02 | Design / Professional Fees | Indirect | 0.356 | 0.395 | 0.454 | Design, QS, controls, assurance and consultants
1 | Class 1 Definitive | 02.03 | Permits / Insurance / Bonds | Indirect | 0.152 | 0.169 | 0.194 | Permits, inspections, legal, bonds and insurance
1 | Class 1 Definitive | 03.01 | QCRA Contingency | Reserve | 0.305 | 0.339 | 0.39 | Known-unknown risk allowance
1 | Class 1 Definitive | 03.02 | Management Reserve | Reserve | 0.152 | 0.169 | 0.194 | Sponsor-held reserve
2 | Class 2 Control | 01.01 | Site Preparation / Enabling | Direct | 0.288 | 0.339 | 0.407 | Demolition, enabling, logistics and access
2 | Class 2 Control | 01.02 | Substructure / Foundations | Direct | 0.383 | 0.451 | 0.541 | Piling, groundworks, retaining and foundations
2 | Class 2 Control | 01.03 | Superstructure / Civil Works | Direct | 0.671 | 0.79 | 0.948 | Frame, civils, primary structures
2 | Class 2 Control | 01.04 | MEP / Systems / Utilities | Direct | 0.671 | 0.79 | 0.948 | Mechanical, electrical, controls and utilities
2 | Class 2 Control | 01.05 | Specialist Equipment / Fit-Out | Direct | 0.575 | 0.677 | 0.812 | Permanent equipment and specialist fit-out
2 | Class 2 Control | 01.06 | Data Halls / White Space | Direct | 0.624 | 0.734 | 0.881 | Server halls, fit-out and critical rooms
2 | Class 2 Control | 01.07 | Power Train / Substations | Direct | 0.768 | 0.903 | 1.084 | HV/MV gear, UPS, generators and substations
2 | Class 2 Control | 01.08 | Cooling Systems | Direct | 0.575 | 0.677 | 0.812 | Chillers, heat rejection, CRAH/CRAC, water systems
2 | Class 2 Control | 01.09 | Direct Labour | Direct | 0.432 | 0.508 | 0.61 | Productivity, supervision and trade labour
2 | Class 2 Control | 01.10 | Direct Materials | Direct | 0.479 | 0.564 | 0.677 | Concrete, steel, envelope, MEP materials
2 | Class 2 Control | 01.11 | Plant / Equipment | Direct | 0.192 | 0.226 | 0.271 | Cranes, heavy plant and site equipment
2 | Class 2 Control | 02.01 | General Conditions / Prelims | Indirect | 0.336 | 0.395 | 0.474 | Site management, safety, offices and temporary services
2 | Class 2 Control | 02.02 | Design / Professional Fees | Indirect | 0.336 | 0.395 | 0.474 | Design, QS, controls, assurance and consultants
2 | Class 2 Control | 02.03 | Permits / Insurance / Bonds | Indirect | 0.144 | 0.169 | 0.203 | Permits, inspections, legal, bonds and insurance
2 | Class 2 Control | 03.01 | QCRA Contingency | Reserve | 0.288 | 0.339 | 0.407 | Known-unknown risk allowance
2 | Class 2 Control | 03.02 | Management Reserve | Reserve | 0.144 | 0.169 | 0.203 | Sponsor-held reserve
3 | Class 3 Budget | 01.01 | Site Preparation / Enabling | Direct | 0.271 | 0.339 | 0.441 | Demolition, enabling, logistics and access
3 | Class 3 Budget | 01.02 | Substructure / Foundations | Direct | 0.361 | 0.451 | 0.586 | Piling, groundworks, retaining and foundations
3 | Class 3 Budget | 01.03 | Superstructure / Civil Works | Direct | 0.632 | 0.79 | 1.027 | Frame, civils, primary structures
3 | Class 3 Budget | 01.04 | MEP / Systems / Utilities | Direct | 0.632 | 0.79 | 1.027 | Mechanical, electrical, controls and utilities
3 | Class 3 Budget | 01.05 | Specialist Equipment / Fit-Out | Direct | 0.542 | 0.677 | 0.88 | Permanent equipment and specialist fit-out
3 | Class 3 Budget | 01.06 | Data Halls / White Space | Direct | 0.587 | 0.734 | 0.954 | Server halls, fit-out and critical rooms
3 | Class 3 Budget | 01.07 | Power Train / Substations | Direct | 0.722 | 0.903 | 1.174 | HV/MV gear, UPS, generators and substations
3 | Class 3 Budget | 01.08 | Cooling Systems | Direct | 0.542 | 0.677 | 0.88 | Chillers, heat rejection, CRAH/CRAC, water systems
3 | Class 3 Budget | 01.09 | Direct Labour | Direct | 0.406 | 0.508 | 0.66 | Productivity, supervision and trade labour
3 | Class 3 Budget | 01.10 | Direct Materials | Direct | 0.451 | 0.564 | 0.733 | Concrete, steel, envelope, MEP materials
3 | Class 3 Budget | 01.11 | Plant / Equipment | Direct | 0.181 | 0.226 | 0.294 | Cranes, heavy plant and site equipment
3 | Class 3 Budget | 02.01 | General Conditions / Prelims | Indirect | 0.316 | 0.395 | 0.514 | Site management, safety, offices and temporary services
3 | Class 3 Budget | 02.02 | Design / Professional Fees | Indirect | 0.316 | 0.395 | 0.514 | Design, QS, controls, assurance and consultants
3 | Class 3 Budget | 02.03 | Permits / Insurance / Bonds | Indirect | 0.135 | 0.169 | 0.22 | Permits, inspections, legal, bonds and insurance
3 | Class 3 Budget | 03.01 | QCRA Contingency | Reserve | 0.271 | 0.339 | 0.441 | Known-unknown risk allowance
3 | Class 3 Budget | 03.02 | Management Reserve | Reserve | 0.135 | 0.169 | 0.22 | Sponsor-held reserve
4 | Class 4 Feasibility | 01.01 | Site Preparation / Enabling | Direct | 0.237 | 0.339 | 0.509 | Demolition, enabling, logistics and access
4 | Class 4 Feasibility | 01.02 | Substructure / Foundations | Direct | 0.316 | 0.451 | 0.676 | Piling, groundworks, retaining and foundations
4 | Class 4 Feasibility | 01.03 | Superstructure / Civil Works | Direct | 0.553 | 0.79 | 1.185 | Frame, civils, primary structures
4 | Class 4 Feasibility | 01.04 | MEP / Systems / Utilities | Direct | 0.553 | 0.79 | 1.185 | Mechanical, electrical, controls and utilities
4 | Class 4 Feasibility | 01.05 | Specialist Equipment / Fit-Out | Direct | 0.474 | 0.677 | 1.016 | Permanent equipment and specialist fit-out
4 | Class 4 Feasibility | 01.06 | Data Halls / White Space | Direct | 0.514 | 0.734 | 1.101 | Server halls, fit-out and critical rooms
4 | Class 4 Feasibility | 01.07 | Power Train / Substations | Direct | 0.632 | 0.903 | 1.355 | HV/MV gear, UPS, generators and substations
4 | Class 4 Feasibility | 01.08 | Cooling Systems | Direct | 0.474 | 0.677 | 1.016 | Chillers, heat rejection, CRAH/CRAC, water systems
4 | Class 4 Feasibility | 01.09 | Direct Labour | Direct | 0.356 | 0.508 | 0.762 | Productivity, supervision and trade labour
4 | Class 4 Feasibility | 01.10 | Direct Materials | Direct | 0.395 | 0.564 | 0.846 | Concrete, steel, envelope, MEP materials
4 | Class 4 Feasibility | 01.11 | Plant / Equipment | Direct | 0.158 | 0.226 | 0.339 | Cranes, heavy plant and site equipment
4 | Class 4 Feasibility | 02.01 | General Conditions / Prelims | Indirect | 0.276 | 0.395 | 0.593 | Site management, safety, offices and temporary services
4 | Class 4 Feasibility | 02.02 | Design / Professional Fees | Indirect | 0.276 | 0.395 | 0.593 | Design, QS, controls, assurance and consultants
4 | Class 4 Feasibility | 02.03 | Permits / Insurance / Bonds | Indirect | 0.118 | 0.169 | 0.254 | Permits, inspections, legal, bonds and insurance
4 | Class 4 Feasibility | 03.01 | QCRA Contingency | Reserve | 0.237 | 0.339 | 0.509 | Known-unknown risk allowance
4 | Class 4 Feasibility | 03.02 | Management Reserve | Reserve | 0.118 | 0.169 | 0.254 | Sponsor-held reserve
5 | Class 5 Concept | 01.01 | Site Preparation / Enabling | Direct | 0.17 | 0.339 | 0.678 | Demolition, enabling, logistics and access
5 | Class 5 Concept | 01.02 | Substructure / Foundations | Direct | 0.226 | 0.451 | 0.902 | Piling, groundworks, retaining and foundations
5 | Class 5 Concept | 01.03 | Superstructure / Civil Works | Direct | 0.395 | 0.79 | 1.58 | Frame, civils, primary structures
5 | Class 5 Concept | 01.04 | MEP / Systems / Utilities | Direct | 0.395 | 0.79 | 1.58 | Mechanical, electrical, controls and utilities
5 | Class 5 Concept | 01.05 | Specialist Equipment / Fit-Out | Direct | 0.339 | 0.677 | 1.354 | Permanent equipment and specialist fit-out
5 | Class 5 Concept | 01.06 | Data Halls / White Space | Direct | 0.367 | 0.734 | 1.468 | Server halls, fit-out and critical rooms
5 | Class 5 Concept | 01.07 | Power Train / Substations | Direct | 0.452 | 0.903 | 1.806 | HV/MV gear, UPS, generators and substations
5 | Class 5 Concept | 01.08 | Cooling Systems | Direct | 0.339 | 0.677 | 1.354 | Chillers, heat rejection, CRAH/CRAC, water systems
5 | Class 5 Concept | 01.09 | Direct Labour | Direct | 0.254 | 0.508 | 1.016 | Productivity, supervision and trade labour
5 | Class 5 Concept | 01.10 | Direct Materials | Direct | 0.282 | 0.564 | 1.128 | Concrete, steel, envelope, MEP materials
5 | Class 5 Concept | 01.11 | Plant / Equipment | Direct | 0.113 | 0.226 | 0.452 | Cranes, heavy plant and site equipment
5 | Class 5 Concept | 02.01 | General Conditions / Prelims | Indirect | 0.198 | 0.395 | 0.79 | Site management, safety, offices and temporary services
5 | Class 5 Concept | 02.02 | Design / Professional Fees | Indirect | 0.198 | 0.395 | 0.79 | Design, QS, controls, assurance and consultants
5 | Class 5 Concept | 02.03 | Permits / Insurance / Bonds | Indirect | 0.085 | 0.169 | 0.338 | Permits, inspections, legal, bonds and insurance
5 | Class 5 Concept | 03.01 | QCRA Contingency | Reserve | 0.17 | 0.339 | 0.678 | Known-unknown risk allowance
5 | Class 5 Concept | 03.02 | Management Reserve | Reserve | 0.085 | 0.169 | 0.338 | Sponsor-held reserve

## 04 Risk Register
FULL RISK REGISTER — CAUSE / EVENT / IMPACT / MITIGATION / QUANTIFIED
ID | Category | Risk | Cause | Event | Impact | Owner | Mitigation | Trigger | Probability % | Cost O BN | Cost ML BN | Cost P BN | Schedule O Days | Schedule ML Days | Schedule P Days | Cost EMV BN | Schedule EMV Days | Status
R-015 | Sector | Funding / approval gate delay | Investment approvals or staged funding gates not aligned with procurement | Capital release is delayed | Procurement missed windows and schedule slippage | Sponsor | Approval roadmap and early board papers | Approval date slips | 0.49 | 0.03 | 0.067 | 0.151 | 16.8 | 42 | 96.6 | 0.042 | 26.1 | Open
R-022 | Sector | Regulatory assurance delay | Regulator or authority review cycle not fully allowed | Approval takes longer than baseline | Critical path delay and extra assurance cost | Consents Lead | Regulatory roadmap and early engagement | Submission returned | 0.44 | 0.045 | 0.101 | 0.227 | 14.8 | 37 | 85.1 | 0.056 | 20.7 | Open
R-023 | Sector | Procurement strategy misalignment | Package strategy does not match market capacity or risk transfer | Tenders return above budget or fail | Retendering, cost growth and schedule slip | Commercial Lead | Market sounding and package strategy review | Low bidder response | 0.49 | 0.015 | 0.034 | 0.076 | 16.8 | 42 | 96.6 | 0.021 | 26.1 | Open
R-005 | Procurement | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | Procurement Lead | Alternate suppliers, early orders, expediting, framework options | Supplier promise date slips | 0.4 | 0.045 | 0.101 | 0.217 | 15.3 | 34 | 76.5 | 0.05 | 17.2 | Open
R-001 | Scope | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | Project Director | Freeze scope baseline, change board, value gates, client decision log | Scope change rate exceeds 2% of package value | 0.42 | 0.055 | 0.123 | 0.265 | 8.1 | 18 | 40.5 | 0.064 | 9.6 | Open
R-014 | Sector | Stakeholder change | Sponsor, operator or authority requirements evolve late | Requirements change after baseline freeze | Scope growth, redesign and approval delays | Project Director | Decision log, change board and stakeholder gates | Late decision count increases | 0.44 | 0.023 | 0.05 | 0.113 | 14.8 | 37 | 85.1 | 0.028 | 20.7 | Open
R-004 | Technical | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | Design Manager | Design maturity gates, independent review, assumption register | Design deliverables miss maturity gate | 0.38 | 0.066 | 0.146 | 0.313 | 9.9 | 22 | 49.5 | 0.068 | 10.6 | Open
R-D01 | Utilities | Grid connection delay | Utility agreement, substation scope or energisation pathway not secured | Power connection or energisation milestone slips | Critical path delay, temporary power cost, phased opening risk and revenue deferral | Utilities Lead | Secure grid agreement, temporary power strategy, early equipment orders | Grid agreement unsigned at gate | 0.52 | 0.035 | 0.078 | 0.169 | 4.5 | 10 | 22.5 | 0.05 | 6.6 | Open
R-002 | Commercial | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy | Index exceeds allowance by 3% | 0.45 | 0.045 | 0.101 | 0.217 | 6.3 | 14 | 31.5 | 0.056 | 8 | Open
R-008 | Integration | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | Integration Manager | Interface control documents, weekly interface board, accountable owners | Interface actions overdue | 0.34 | 0.055 | 0.123 | 0.265 | 17.1 | 38 | 85.5 | 0.052 | 16.3 | Open
R-021 | Sector | Utilities diversion / enabling risk | Unknown utilities, access or enabling works underestimated | Enabling works expand or delay critical start | Cost growth, access delay and resequencing | Enabling Works Lead | Surveys, trial pits and early utility agreements | Unknown utilities found | 0.39 | 0.038 | 0.084 | 0.189 | 12.8 | 32 | 73.6 | 0.041 | 15.8 | Open
R-012 | Sector | Cyber / controls integration | Operational technology and control systems interfaces immature | Controls integration fails testing | Commissioning delay, resilience issue and operational risk | Systems Lead | Early cyber review, FAT/SAT plan, integration lab | Controls defect trend increases | 0.34 | 0.045 | 0.101 | 0.227 | 10.8 | 27 | 62.1 | 0.043 | 11.7 | Open
R-006 | Delivery | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | Delivery Lead | Package productivity controls, daily planning, earned value cadence | SPI/CPI deteriorates for two reporting periods | 0.35 | 0.035 | 0.078 | 0.169 | 13.5 | 30 | 67.5 | 0.034 | 13.3 | Open
R-013 | Sector | Weather / environmental disruption | Extreme weather, environmental windows or site constraints not fully allowed | Workface access or productivity is disrupted | Delay, access cost and resequencing | Construction Manager | Weather calendars, contingency workfronts, protection strategy | Weather downtime exceeds allowance | 0.39 | 0.015 | 0.034 | 0.076 | 12.8 | 32 | 73.6 | 0.017 | 15.8 | Open
R-020 | Sector | Design change after procurement | Procurement released before design maturity is sufficient | Vendor packages require change | Variation cost, rework and programme delay | Design Manager | Design freeze gates and change impact board | IFC maturity below gate | 0.34 | 0.03 | 0.067 | 0.151 | 10.8 | 27 | 62.1 | 0.029 | 11.7 | Open
R-007 | Handover | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration | Test failures trend upward | 0.32 | 0.066 | 0.146 | 0.313 | 2.7 | 6 | 13.5 | 0.058 | 2.4 | Open
R-D02 | Technical | Cooling system capacity | Thermal basis, water availability or cooling vendor performance uncertain | Cooling design fails capacity, redundancy or commissioning test | Re-design, commissioning delay, lower IT load and resilience concern | MEP Lead | Thermal modelling, supplier validation, early performance test | Cooling performance test fails | 0.36 | 0.025 | 0.056 | 0.12 | 11.7 | 26 | 58.5 | 0.025 | 11.8 | Open
R-D04 | Sector | Generator / UPS lead time | Critical power equipment supply constrained | Power train delivery slips | Critical path movement and acceleration premium | Procurement Lead | Early vendor reservation and dual-source strategy | Vendor delivery warning | 0.29 | 0.045 | 0.101 | 0.227 | 8.8 | 22 | 50.6 | 0.037 | 8.1 | Open
R-011 | Sector | Quality failure / rework | Installation quality, vendor QA or inspection regime below need | Inspection failure triggers rework | Rework cost, schedule delay and confidence loss | Quality Manager | ITPs, hold points, vendor QA, right-first-time reviews | NCR trend increases | 0.29 | 0.038 | 0.084 | 0.189 | 8.8 | 22 | 50.6 | 0.031 | 8.1 | Open
R-003 | Regulatory | Permits / approvals delay | Authority process, stakeholder objections or incomplete submissions | Consent milestone slips beyond baseline | Critical path delay, extended preliminaries and potential redesign conditions | Consents Lead | Authority plan, consent tracker, early submissions, stakeholder map | Consent milestone slips by 30 days | 0.35 | 0.025 | 0.056 | 0.12 | 4.5 | 10 | 22.5 | 0.024 | 4.4 | Open
R-019 | Sector | Supply chain insolvency | Tier 2/3 financial health is unknown or weak | Critical supplier fails or cannot perform | Replacement cost, procurement delay and claims exposure | Procurement Lead | Financial checks, dual sourcing, step-in rights | Supplier credit alert | 0.29 | 0.023 | 0.05 | 0.113 | 8.8 | 22 | 50.6 | 0.018 | 8.1 | Open
R-D03 | Sector | Liquid cooling vendor maturity | Cooling technology or supplier capacity immature | Vendor solution underperforms acceptance tests | Capacity derate, redesign and delay | MEP Lead | Prototype, vendor qualification and performance guarantee | Cooling FAT failed | 0.24 | 0.038 | 0.084 | 0.189 | 6.8 | 17 | 39.1 | 0.026 | 5.2 | Open
R-010 | Sector | Resource availability | Labour, specialist supervisors or commissioning teams constrained | Required resources are unavailable when planned | Productivity loss, resequencing and higher preliminaries | Delivery Lead | Resource loading, framework call-offs and labour strategy | Resource histogram red flag | 0.24 | 0.03 | 0.067 | 0.151 | 6.8 | 17 | 39.1 | 0.02 | 5.2 | Open
R-017 | Sector | Data / estimate basis weakness | Estimate source data, quantities or benchmarks are incomplete | Baseline cannot be defended under challenge | Confidence reduction and rework of cost plan | Cost Lead | Assumption register, benchmark evidence, quantity validation | Unknown allowance exceeds threshold | 0.19 | 0.045 | 0.101 | 0.227 | 4.8 | 12 | 27.6 | 0.024 | 2.9 | Open
R-018 | Sector | Interface ownership gap | RACI and package boundaries are unclear across packages | Interface issue has no accountable owner | Delay, claims and fragmented accountability | Integration Manager | Interface control documents and owner matrix | Interface actions overdue | 0.24 | 0.015 | 0.034 | 0.076 | 6.8 | 17 | 39.1 | 0.01 | 5.2 | Open
R-025 | Sector | Benefits realisation risk | Commercial benefits rely on optimistic demand or ramp-up | Ramp-up underperforms plan | Revenue / value case weakens | Sponsor | Benefits model validation and ramp-up sensitivity | Demand evidence weak | 0.19 | 0.03 | 0.067 | 0.151 | 4.8 | 12 | 27.6 | 0.016 | 2.9 | Open
R-009 | Sector | Commercial claims escalation | Contract ambiguity, late changes and fragmented accountability | Claims submitted above allowance | Commercial pressure, management distraction and increased outturn cost | Commercial Lead | Tight change control and dispute avoidance board | Claim volume exceeds baseline | 0.19 | 0.023 | 0.05 | 0.113 | 4.8 | 12 | 27.6 | 0.012 | 2.9 | Open
R-016 | Sector | Commissioning readiness gap | Incomplete test packs, operational readiness or training gaps | Commissioning starts without readiness | Repeated tests, handover delay and operational risk | Commissioning Lead | Readiness dashboard, integrated test plan, ORAT | Readiness score below threshold | 0.14 | 0.038 | 0.084 | 0.189 | 2.8 | 7 | 16.1 | 0.015 | 1.2 | Open
R-024 | Sector | Operational readiness shortfall | Operating model, training or maintenance strategy immature | Asset cannot enter service as planned | Delayed opening and benefit deferral | Operations Lead | ORAT/readiness plan and service transition gate | Readiness gate failed | 0.14 | 0.023 | 0.05 | 0.113 | 2.8 | 7 | 16.1 | 0.009 | 1.2 | Open

## 05 QCRA QSRA Curves
QCRA + QSRA CURVES — SEPARATE DISTRIBUTIONS
Percentile | QCRA Cost BN | QSRA Months
1 | 4.266 | 42.03
5 | 4.619 | 43.69
10 | 4.823 | 44.62
20 | 5.077 | 45.75
30 | 5.27 | 46.6
40 | 5.439 | 47.32
50 | 5.6 | 48
60 | 5.766 | 48.69
70 | 5.951 | 49.45
80 | 6.177 | 50.36
85 | 6.323 | 50.93
90 | 6.503 | 51.64
95 | 6.79 | 52.74
99 | 7.351 | 54.82

## 06 Tornado Drivers
TORNADO DRIVERS — QCRA COST AND QSRA SCHEDULE SEPARATED
Rank | QCRA Cost Driver | ID | Cost EMV BN | Owner | Mitigation | Rank | QSRA Schedule Driver | ID | Schedule EMV Days | Owner | Mitigation
1 | Design maturity gap | R-004 | 0.068 | Design Manager | Design maturity gates, independent review, assumption register | 1 | Funding / approval gate delay | R-015 | 26.1 | Sponsor | Approval roadmap and early board papers
2 | Scope growth | R-001 | 0.064 | Project Director | Freeze scope baseline, change board, value gates, client decision log | 2 | Procurement strategy misalignment | R-023 | 26.1 | Commercial Lead | Market sounding and package strategy review
3 | Commissioning delay | R-007 | 0.058 | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration | 3 | Regulatory assurance delay | R-022 | 20.7 | Consents Lead | Regulatory roadmap and early engagement
4 | Regulatory assurance delay | R-022 | 0.056 | Consents Lead | Regulatory roadmap and early engagement | 4 | Stakeholder change | R-014 | 20.7 | Project Director | Decision log, change board and stakeholder gates
5 | Market escalation | R-002 | 0.056 | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy | 5 | Supply chain delay | R-005 | 17.2 | Procurement Lead | Alternate suppliers, early orders, expediting, framework options
6 | Interface misalignment | R-008 | 0.052 | Integration Manager | Interface control documents, weekly interface board, accountable owners | 6 | Interface misalignment | R-008 | 16.3 | Integration Manager | Interface control documents, weekly interface board, accountable owners
7 | Supply chain delay | R-005 | 0.05 | Procurement Lead | Alternate suppliers, early orders, expediting, framework options | 7 | Utilities diversion / enabling risk | R-021 | 15.8 | Enabling Works Lead | Surveys, trial pits and early utility agreements
8 | Grid connection delay | R-D01 | 0.05 | Utilities Lead | Secure grid agreement, temporary power strategy, early equipment orders | 8 | Weather / environmental disruption | R-013 | 15.8 | Construction Manager | Weather calendars, contingency workfronts, protection strategy
9 | Cyber / controls integration | R-012 | 0.043 | Systems Lead | Early cyber review, FAT/SAT plan, integration lab | 9 | Productivity underperformance | R-006 | 13.3 | Delivery Lead | Package productivity controls, daily planning, earned value cadence
10 | Funding / approval gate delay | R-015 | 0.042 | Sponsor | Approval roadmap and early board papers | 10 | Cooling system capacity | R-D02 | 11.8 | MEP Lead | Thermal modelling, supplier validation, early performance test
11 | Utilities diversion / enabling risk | R-021 | 0.041 | Enabling Works Lead | Surveys, trial pits and early utility agreements | 11 | Cyber / controls integration | R-012 | 11.7 | Systems Lead | Early cyber review, FAT/SAT plan, integration lab
12 | Generator / UPS lead time | R-D04 | 0.037 | Procurement Lead | Early vendor reservation and dual-source strategy | 12 | Design change after procurement | R-020 | 11.7 | Design Manager | Design freeze gates and change impact board
13 | Productivity underperformance | R-006 | 0.034 | Delivery Lead | Package productivity controls, daily planning, earned value cadence | 13 | Design maturity gap | R-004 | 10.6 | Design Manager | Design maturity gates, independent review, assumption register
14 | Quality failure / rework | R-011 | 0.031 | Quality Manager | ITPs, hold points, vendor QA, right-first-time reviews | 14 | Scope growth | R-001 | 9.6 | Project Director | Freeze scope baseline, change board, value gates, client decision log
15 | Design change after procurement | R-020 | 0.029 | Design Manager | Design freeze gates and change impact board | 15 | Generator / UPS lead time | R-D04 | 8.1 | Procurement Lead | Early vendor reservation and dual-source strategy

## 07 Schedule Levels
ALL SCHEDULE LEVELS — LEVEL 1 TO 5
Level | Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
1 | M100 | Milestone | Investment approval |  | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M200 | Milestone | Design complete | M100 | 10 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M300 | Milestone | Procurement complete | M200 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M400 | Milestone | Delivery complete | M300 | 19 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M500 | Milestone | Ready for operations | M400 | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M600 | Milestone | Handover | M500 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1000 | Governance | Project initiation / controls setup |  | 1 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1100 | Business Case | Strategic brief, funding and approval | A1000 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1200 | Scope | Requirements definition and scope freeze | A1100 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1300 | Design | Concept / reference architecture | A1200 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1600 | Design | Detailed design / IFC development | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1700 | Procurement | Long-lead procurement | A1500 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 11 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A2000 | Integration | Systems integration and testing | A1900 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1000 | Governance | Project initiation / controls setup |  | 1 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1100 | Business Case | Strategic brief, funding and approval | A1000 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1200 | Scope | Requirements definition and scope freeze | A1100 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1300 | Design | Concept / reference architecture | A1200 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1600 | Design | Detailed design / IFC development | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1700 | Procurement | Long-lead procurement | A1500 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 11 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A2000 | Integration | Systems integration and testing | A1900 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1000 | Governance | Project initiation / controls setup |  | 1 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1100 | Business Case | Strategic brief, funding and approval | A1000 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1200 | Scope | Requirements definition and scope freeze | A1100 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1300 | Design | Concept / reference architecture | A1200 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1600 | Design | Detailed design / IFC development | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1700 | Procurement | Long-lead procurement | A1500 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 11 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A2000 | Integration | Systems integration and testing | A1900 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P1000 | Package | Grid connection | A1900 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P2000 | Package | Data halls | P1000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P3000 | Package | Cooling plant | P2000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P4000 | Package | Power train | P3000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P5000 | Package | Controls and commissioning | P4000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1000 | Governance | Project initiation / controls setup |  | 1 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1100 | Business Case | Strategic brief, funding and approval | A1000 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1200 | Scope | Requirements definition and scope freeze | A1100 | 2 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1300 | Design | Concept / reference architecture | A1200 | 4 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1600 | Design | Detailed design / IFC development | A1300 | 5 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1700 | Procurement | Long-lead procurement | A1500 | 4 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 3 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 11 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A2000 | Integration | Systems integration and testing | A1900 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 3 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P1000 | Package | Grid connection | A1900 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P1100 | Activity | Grid connection - mobilise / method | A1900 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P1200 | Activity | Grid connection - execute works | P1100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P1300 | Activity | Grid connection - inspect / closeout | P1200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P2000 | Package | Data halls | P1000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P2100 | Activity | Data halls - mobilise / method | P1000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P2200 | Activity | Data halls - execute works | P2100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P2300 | Activity | Data halls - inspect / closeout | P2200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P3000 | Package | Cooling plant | P2000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P3100 | Activity | Cooling plant - mobilise / method | P2000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P3200 | Activity | Cooling plant - execute works | P3100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P3300 | Activity | Cooling plant - inspect / closeout | P3200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P4000 | Package | Power train | P3000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P4100 | Activity | Power train - mobilise / method | P3000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P4200 | Activity | Power train - execute works | P4100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P4300 | Activity | Power train - inspect / closeout | P4200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P5000 | Package | Controls and commissioning | P4000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P5100 | Activity | Controls and commissioning - mobilise / method | P4000 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P5200 | Activity | Controls and commissioning - execute works | P5100 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P5300 | Activity | Controls and commissioning - inspect / closeout | P5200 | 1 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## 08 Basis + Audit
BASIS, LIMITATIONS AND AUDIT
Field | Value
Scenario | Base
Project | AI Data Centre Campus
Subsector | Digital Infrastructure / Hyperscale Data Centre
Location | Saudi Arabia / GCC
Mode | Earth
Estimate class | 3
Schedule level | 5
Generated | 2026-05-05 18:08 UTC
Model version | v56 Global Standard
Limitation | First-pass project controls intelligence. Validate against project-specific tender, survey, design and schedule evidence before capital commitment.
Methodology | Cost is parametric/benchmark/factor-based; QCRA and QSRA are separated; risks are cause-event-impact structured; scenarios change cost, schedule, risk and confidence.
Output standard | PDF/PPTX excluded from primary output pack to avoid weak or unreadable exports. Excel, schedule and audit outputs are the source of truth.