## Risk Control Centre
CASEY v56 RISK CONTROL CENTRE — BASE SCENARIO
Top risks by combined cost/schedule exposure
ID | Risk | Likelihood | Cost EMV BN | Schedule EMV Days | Owner | Action
R-015 | Funding / approval gate delay | 0.49 | 0.042 | 26.1 | Sponsor | Approval roadmap and early board papers
R-022 | Regulatory assurance delay | 0.44 | 0.056 | 20.7 | Consents Lead | Regulatory roadmap and early engagement
R-023 | Procurement strategy misalignment | 0.49 | 0.021 | 26.1 | Commercial Lead | Market sounding and package strategy review
R-005 | Supply chain delay | 0.4 | 0.05 | 17.2 | Procurement Lead | Alternate suppliers, early orders, expediting, framework options
R-001 | Scope growth | 0.42 | 0.064 | 9.6 | Project Director | Freeze scope baseline, change board, value gates, client decision log
R-014 | Stakeholder change | 0.44 | 0.028 | 20.7 | Project Director | Decision log, change board and stakeholder gates
R-004 | Design maturity gap | 0.38 | 0.068 | 10.6 | Design Manager | Design maturity gates, independent review, assumption register
R-D01 | Grid connection delay | 0.52 | 0.05 | 6.6 | Utilities Lead | Secure grid agreement, temporary power strategy, early equipment orders
R-002 | Market escalation | 0.45 | 0.056 | 8 | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy
R-008 | Interface misalignment | 0.34 | 0.052 | 16.3 | Integration Manager | Interface control documents, weekly interface board, accountable owners

## Full Risk Register
FULL RISK REGISTER — NO ZERO LIKELIHOOD, FULL CAUSE / EVENT / IMPACT
ID | Category | Risk | Cause | Event | Impact | Owner | Mitigation | Trigger | Likelihood | Cost O BN | Cost ML BN | Cost P BN | Schedule O Days | Schedule ML Days | Schedule P Days | Cost EMV BN | Schedule EMV Days | Status
R-015 | Sector | Funding / approval gate delay | Investment approvals or staged funding gates not aligned with procurement | Capital release is delayed | Procurement missed windows and schedule slippage | Sponsor | Approval roadmap and early board papers | Approval date slips | 0.49 | 0.03 | 0.067 | 0.151 | 16.8 | 42 | 96.6 | 0.042 | 26.1 | Open
R-022 | Sector | Regulatory assurance delay | Regulator or authority review cycle not fully allowed | Approval takes longer than baseline | Critical path delay and extra assurance cost | Consents Lead | Regulatory roadmap and early engagement | Submission returned | 0.44 | 0.045 | 0.101 | 0.227 | 14.8 | 37 | 85.1 | 0.056 | 20.7 | Open
R-023 | Sector | Procurement strategy misalignment | Package strategy does not match market capacity or risk transfer | Tenders return above budget or fail | Retendering, cost growth and schedule slip | Commercial Lead | Market sounding and package strategy review | Low bidder response | 0.49 | 0.015 | 0.034 | 0.076 | 16.8 | 42 | 96.6 | 0.021 | 26.1 | Open
R-005 | Procurement | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | Procurement Lead | Alternate suppliers, early orders, expediting, framework options | Supplier promise date slips | 0.4 | 0.045 | 0.101 | 0.217 | 15.3 | 34 | 76.5 | 0.05 | 17.2 | Open
R-001 | Scope | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | Project Director | Freeze scope baseline, change board, value gates, client decision log | Scope change rate exceeds 2% of package value | 0.42 | 0.055 | 0.123 | 0.265 | 8.1 | 18 | 40.5 | 0.064 | 9.6 | Open
R-014 | Sector | Stakeholder change | Sponsor, operator or authority requirements evolve late | Requirements change after baseline freeze | Scope growth, redesign and approval delays | Project Director | Decision log, change board and stakeholder gates | Late decision count increases | 0.44 | 0.023 | 0.05 | 0.113 | 14.8 | 37 | 85.1 | 0.028 | 20.7 | Open
R-004 | Technical | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | Design Manager | Design maturity gates, independent review, assumption register | Design deliverables miss maturity gate | 0.38 | 0.066 | 0.146 | 0.313 | 9.9 | 22 | 49.5 | 0.068 | 10.6 | Open
R-D01 | Utilities | Grid connection delay | Utility agreement, substation scope or energisation pathway not secured | Power connection or energisation milestone slips | Critical path delay, temporary power cost, phased opening risk and revenue deferral | Utilities Lead | Secure grid agreement, temporary power strategy, early equipment orders | Grid agreement unsigned at gate | 0.52 | 0.035 | 0.078 | 0.169 | 4.5 | 10 | 22.5 | 0.05 | 6.6 | Open
R-002 | Commercial | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy | Index exceeds allowance by 3% | 0.45 | 0.045 | 0.101 | 0.217 | 6.3 | 14 | 31.5 | 0.056 | 8 | Open
R-008 | Integration | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | Integration Manager | Interface control documents, weekly interface board, accountable owners | Interface actions overdue | 0.34 | 0.055 | 0.123 | 0.265 | 17.1 | 38 | 85.5 | 0.052 | 16.3 | Open
R-021 | Sector | Utilities diversion / enabling risk | Unknown utilities, access or enabling works underestimated | Enabling works expand or delay critical start | Cost growth, access delay and resequencing | Enabling Works Lead | Surveys, trial pits and early utility agreements | Unknown utilities found | 0.39 | 0.038 | 0.084 | 0.189 | 12.8 | 32 | 73.6 | 0.041 | 15.8 | Open
R-012 | Sector | Cyber / controls integration | Operational technology and control systems interfaces immature | Controls integration fails testing | Commissioning delay, resilience issue and operational risk | Systems Lead | Early cyber review, FAT/SAT plan, integration lab | Controls defect trend increases | 0.34 | 0.045 | 0.101 | 0.227 | 10.8 | 27 | 62.1 | 0.043 | 11.7 | Open
R-006 | Delivery | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | Delivery Lead | Package productivity controls, daily planning, earned value cadence | SPI/CPI deteriorates for two reporting periods | 0.35 | 0.035 | 0.078 | 0.169 | 13.5 | 30 | 67.5 | 0.034 | 13.3 | Open
R-013 | Sector | Weather / environmental disruption | Extreme weather, environmental windows or site constraints not fully allowed | Workface access or productivity is disrupted | Delay, access cost and resequencing | Construction Manager | Weather calendars, contingency workfronts, protection strategy | Weather downtime exceeds allowance | 0.39 | 0.015 | 0.034 | 0.076 | 12.8 | 32 | 73.6 | 0.017 | 15.8 | Open
R-020 | Sector | Design change after procurement | Procurement released before design maturity is sufficient | Vendor packages require change | Variation cost, rework and programme delay | Design Manager | Design freeze gates and change impact board | IFC maturity below gate | 0.34 | 0.03 | 0.067 | 0.151 | 10.8 | 27 | 62.1 | 0.029 | 11.7 | Open
R-007 | Handover | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration | Test failures trend upward | 0.32 | 0.066 | 0.146 | 0.313 | 2.7 | 6 | 13.5 | 0.058 | 2.4 | Open
R-D02 | Technical | Cooling system capacity | Thermal basis, water availability or cooling vendor performance uncertain | Cooling design fails capacity, redundancy or commissioning test | Re-design, commissioning delay, lower IT load and resilience concern | MEP Lead | Thermal modelling, supplier validation, early performance test | Cooling performance test fails | 0.36 | 0.025 | 0.056 | 0.12 | 11.7 | 26 | 58.5 | 0.025 | 11.8 | Open
R-D04 | Sector | Generator / UPS lead time | Critical power equipment supply constrained | Power train delivery slips | Critical path movement and acceleration premium | Procurement Lead | Early vendor reservation and dual-source strategy | Vendor delivery warning | 0.29 | 0.045 | 0.101 | 0.227 | 8.8 | 22 | 50.6 | 0.037 | 8.1 | Open
R-011 | Sector | Quality failure / rework | Installation quality, vendor QA or inspection regime below need | Inspection failure triggers rework | Rework cost, schedule delay and confidence loss | Quality Manager | ITPs, hold points, vendor QA, right-first-time reviews | NCR trend increases | 0.29 | 0.038 | 0.084 | 0.189 | 8.8 | 22 | 50.6 | 0.031 | 8.1 | Open
R-003 | Regulatory | Permits / approvals delay | Authority process, stakeholder objections or incomplete submissions | Consent milestone slips beyond baseline | Critical path delay, extended preliminaries and potential redesign conditions | Consents Lead | Authority plan, consent tracker, early submissions, stakeholder map | Consent milestone slips by 30 days | 0.35 | 0.025 | 0.056 | 0.12 | 4.5 | 10 | 22.5 | 0.024 | 4.4 | Open
R-019 | Sector | Supply chain insolvency | Tier 2/3 financial health is unknown or weak | Critical supplier fails or cannot perform | Replacement cost, procurement delay and claims exposure | Procurement Lead | Financial checks, dual sourcing, step-in rights | Supplier credit alert | 0.29 | 0.023 | 0.05 | 0.113 | 8.8 | 22 | 50.6 | 0.018 | 8.1 | Open
R-D03 | Sector | Liquid cooling vendor maturity | Cooling technology or supplier capacity immature | Vendor solution underperforms acceptance tests | Capacity derate, redesign and delay | MEP Lead | Prototype, vendor qualification and performance guarantee | Cooling FAT failed | 0.24 | 0.038 | 0.084 | 0.189 | 6.8 | 17 | 39.1 | 0.026 | 5.2 | Open
R-010 | Sector | Resource availability | Labour, specialist supervisors or commissioning teams constrained | Required resources are unavailable when planned | Productivity loss, resequencing and higher preliminaries | Delivery Lead | Resource loading, framework call-offs and labour strategy | Resource histogram red flag | 0.24 | 0.03 | 0.067 | 0.151 | 6.8 | 17 | 39.1 | 0.02 | 5.2 | Open
R-017 | Sector | Data / estimate basis weakness | Estimate source data, quantities or benchmarks are incomplete | Baseline cannot be defended under challenge | Confidence reduction and rework of cost plan | Cost Lead | Assumption register, benchmark evidence, quantity validation | Unknown allowance exceeds threshold | 0.19 | 0.045 | 0.101 | 0.227 | 4.8 | 12 | 27.6 | 0.024 | 2.9 | Open
R-018 | Sector | Interface ownership gap | RACI and package boundaries are unclear across packages | Interface issue has no accountable owner | Delay, claims and fragmented accountability | Integration Manager | Interface control documents and owner matrix | Interface actions overdue | 0.24 | 0.015 | 0.034 | 0.076 | 6.8 | 17 | 39.1 | 0.01 | 5.2 | Open
R-025 | Sector | Benefits realisation risk | Commercial benefits rely on optimistic demand or ramp-up | Ramp-up underperforms plan | Revenue / value case weakens | Sponsor | Benefits model validation and ramp-up sensitivity | Demand evidence weak | 0.19 | 0.03 | 0.067 | 0.151 | 4.8 | 12 | 27.6 | 0.016 | 2.9 | Open
R-009 | Sector | Commercial claims escalation | Contract ambiguity, late changes and fragmented accountability | Claims submitted above allowance | Commercial pressure, management distraction and increased outturn cost | Commercial Lead | Tight change control and dispute avoidance board | Claim volume exceeds baseline | 0.19 | 0.023 | 0.05 | 0.113 | 4.8 | 12 | 27.6 | 0.012 | 2.9 | Open
R-016 | Sector | Commissioning readiness gap | Incomplete test packs, operational readiness or training gaps | Commissioning starts without readiness | Repeated tests, handover delay and operational risk | Commissioning Lead | Readiness dashboard, integrated test plan, ORAT | Readiness score below threshold | 0.14 | 0.038 | 0.084 | 0.189 | 2.8 | 7 | 16.1 | 0.015 | 1.2 | Open
R-024 | Sector | Operational readiness shortfall | Operating model, training or maintenance strategy immature | Asset cannot enter service as planned | Delayed opening and benefit deferral | Operations Lead | ORAT/readiness plan and service transition gate | Readiness gate failed | 0.14 | 0.023 | 0.05 | 0.113 | 2.8 | 7 | 16.1 | 0.009 | 1.2 | Open

## QCRA Tornado
QCRA COST TORNADO
Rank | Driver | Risk ID | Cost EMV BN | Owner | Action
1 | Design maturity gap | R-004 | 0.068 | Design Manager | Design maturity gates, independent review, assumption register
2 | Scope growth | R-001 | 0.064 | Project Director | Freeze scope baseline, change board, value gates, client decision log
3 | Commissioning delay | R-007 | 0.058 | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration
4 | Regulatory assurance delay | R-022 | 0.056 | Consents Lead | Regulatory roadmap and early engagement
5 | Market escalation | R-002 | 0.056 | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy
6 | Interface misalignment | R-008 | 0.052 | Integration Manager | Interface control documents, weekly interface board, accountable owners
7 | Supply chain delay | R-005 | 0.05 | Procurement Lead | Alternate suppliers, early orders, expediting, framework options
8 | Grid connection delay | R-D01 | 0.05 | Utilities Lead | Secure grid agreement, temporary power strategy, early equipment orders
9 | Cyber / controls integration | R-012 | 0.043 | Systems Lead | Early cyber review, FAT/SAT plan, integration lab
10 | Funding / approval gate delay | R-015 | 0.042 | Sponsor | Approval roadmap and early board papers
11 | Utilities diversion / enabling risk | R-021 | 0.041 | Enabling Works Lead | Surveys, trial pits and early utility agreements
12 | Generator / UPS lead time | R-D04 | 0.037 | Procurement Lead | Early vendor reservation and dual-source strategy
13 | Productivity underperformance | R-006 | 0.034 | Delivery Lead | Package productivity controls, daily planning, earned value cadence
14 | Quality failure / rework | R-011 | 0.031 | Quality Manager | ITPs, hold points, vendor QA, right-first-time reviews
15 | Design change after procurement | R-020 | 0.029 | Design Manager | Design freeze gates and change impact board

## QSRA Tornado
QSRA SCHEDULE TORNADO
Rank | Driver | Risk ID | Schedule EMV Days | Owner | Action
1 | Funding / approval gate delay | R-015 | 26.1 | Sponsor | Approval roadmap and early board papers
2 | Procurement strategy misalignment | R-023 | 26.1 | Commercial Lead | Market sounding and package strategy review
3 | Regulatory assurance delay | R-022 | 20.7 | Consents Lead | Regulatory roadmap and early engagement
4 | Stakeholder change | R-014 | 20.7 | Project Director | Decision log, change board and stakeholder gates
5 | Supply chain delay | R-005 | 17.2 | Procurement Lead | Alternate suppliers, early orders, expediting, framework options
6 | Interface misalignment | R-008 | 16.3 | Integration Manager | Interface control documents, weekly interface board, accountable owners
7 | Utilities diversion / enabling risk | R-021 | 15.8 | Enabling Works Lead | Surveys, trial pits and early utility agreements
8 | Weather / environmental disruption | R-013 | 15.8 | Construction Manager | Weather calendars, contingency workfronts, protection strategy
9 | Productivity underperformance | R-006 | 13.3 | Delivery Lead | Package productivity controls, daily planning, earned value cadence
10 | Cooling system capacity | R-D02 | 11.8 | MEP Lead | Thermal modelling, supplier validation, early performance test
11 | Cyber / controls integration | R-012 | 11.7 | Systems Lead | Early cyber review, FAT/SAT plan, integration lab
12 | Design change after procurement | R-020 | 11.7 | Design Manager | Design freeze gates and change impact board
13 | Design maturity gap | R-004 | 10.6 | Design Manager | Design maturity gates, independent review, assumption register
14 | Scope growth | R-001 | 9.6 | Project Director | Freeze scope baseline, change board, value gates, client decision log
15 | Generator / UPS lead time | R-D04 | 8.1 | Procurement Lead | Early vendor reservation and dual-source strategy