## 00 Control Centre
CASEY v56 GLOBAL STANDARD OUTPUT PACK — Space Base
Scenario: Lower Risk ¦ Estimate Class: 3 ¦ Schedule Level: 5 ¦ Generated: 2026-05-05 18:08 UTC
P50 Cost |  | Cost Range | QCRA P80 | Schedule
$198.0B |  | $158.4B - $257.4B | $225.0B | 249 months
QSRA P80 |  | Risk | Confidence
265.4 months |  | High | 65%
Decision Engine
Recommended where certainty matters more than lowest first cost.
Adds surveys, assurance, buffers and procurement validation to improve confidence.
Output QA Lock
✓ | Excel generated with XlsxWriter to avoid workbook repair errors
✓ | No PPTX/PDF in primary pack
✓ | Scenario visible on every workbook control sheet
✓ | All class estimates included; selected class clearly identified
✓ | All schedule levels included; selected level clearly identified
✓ | Risk register contains no zero likelihood values
✓ | QCRA and QSRA curves/tornadoes separated

## 01 Scenario Comparison
SCENARIO COMPARISON — ALL OPTIONS
Selected scenario: Lower Risk. These values are scenario-linked and used to drive output interpretation.
Scenario | P50 Cost BN | Delta vs Selected | Schedule Months | Delta Months | Risk | Confidence | QCRA P80 BN | QSRA P80 Months | Commercial interpretation | Board decision
Base | 181.7 | -16.3 | 226 | -23 | Extreme | 46 | 306.669 | 311.2 | Balanced reference case for first-pass board challenge and option testing. | Use as control baseline; approve definition, not unconditional capital.
Faster | 201.6 | 3.6 | 185 | -64 | Extreme | 41 | 340.256 | 254.7 | Compresses delivery through parallel design, early procurement and acceleration premium. | Use only where time value exceeds cost and interface risk.
Cheaper | 159.9 | -38.1 | 244 | -5 | Extreme | 40 | 269.876 | 336 | Reduces first cost through value engineering and tighter scope but transfers risk into delivery. | Use only if capex pressure dominates and residual risk is accepted.
Lower Risk | 198 | 0 | 249 | 0 | High | 65 | 301.18 | 319.5 | Adds surveys, assurance, buffers and procurement validation to improve confidence. | Recommended where certainty matters more than lowest first cost.
Premium | 208.9 | 10.9 | 235 | -14 | High | 68 | 317.76 | 301.5 | Strengthens suppliers, resilience, design maturity and governance for flagship delivery. | Use for mission-critical, reputational or flagship programmes.
Investor | 178 | -20 | 226 | -23 | Very High | 55 | 287.569 | 302 | Frames the programme around capital discipline, risk transparency and investment committee challenge. | Use for sponsor, lender, partner or IC review.
Survival | 141.7 | -56.3 | 271 | 22 | Extreme | 36 | 239.158 | 373.1 | Minimum viable scope and warning-heavy commercial stress case with high residual risk. | Use as a stress case only, not as the preferred baseline.

## 02 Cost Selected
SELECTED CLASS COST ESTIMATE — CLASS 3 — LOWER RISK SCENARIO
CBS | Description | Type | Basis | P10 BN | Most Likely / P50 BN | P80 BN | P90 BN | % of P50 | Challenge Question
01.01 | DDT&E Engineering | Direct | Engineering design, mission architecture and qualification | 14.256 | 17.82 | 21.295 | 23.166 | 0.085713 | What evidence supports DDT&E Engineering at $17.8B?
01.02 | Systems Engineering & Integration | Direct | Requirements, ICDs, verification and validation | 9.504 | 11.88 | 14.197 | 15.444 | 0.057142 | What evidence supports Systems Engineering & Integration at $11.9B?
01.03 | Structures / Habitat Shell | Direct | Pressure vessels, shielding and primary structures | 15.841 | 19.801 | 23.662 | 25.741 | 0.095242 | What evidence supports Structures / Habitat Shell at $19.8B?
01.04 | Power Generation & Distribution | Direct | Solar/nuclear source, grid and controls | 12.672 | 15.84 | 18.929 | 20.592 | 0.07619 | What evidence supports Power Generation & Distribution at $15.8B?
01.05 | ECLSS / Life Support | Direct | Air, water, waste, atmosphere and safety systems | 14.256 | 17.82 | 21.295 | 23.166 | 0.085713 | What evidence supports ECLSS / Life Support at $17.8B?
01.06 | Payload / Mission Equipment | Direct | Scientific, medical, industrial or settlement payload | 11.088 | 13.86 | 16.563 | 18.018 | 0.066666 | What evidence supports Payload / Mission Equipment at $13.9B?
01.07 | Robotics / Autonomous Construction | Direct | Robotic construction, inspection and maintenance | 9.504 | 11.88 | 14.197 | 15.444 | 0.057142 | What evidence supports Robotics / Autonomous Construction at $11.9B?
01.08 | Launch Services | Direct | Launch vehicle, manifest, payload processing | 22.177 | 27.721 | 33.127 | 36.037 | 0.13334 | What evidence supports Launch Services at $27.7B?
01.09 | Transport / Landing / Surface Logistics | Direct | Transit, landing, mobility and logistics chain | 14.256 | 17.82 | 21.295 | 23.166 | 0.085713 | What evidence supports Transport / Landing / Surface Logistics at $17.8B?
02.01 | Test & Qualification Facilities | Indirect | Thermal-vac, vibration, radiation and integrated testing | 7.92 | 9.9 | 11.831 | 12.87 | 0.047619 | What evidence supports Test & Qualification Facilities at $9.9B?
02.02 | Safety & Mission Assurance | Indirect | Quality, safety, independent review and compliance | 7.92 | 9.9 | 11.831 | 12.87 | 0.047619 | What evidence supports Safety & Mission Assurance at $9.9B?
02.03 | Programme Management / PMO | Indirect | Controls, reporting, commercial and integration PMO | 7.92 | 9.9 | 11.831 | 12.87 | 0.047619 | What evidence supports Programme Management / PMO at $9.9B?
03.01 | Risk Contingency / UFE | Reserve | Known-unknown risk allowance linked to QCRA/QSRA | 11.088 | 13.86 | 16.563 | 18.018 | 0.066666 | What evidence supports Risk Contingency / UFE at $13.9B?
03.02 | Management Reserve | Reserve | Sponsor-held unknown-unknown reserve | 7.92 | 9.9 | 11.831 | 12.87 | 0.047619 | What evidence supports Management Reserve at $9.9B?

## 03 Cost All Classes
ALL ESTIMATE CLASS LEVELS — CLASS 1 TO 5
Class | Class Name | CBS | Description | Type | P10 BN | P50 BN | P90 BN | Maturity / Use
1 | Class 1 Definitive | 01.01 | DDT&E Engineering | Direct | 16.038 | 17.82 | 20.493 | Engineering design, mission architecture and qualification
1 | Class 1 Definitive | 01.02 | Systems Engineering & Integration | Direct | 10.692 | 11.88 | 13.662 | Requirements, ICDs, verification and validation
1 | Class 1 Definitive | 01.03 | Structures / Habitat Shell | Direct | 17.821 | 19.801 | 22.771 | Pressure vessels, shielding and primary structures
1 | Class 1 Definitive | 01.04 | Power Generation & Distribution | Direct | 14.256 | 15.84 | 18.216 | Solar/nuclear source, grid and controls
1 | Class 1 Definitive | 01.05 | ECLSS / Life Support | Direct | 16.038 | 17.82 | 20.493 | Air, water, waste, atmosphere and safety systems
1 | Class 1 Definitive | 01.06 | Payload / Mission Equipment | Direct | 12.474 | 13.86 | 15.939 | Scientific, medical, industrial or settlement payload
1 | Class 1 Definitive | 01.07 | Robotics / Autonomous Construction | Direct | 10.692 | 11.88 | 13.662 | Robotic construction, inspection and maintenance
1 | Class 1 Definitive | 01.08 | Launch Services | Direct | 24.949 | 27.721 | 31.879 | Launch vehicle, manifest, payload processing
1 | Class 1 Definitive | 01.09 | Transport / Landing / Surface Logistics | Direct | 16.038 | 17.82 | 20.493 | Transit, landing, mobility and logistics chain
1 | Class 1 Definitive | 02.01 | Test & Qualification Facilities | Indirect | 8.91 | 9.9 | 11.385 | Thermal-vac, vibration, radiation and integrated testing
1 | Class 1 Definitive | 02.02 | Safety & Mission Assurance | Indirect | 8.91 | 9.9 | 11.385 | Quality, safety, independent review and compliance
1 | Class 1 Definitive | 02.03 | Programme Management / PMO | Indirect | 8.91 | 9.9 | 11.385 | Controls, reporting, commercial and integration PMO
1 | Class 1 Definitive | 03.01 | Risk Contingency / UFE | Reserve | 12.474 | 13.86 | 15.939 | Known-unknown risk allowance linked to QCRA/QSRA
1 | Class 1 Definitive | 03.02 | Management Reserve | Reserve | 8.91 | 9.9 | 11.385 | Sponsor-held unknown-unknown reserve
2 | Class 2 Control | 01.01 | DDT&E Engineering | Direct | 15.147 | 17.82 | 21.384 | Engineering design, mission architecture and qualification
2 | Class 2 Control | 01.02 | Systems Engineering & Integration | Direct | 10.098 | 11.88 | 14.256 | Requirements, ICDs, verification and validation
2 | Class 2 Control | 01.03 | Structures / Habitat Shell | Direct | 16.831 | 19.801 | 23.761 | Pressure vessels, shielding and primary structures
2 | Class 2 Control | 01.04 | Power Generation & Distribution | Direct | 13.464 | 15.84 | 19.008 | Solar/nuclear source, grid and controls
2 | Class 2 Control | 01.05 | ECLSS / Life Support | Direct | 15.147 | 17.82 | 21.384 | Air, water, waste, atmosphere and safety systems
2 | Class 2 Control | 01.06 | Payload / Mission Equipment | Direct | 11.781 | 13.86 | 16.632 | Scientific, medical, industrial or settlement payload
2 | Class 2 Control | 01.07 | Robotics / Autonomous Construction | Direct | 10.098 | 11.88 | 14.256 | Robotic construction, inspection and maintenance
2 | Class 2 Control | 01.08 | Launch Services | Direct | 23.563 | 27.721 | 33.265 | Launch vehicle, manifest, payload processing
2 | Class 2 Control | 01.09 | Transport / Landing / Surface Logistics | Direct | 15.147 | 17.82 | 21.384 | Transit, landing, mobility and logistics chain
2 | Class 2 Control | 02.01 | Test & Qualification Facilities | Indirect | 8.415 | 9.9 | 11.88 | Thermal-vac, vibration, radiation and integrated testing
2 | Class 2 Control | 02.02 | Safety & Mission Assurance | Indirect | 8.415 | 9.9 | 11.88 | Quality, safety, independent review and compliance
2 | Class 2 Control | 02.03 | Programme Management / PMO | Indirect | 8.415 | 9.9 | 11.88 | Controls, reporting, commercial and integration PMO
2 | Class 2 Control | 03.01 | Risk Contingency / UFE | Reserve | 11.781 | 13.86 | 16.632 | Known-unknown risk allowance linked to QCRA/QSRA
2 | Class 2 Control | 03.02 | Management Reserve | Reserve | 8.415 | 9.9 | 11.88 | Sponsor-held unknown-unknown reserve
3 | Class 3 Budget | 01.01 | DDT&E Engineering | Direct | 14.256 | 17.82 | 23.166 | Engineering design, mission architecture and qualification
3 | Class 3 Budget | 01.02 | Systems Engineering & Integration | Direct | 9.504 | 11.88 | 15.444 | Requirements, ICDs, verification and validation
3 | Class 3 Budget | 01.03 | Structures / Habitat Shell | Direct | 15.841 | 19.801 | 25.741 | Pressure vessels, shielding and primary structures
3 | Class 3 Budget | 01.04 | Power Generation & Distribution | Direct | 12.672 | 15.84 | 20.592 | Solar/nuclear source, grid and controls
3 | Class 3 Budget | 01.05 | ECLSS / Life Support | Direct | 14.256 | 17.82 | 23.166 | Air, water, waste, atmosphere and safety systems
3 | Class 3 Budget | 01.06 | Payload / Mission Equipment | Direct | 11.088 | 13.86 | 18.018 | Scientific, medical, industrial or settlement payload
3 | Class 3 Budget | 01.07 | Robotics / Autonomous Construction | Direct | 9.504 | 11.88 | 15.444 | Robotic construction, inspection and maintenance
3 | Class 3 Budget | 01.08 | Launch Services | Direct | 22.177 | 27.721 | 36.037 | Launch vehicle, manifest, payload processing
3 | Class 3 Budget | 01.09 | Transport / Landing / Surface Logistics | Direct | 14.256 | 17.82 | 23.166 | Transit, landing, mobility and logistics chain
3 | Class 3 Budget | 02.01 | Test & Qualification Facilities | Indirect | 7.92 | 9.9 | 12.87 | Thermal-vac, vibration, radiation and integrated testing
3 | Class 3 Budget | 02.02 | Safety & Mission Assurance | Indirect | 7.92 | 9.9 | 12.87 | Quality, safety, independent review and compliance
3 | Class 3 Budget | 02.03 | Programme Management / PMO | Indirect | 7.92 | 9.9 | 12.87 | Controls, reporting, commercial and integration PMO
3 | Class 3 Budget | 03.01 | Risk Contingency / UFE | Reserve | 11.088 | 13.86 | 18.018 | Known-unknown risk allowance linked to QCRA/QSRA
3 | Class 3 Budget | 03.02 | Management Reserve | Reserve | 7.92 | 9.9 | 12.87 | Sponsor-held unknown-unknown reserve
4 | Class 4 Feasibility | 01.01 | DDT&E Engineering | Direct | 12.474 | 17.82 | 26.73 | Engineering design, mission architecture and qualification
4 | Class 4 Feasibility | 01.02 | Systems Engineering & Integration | Direct | 8.316 | 11.88 | 17.82 | Requirements, ICDs, verification and validation
4 | Class 4 Feasibility | 01.03 | Structures / Habitat Shell | Direct | 13.861 | 19.801 | 29.701 | Pressure vessels, shielding and primary structures
4 | Class 4 Feasibility | 01.04 | Power Generation & Distribution | Direct | 11.088 | 15.84 | 23.76 | Solar/nuclear source, grid and controls
4 | Class 4 Feasibility | 01.05 | ECLSS / Life Support | Direct | 12.474 | 17.82 | 26.73 | Air, water, waste, atmosphere and safety systems
4 | Class 4 Feasibility | 01.06 | Payload / Mission Equipment | Direct | 9.702 | 13.86 | 20.79 | Scientific, medical, industrial or settlement payload
4 | Class 4 Feasibility | 01.07 | Robotics / Autonomous Construction | Direct | 8.316 | 11.88 | 17.82 | Robotic construction, inspection and maintenance
4 | Class 4 Feasibility | 01.08 | Launch Services | Direct | 19.405 | 27.721 | 41.581 | Launch vehicle, manifest, payload processing
4 | Class 4 Feasibility | 01.09 | Transport / Landing / Surface Logistics | Direct | 12.474 | 17.82 | 26.73 | Transit, landing, mobility and logistics chain
4 | Class 4 Feasibility | 02.01 | Test & Qualification Facilities | Indirect | 6.93 | 9.9 | 14.85 | Thermal-vac, vibration, radiation and integrated testing
4 | Class 4 Feasibility | 02.02 | Safety & Mission Assurance | Indirect | 6.93 | 9.9 | 14.85 | Quality, safety, independent review and compliance
4 | Class 4 Feasibility | 02.03 | Programme Management / PMO | Indirect | 6.93 | 9.9 | 14.85 | Controls, reporting, commercial and integration PMO
4 | Class 4 Feasibility | 03.01 | Risk Contingency / UFE | Reserve | 9.702 | 13.86 | 20.79 | Known-unknown risk allowance linked to QCRA/QSRA
4 | Class 4 Feasibility | 03.02 | Management Reserve | Reserve | 6.93 | 9.9 | 14.85 | Sponsor-held unknown-unknown reserve
5 | Class 5 Concept | 01.01 | DDT&E Engineering | Direct | 8.91 | 17.82 | 35.64 | Engineering design, mission architecture and qualification
5 | Class 5 Concept | 01.02 | Systems Engineering & Integration | Direct | 5.94 | 11.88 | 23.76 | Requirements, ICDs, verification and validation
5 | Class 5 Concept | 01.03 | Structures / Habitat Shell | Direct | 9.9 | 19.801 | 39.602 | Pressure vessels, shielding and primary structures
5 | Class 5 Concept | 01.04 | Power Generation & Distribution | Direct | 7.92 | 15.84 | 31.68 | Solar/nuclear source, grid and controls
5 | Class 5 Concept | 01.05 | ECLSS / Life Support | Direct | 8.91 | 17.82 | 35.64 | Air, water, waste, atmosphere and safety systems
5 | Class 5 Concept | 01.06 | Payload / Mission Equipment | Direct | 6.93 | 13.86 | 27.72 | Scientific, medical, industrial or settlement payload
5 | Class 5 Concept | 01.07 | Robotics / Autonomous Construction | Direct | 5.94 | 11.88 | 23.76 | Robotic construction, inspection and maintenance
5 | Class 5 Concept | 01.08 | Launch Services | Direct | 13.861 | 27.721 | 55.442 | Launch vehicle, manifest, payload processing
5 | Class 5 Concept | 01.09 | Transport / Landing / Surface Logistics | Direct | 8.91 | 17.82 | 35.64 | Transit, landing, mobility and logistics chain
5 | Class 5 Concept | 02.01 | Test & Qualification Facilities | Indirect | 4.95 | 9.9 | 19.8 | Thermal-vac, vibration, radiation and integrated testing
5 | Class 5 Concept | 02.02 | Safety & Mission Assurance | Indirect | 4.95 | 9.9 | 19.8 | Quality, safety, independent review and compliance
5 | Class 5 Concept | 02.03 | Programme Management / PMO | Indirect | 4.95 | 9.9 | 19.8 | Controls, reporting, commercial and integration PMO
5 | Class 5 Concept | 03.01 | Risk Contingency / UFE | Reserve | 6.93 | 13.86 | 27.72 | Known-unknown risk allowance linked to QCRA/QSRA
5 | Class 5 Concept | 03.02 | Management Reserve | Reserve | 4.95 | 9.9 | 19.8 | Sponsor-held unknown-unknown reserve

## 04 Risk Register
FULL RISK REGISTER — CAUSE / EVENT / IMPACT / MITIGATION / QUANTIFIED
ID | Category | Risk | Cause | Event | Impact | Owner | Mitigation | Trigger | Probability % | Cost O BN | Cost ML BN | Cost P BN | Schedule O Days | Schedule ML Days | Schedule P Days | Cost EMV BN | Schedule EMV Days | Status
R-022 | Sector | Regulatory assurance delay | Regulator or authority review cycle not fully allowed | Approval takes longer than baseline | Critical path delay and extra assurance cost | Consents Lead | Regulatory roadmap and early engagement | Submission returned | 0.44 | 1.604 | 3.564 | 8.019 | 14.8 | 37 | 85.1 | 1.984 | 20.7 | Open
R-015 | Sector | Funding / approval gate delay | Investment approvals or staged funding gates not aligned with procurement | Capital release is delayed | Procurement missed windows and schedule slippage | Sponsor | Approval roadmap and early board papers | Approval date slips | 0.49 | 1.069 | 2.376 | 5.346 | 16.8 | 42 | 96.6 | 1.473 | 26.1 | Open
R-002 | Commercial | Market escalation | Supplier market tightness, inflation, FX and long procurement window | Rates exceed assumed escalation profile | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy | Index exceeds allowance by 3% | 0.32 | 2.317 | 5.148 | 11.068 | 9.9 | 22 | 49.5 | 2.034 | 8.9 | Open
R-021 | Sector | Utilities diversion / enabling risk | Unknown utilities, access or enabling works underestimated | Enabling works expand or delay critical start | Cost growth, access delay and resequencing | Enabling Works Lead | Surveys, trial pits and early utility agreements | Unknown utilities found | 0.39 | 1.337 | 2.97 | 6.683 | 12.8 | 32 | 73.6 | 1.465 | 15.8 | Open
R-012 | Sector | Cyber / controls integration | Operational technology and control systems interfaces immature | Controls integration fails testing | Commissioning delay, resilience issue and operational risk | Systems Lead | Early cyber review, FAT/SAT plan, integration lab | Controls defect trend increases | 0.34 | 1.604 | 3.564 | 8.019 | 10.8 | 27 | 62.1 | 1.533 | 11.7 | Open
R-S02 | Technical | Mass growth | Design creep, shielding, redundancy or late payload additions increase mass | Payload mass exceeds launch and landing allowance | Launch cost, redesign, performance loss and mission safety exposure | Chief Engineer | Mass control board, margin policy, design-to-mass reviews | Mass margin below 8% | 0.31 | 1.96 | 4.356 | 9.365 | 8.1 | 18 | 40.5 | 1.668 | 7.1 | Open
R-S01 | Launch | Launch manifest delay | Launch provider capacity, weather windows, manifest priority or vehicle readiness | Confirmed launch slot moves or payload misses manifest gate | Programme delay, storage cost, resequencing and mission-readiness risk | Launch Integration Lead | Reserve alternate launch slot, freeze payload interface, maintain launch-readiness checklist | Launch slot not confirmed at L-12 months | 0.37 | 1.247 | 2.772 | 5.96 | 4.5 | 10 | 22.5 | 1.267 | 4.7 | Open
R-014 | Sector | Stakeholder change | Sponsor, operator or authority requirements evolve late | Requirements change after baseline freeze | Scope growth, redesign and approval delays | Project Director | Decision log, change board and stakeholder gates | Late decision count increases | 0.44 | 0.802 | 1.782 | 4.01 | 14.8 | 37 | 85.1 | 0.992 | 20.7 | Open
R-005 | Procurement | Supply chain delay | Long-lead equipment, constrained suppliers or late procurement release | Supplier promise dates move right | Delayed installation, critical path movement and acceleration cost | Procurement Lead | Alternate suppliers, early orders, expediting, framework options | Supplier promise date slips | 0.28 | 1.96 | 4.356 | 9.365 | 17.1 | 38 | 85.5 | 1.506 | 13.5 | Open
R-023 | Sector | Procurement strategy misalignment | Package strategy does not match market capacity or risk transfer | Tenders return above budget or fail | Retendering, cost growth and schedule slip | Commercial Lead | Market sounding and package strategy review | Low bidder response | 0.49 | 0.535 | 1.188 | 2.673 | 16.8 | 42 | 96.6 | 0.736 | 26.1 | Open
R-008 | Integration | Interface misalignment | Multiple contractors, unclear interface ownership or late design coordination | Package interfaces do not align during installation/integration | Rework, claims, delay and fragmented accountability | Integration Manager | Interface control documents, weekly interface board, accountable owners | Interface actions overdue | 0.24 | 2.317 | 5.148 | 11.068 | 2.7 | 6 | 13.5 | 1.526 | 1.8 | Open
R-020 | Sector | Design change after procurement | Procurement released before design maturity is sufficient | Vendor packages require change | Variation cost, rework and programme delay | Design Manager | Design freeze gates and change impact board | IFC maturity below gate | 0.34 | 1.069 | 2.376 | 5.346 | 10.8 | 27 | 62.1 | 1.022 | 11.7 | Open
R-S03 | Safety / Mission | Life-support reliability | ECLSS reliability, spares or redundancy evidence below target | Life-support system fails reliability growth or integrated test | Crew safety exposure, launch delay, redesign and mission abort risk | Life Support Lead | Prototype testing, redundancy, reliability growth, independent assurance | Reliability growth misses target | 0.27 | 1.604 | 3.564 | 7.663 | 6.3 | 14 | 31.5 | 1.188 | 4.8 | Open
R-011 | Sector | Quality failure / rework | Installation quality, vendor QA or inspection regime below need | Inspection failure triggers rework | Rework cost, schedule delay and confidence loss | Quality Manager | ITPs, hold points, vendor QA, right-first-time reviews | NCR trend increases | 0.29 | 1.337 | 2.97 | 6.683 | 8.8 | 22 | 50.6 | 1.09 | 8.1 | Open
R-001 | Scope | Scope growth | Ambiguous requirements, immature scope freeze and late stakeholder changes | Approved scope expands after estimate freeze | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | Project Director | Freeze scope baseline, change board, value gates, client decision log | Scope change rate exceeds 2% of package value | 0.3 | 1.247 | 2.772 | 5.96 | 13.5 | 30 | 67.5 | 1.027 | 11.4 | Open
R-006 | Delivery | Productivity underperformance | Access constraints, poor sequencing, labour scarcity or learning curve | Actual production rates underperform plan | Extended duration, increased preliminaries and loss of float | Delivery Lead | Package productivity controls, daily planning, earned value cadence | SPI/CPI deteriorates for two reporting periods | 0.25 | 1.604 | 3.564 | 7.663 | 15.3 | 34 | 76.5 | 1.1 | 10.8 | Open
R-013 | Sector | Weather / environmental disruption | Extreme weather, environmental windows or site constraints not fully allowed | Workface access or productivity is disrupted | Delay, access cost and resequencing | Construction Manager | Weather calendars, contingency workfronts, protection strategy | Weather downtime exceeds allowance | 0.39 | 0.535 | 1.188 | 2.673 | 12.8 | 32 | 73.6 | 0.586 | 15.8 | Open
R-003 | Regulatory | Permits / approvals delay | Authority process, stakeholder objections or incomplete submissions | Consent milestone slips beyond baseline | Critical path delay, extended preliminaries and potential redesign conditions | Consents Lead | Authority plan, consent tracker, early submissions, stakeholder map | Consent milestone slips by 30 days | 0.25 | 1.247 | 2.772 | 5.96 | 6.3 | 14 | 31.5 | 0.856 | 4.4 | Open
R-019 | Sector | Supply chain insolvency | Tier 2/3 financial health is unknown or weak | Critical supplier fails or cannot perform | Replacement cost, procurement delay and claims exposure | Procurement Lead | Financial checks, dual sourcing, step-in rights | Supplier credit alert | 0.29 | 0.802 | 1.782 | 4.01 | 8.8 | 22 | 50.6 | 0.654 | 8.1 | Open
R-004 | Technical | Design maturity gap | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design basis changes during detailed design | Cost growth, quantity movement, rework and schedule resequencing | Design Manager | Design maturity gates, independent review, assumption register | Design deliverables miss maturity gate | 0.27 | 0.891 | 1.98 | 4.257 | 11.7 | 26 | 58.5 | 0.66 | 8.9 | Open
R-010 | Sector | Resource availability | Labour, specialist supervisors or commissioning teams constrained | Required resources are unavailable when planned | Productivity loss, resequencing and higher preliminaries | Delivery Lead | Resource loading, framework call-offs and labour strategy | Resource histogram red flag | 0.24 | 1.069 | 2.376 | 5.346 | 6.8 | 17 | 39.1 | 0.721 | 5.2 | Open
R-017 | Sector | Data / estimate basis weakness | Estimate source data, quantities or benchmarks are incomplete | Baseline cannot be defended under challenge | Confidence reduction and rework of cost plan | Cost Lead | Assumption register, benchmark evidence, quantity validation | Unknown allowance exceeds threshold | 0.19 | 1.604 | 3.564 | 8.019 | 4.8 | 12 | 27.6 | 0.857 | 2.9 | Open
R-007 | Handover | Commissioning delay | Incomplete readiness, software integration issues or defects during testing | Systems fail tests or require repeated commissioning cycles | Delayed handover, operational readiness slippage and liquidated damages exposure | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration | Test failures trend upward | 0.23 | 0.891 | 1.98 | 4.257 | 4.5 | 10 | 22.5 | 0.562 | 2.9 | Open
R-025 | Sector | Benefits realisation risk | Commercial benefits rely on optimistic demand or ramp-up | Ramp-up underperforms plan | Revenue / value case weakens | Sponsor | Benefits model validation and ramp-up sensitivity | Demand evidence weak | 0.19 | 1.069 | 2.376 | 5.346 | 4.8 | 12 | 27.6 | 0.571 | 2.9 | Open
R-018 | Sector | Interface ownership gap | RACI and package boundaries are unclear across packages | Interface issue has no accountable owner | Delay, claims and fragmented accountability | Integration Manager | Interface control documents and owner matrix | Interface actions overdue | 0.24 | 0.535 | 1.188 | 2.673 | 6.8 | 17 | 39.1 | 0.361 | 5.2 | Open
R-009 | Sector | Commercial claims escalation | Contract ambiguity, late changes and fragmented accountability | Claims submitted above allowance | Commercial pressure, management distraction and increased outturn cost | Commercial Lead | Tight change control and dispute avoidance board | Claim volume exceeds baseline | 0.19 | 0.802 | 1.782 | 4.01 | 4.8 | 12 | 27.6 | 0.428 | 2.9 | Open
R-016 | Sector | Commissioning readiness gap | Incomplete test packs, operational readiness or training gaps | Commissioning starts without readiness | Repeated tests, handover delay and operational risk | Commissioning Lead | Readiness dashboard, integrated test plan, ORAT | Readiness score below threshold | 0.14 | 1.337 | 2.97 | 6.683 | 2.8 | 7 | 16.1 | 0.526 | 1.2 | Open
R-024 | Sector | Operational readiness shortfall | Operating model, training or maintenance strategy immature | Asset cannot enter service as planned | Delayed opening and benefit deferral | Operations Lead | ORAT/readiness plan and service transition gate | Readiness gate failed | 0.14 | 0.802 | 1.782 | 4.01 | 2.8 | 7 | 16.1 | 0.316 | 1.2 | Open

## 05 QCRA QSRA Curves
QCRA + QSRA CURVES — SEPARATE DISTRIBUTIONS
Percentile | QCRA Cost BN | QSRA Months
1 | 138.936 | 208.61
5 | 154.069 | 219.67
10 | 162.985 | 225.93
20 | 174.261 | 233.61
30 | 182.949 | 239.36
40 | 190.615 | 244.32
50 | 198 | 249
60 | 205.671 | 253.77
70 | 214.289 | 259.03
80 | 224.973 | 265.4
85 | 231.919 | 269.47
90 | 240.538 | 274.42
95 | 254.457 | 282.24
99 | 282.173 | 297.2

## 06 Tornado Drivers
TORNADO DRIVERS — QCRA COST AND QSRA SCHEDULE SEPARATED
Rank | QCRA Cost Driver | ID | Cost EMV BN | Owner | Mitigation | Rank | QSRA Schedule Driver | ID | Schedule EMV Days | Owner | Mitigation
1 | Market escalation | R-002 | 2.034 | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy | 1 | Funding / approval gate delay | R-015 | 26.1 | Sponsor | Approval roadmap and early board papers
2 | Regulatory assurance delay | R-022 | 1.984 | Consents Lead | Regulatory roadmap and early engagement | 2 | Procurement strategy misalignment | R-023 | 26.1 | Commercial Lead | Market sounding and package strategy review
3 | Mass growth | R-S02 | 1.668 | Chief Engineer | Mass control board, margin policy, design-to-mass reviews | 3 | Regulatory assurance delay | R-022 | 20.7 | Consents Lead | Regulatory roadmap and early engagement
4 | Cyber / controls integration | R-012 | 1.533 | Systems Lead | Early cyber review, FAT/SAT plan, integration lab | 4 | Stakeholder change | R-014 | 20.7 | Project Director | Decision log, change board and stakeholder gates
5 | Interface misalignment | R-008 | 1.526 | Integration Manager | Interface control documents, weekly interface board, accountable owners | 5 | Utilities diversion / enabling risk | R-021 | 15.8 | Enabling Works Lead | Surveys, trial pits and early utility agreements
6 | Supply chain delay | R-005 | 1.506 | Procurement Lead | Alternate suppliers, early orders, expediting, framework options | 6 | Weather / environmental disruption | R-013 | 15.8 | Construction Manager | Weather calendars, contingency workfronts, protection strategy
7 | Funding / approval gate delay | R-015 | 1.473 | Sponsor | Approval roadmap and early board papers | 7 | Supply chain delay | R-005 | 13.5 | Procurement Lead | Alternate suppliers, early orders, expediting, framework options
8 | Utilities diversion / enabling risk | R-021 | 1.465 | Enabling Works Lead | Surveys, trial pits and early utility agreements | 8 | Cyber / controls integration | R-012 | 11.7 | Systems Lead | Early cyber review, FAT/SAT plan, integration lab
9 | Launch manifest delay | R-S01 | 1.267 | Launch Integration Lead | Reserve alternate launch slot, freeze payload interface, maintain launch-readiness checklist | 9 | Design change after procurement | R-020 | 11.7 | Design Manager | Design freeze gates and change impact board
10 | Life-support reliability | R-S03 | 1.188 | Life Support Lead | Prototype testing, redundancy, reliability growth, independent assurance | 10 | Scope growth | R-001 | 11.4 | Project Director | Freeze scope baseline, change board, value gates, client decision log
11 | Productivity underperformance | R-006 | 1.1 | Delivery Lead | Package productivity controls, daily planning, earned value cadence | 11 | Productivity underperformance | R-006 | 10.8 | Delivery Lead | Package productivity controls, daily planning, earned value cadence
12 | Quality failure / rework | R-011 | 1.09 | Quality Manager | ITPs, hold points, vendor QA, right-first-time reviews | 12 | Market escalation | R-002 | 8.9 | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy
13 | Scope growth | R-001 | 1.027 | Project Director | Freeze scope baseline, change board, value gates, client decision log | 13 | Design maturity gap | R-004 | 8.9 | Design Manager | Design maturity gates, independent review, assumption register
14 | Design change after procurement | R-020 | 1.022 | Design Manager | Design freeze gates and change impact board | 14 | Quality failure / rework | R-011 | 8.1 | Quality Manager | ITPs, hold points, vendor QA, right-first-time reviews
15 | Stakeholder change | R-014 | 0.992 | Project Director | Decision log, change board and stakeholder gates | 15 | Supply chain insolvency | R-019 | 8.1 | Procurement Lead | Financial checks, dual sourcing, step-in rights

## 07 Schedule Levels
ALL SCHEDULE LEVELS — LEVEL 1 TO 5
Level | Activity ID | Phase | Activity | Predecessor | Duration Months | Critical | Basis
1 | M100 | Milestone | Investment approval |  | 12 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M200 | Milestone | Design complete | M100 | 50 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M300 | Milestone | Procurement complete | M200 | 37 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M400 | Milestone | Delivery complete | M300 | 100 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M500 | Milestone | Ready for operations | M400 | 37 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
1 | M600 | Milestone | Handover | M500 | 12 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1000 | Governance | Project initiation / controls setup |  | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1100 | Business Case | Strategic brief, funding and approval | A1000 | 12 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1200 | Scope | Requirements definition and scope freeze | A1100 | 12 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1300 | Design | Concept / reference architecture | A1200 | 20 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 15 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1600 | Design | Detailed design / IFC development | A1300 | 25 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1700 | Procurement | Long-lead procurement | A1500 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 17 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 55 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A2000 | Integration | Systems integration and testing | A1900 | 25 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
2 | A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 15 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1000 | Governance | Project initiation / controls setup |  | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1100 | Business Case | Strategic brief, funding and approval | A1000 | 12 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1200 | Scope | Requirements definition and scope freeze | A1100 | 12 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1300 | Design | Concept / reference architecture | A1200 | 20 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 15 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1600 | Design | Detailed design / IFC development | A1300 | 25 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1700 | Procurement | Long-lead procurement | A1500 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 17 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 55 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A2000 | Integration | Systems integration and testing | A1900 | 25 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
3 | A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 15 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1000 | Governance | Project initiation / controls setup |  | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1100 | Business Case | Strategic brief, funding and approval | A1000 | 12 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1200 | Scope | Requirements definition and scope freeze | A1100 | 12 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1300 | Design | Concept / reference architecture | A1200 | 20 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 15 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1600 | Design | Detailed design / IFC development | A1300 | 25 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1700 | Procurement | Long-lead procurement | A1500 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 17 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 55 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A2000 | Integration | Systems integration and testing | A1900 | 25 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 15 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P1000 | Package | Launch campaign | A1900 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P2000 | Package | Payload integration | P1000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P3000 | Package | Power and ECLSS | P2000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P4000 | Package | Surface logistics | P3000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P5000 | Package | Mission operations | P4000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
4 | P6000 | Package | Robotic assembly | P5000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1000 | Governance | Project initiation / controls setup |  | 7 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1100 | Business Case | Strategic brief, funding and approval | A1000 | 12 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1200 | Scope | Requirements definition and scope freeze | A1100 | 12 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1300 | Design | Concept / reference architecture | A1200 | 20 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1400 | Consents | Planning, regulatory and stakeholder approvals | A1200 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1500 | Procurement | Procurement strategy and tender packaging | A1300 | 15 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1600 | Design | Detailed design / IFC development | A1300 | 25 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1700 | Procurement | Long-lead procurement | A1500 | 22 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1800 | Enabling | Site / launch integration readiness | A1400;A1500 | 17 | No | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A1900 | Delivery | Main construction / fabrication / assembly | A1600;A1700;A1800 | 55 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A2000 | Integration | Systems integration and testing | A1900 | 25 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | A2100 | Handover | Commissioning, operations readiness and closeout | A2000 | 15 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P1000 | Package | Launch campaign | A1900 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P1100 | Activity | Launch campaign - mobilise / method | A1900 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P1200 | Activity | Launch campaign - execute works | P1100 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P1300 | Activity | Launch campaign - inspect / closeout | P1200 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P2000 | Package | Payload integration | P1000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P2100 | Activity | Payload integration - mobilise / method | P1000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P2200 | Activity | Payload integration - execute works | P2100 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P2300 | Activity | Payload integration - inspect / closeout | P2200 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P3000 | Package | Power and ECLSS | P2000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P3100 | Activity | Power and ECLSS - mobilise / method | P2000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P3200 | Activity | Power and ECLSS - execute works | P3100 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P3300 | Activity | Power and ECLSS - inspect / closeout | P3200 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P4000 | Package | Surface logistics | P3000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P4100 | Activity | Surface logistics - mobilise / method | P3000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P4200 | Activity | Surface logistics - execute works | P4100 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P4300 | Activity | Surface logistics - inspect / closeout | P4200 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P5000 | Package | Mission operations | P4000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P5100 | Activity | Mission operations - mobilise / method | P4000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P5200 | Activity | Mission operations - execute works | P5100 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P5300 | Activity | Mission operations - inspect / closeout | P5200 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P6000 | Package | Robotic assembly | P5000 | 9 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P6100 | Activity | Robotic assembly - mobilise / method | P5000 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P6200 | Activity | Robotic assembly - execute works | P6100 | 5 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.
5 | P6300 | Activity | Robotic assembly - inspect / closeout | P6200 | 2 | Yes | Duration derived from sector schedule model, selected schedule level and scenario compression/buffer logic.

## 08 Basis + Audit
BASIS, LIMITATIONS AND AUDIT
Field | Value
Scenario | Lower Risk
Project | Space Base
Subsector | Surface Habitat/Base
Location | Moon / Lunar Surface
Mode | Space
Estimate class | 3
Schedule level | 5
Generated | 2026-05-05 18:08 UTC
Model version | v56 Global Standard
Limitation | First-pass project controls intelligence. Validate against project-specific tender, survey, design and schedule evidence before capital commitment.
Methodology | Cost is parametric/benchmark/factor-based; QCRA and QSRA are separated; risks are cause-event-impact structured; scenarios change cost, schedule, risk and confidence.
Output standard | PDF/PPTX excluded from primary output pack to avoid weak or unreadable exports. Excel, schedule and audit outputs are the source of truth.