## 01 Risk Dashboard
CASEY PLATINUM RISK REGISTER
Advanced Semiconductor Fab ¦ Base scenario ¦ 18 risks
Metric | Value
Total risks | 18
Red risks | 1
Amber risks | 8
Top QCRA driver | Market escalation
Top QSRA driver | Permits / approvals delay

## 02 Full Risk Register
ID | Risk | Category | Likelihood % | Cause | Risk Event | Impact Description | Owner | Mitigation / Response | Trigger | Residual | Activity | Activity Name | CBS | CBS Name | QCRA Mean $B | QSRA Mean Days | Status
R-002 | Market escalation | Commercial | 45 | Supplier market tightness, inflation, FX and long procurement window | Market escalation occurs or materialises during delivery. | P50 cost becomes understated; commercial approvals or procurement strategy may need reset | Commercial Lead | Early procurement, index-linked allowances, market testing, FX strategy | Index exceeds allowance by 3% | Medium | A1500 | Procurement strategy and tender packaging | 01.05 | Power and resilient utilities | 0.956 | 0.1 | Open
R-004 | Design maturity gap | Technical | 38 | Estimate is based on immature design, incomplete surveys or unresolved interfaces | Design maturity gap occurs or materialises during delivery. | Cost growth, quantity movement, rework and schedule resequencing | Design Manager | Design maturity gates, independent review, assumption register | Design deliverables miss maturity gate | Medium | A1700 | Long-lead procurement | 02.02 | PMO and controls | 0.726 | 17.1 | Open
R-001 | Scope growth | Scope | 42 | Ambiguous requirements, immature scope freeze and late stakeholder changes | Scope growth occurs or materialises during delivery. | Additional quantities, redesign, rework, procurement churn and board contingency drawdown | Project Director | Freeze scope baseline, change board, value gates, client decision log | Scope change rate exceeds 2% of package value | Medium | A1400 | Planning, regulatory and stakeholder approvals | 01.04 | UPW, chemicals and specialty gases | 0.714 | 18.9 | Open
R-006 | Productivity underperformance | Delivery | 35 | Access constraints, poor sequencing, labour scarcity or learning curve | Productivity underperformance occurs or materialises during delivery. | Extended duration, increased preliminaries and loss of float | Delivery Lead | Package productivity controls, daily planning, earned value cadence | SPI/CPI deteriorates for two reporting periods | Medium | A1900 | Main construction / fabrication / assembly | 03.01 | Risk reserve | 0.595 | 17.5 | Open
R-005 | Supply chain delay | Procurement | 40 | Long-lead equipment, constrained suppliers or late procurement release | Supply chain delay occurs or materialises during delivery. | Delayed installation, critical path movement and acceleration cost | Procurement Lead | Alternate suppliers, early orders, expediting, framework options | Supplier promise date slips | Medium | A1800 | Site / launch integration readiness | 03.01 | Risk reserve | 0.595 | 16 | Open
R-008 | Interface misalignment | Integration | 34 | Multiple contractors, unclear interface ownership or late design coordination | Interface misalignment occurs or materialises during delivery. | Rework, claims, delay and fragmented accountability | Integration Manager | Interface control documents, weekly interface board, accountable owners | Interface actions overdue | Low | A2100 | Commissioning, operations readiness and closeout | 03.01 | Risk reserve | 0.506 | 11.9 | Open
R-007 | Commissioning delay | Handover | 32 | Incomplete readiness, software integration issues or defects during testing | Commissioning delay occurs or materialises during delivery. | Delayed handover, operational readiness slippage and liquidated damages exposure | Commissioning Lead | Commissioning readiness plan, early test packs, digital systems integration | Test failures trend upward | Low | A2000 | Systems integration and testing | 03.01 | Risk reserve | 0.408 | 11.2 | Open
R-003 | Permits / approvals delay | Regulatory | 35 | Authority process, stakeholder objections or incomplete submissions | Permits / approvals delay occurs or materialises during delivery. | Critical path delay, extended preliminaries and potential redesign conditions | Consents Lead | Authority plan, consent tracker, early submissions, stakeholder map | Consent milestone slips by 30 days | Low | A1600 | Detailed design / IFC development | 02.01 | Qualification and ramp-up | 0.297 | 24.5 | Open
R-013 | Weather / environmental disruption | Delivery | 46 | Extreme weather, environmental windows or site constraints not fully allowed | Workface access or productivity is disrupted | Delay, access cost and resequencing | Construction Manager | Weather calendars, contingency workfronts, protection strategy | Weather downtime exceeds allowance | Red | A1900 | Linked schedule activity | 01.03 | Linked cost package | 0.176 | 17.6 | Open
R-018 | Interface ownership gap | Delivery | 38 | RACI and package boundaries are unclear across packages | Interface issue has no accountable owner | Delay, claims and fragmented accountability | Integration Manager | Interface control documents and owner matrix | Interface actions overdue | Amber | A1600 | Linked schedule activity | 01.08 | Linked cost package | 0.145 | 12.2 | Open
R-009 | Commercial claims escalation | Delivery | 30 | Contract ambiguity, change volume and interface disputes | Claims submitted above allowance | Commercial pressure, management distraction and increased outturn cost | Commercial Lead | Tight change control, entitlement reviews, dispute avoidance board | Claim volume exceeds baseline | Amber | A1500 | Linked schedule activity | 01.10 | Linked cost package | 0.14 | 15.1 | Open
R-012 | Cyber / controls integration | Delivery | 42 | Operational technology, control systems and network interfaces immature | Controls integration fails testing | Commissioning delay, resilience issue and operational risk | Systems Lead | Early cyber review, FAT/SAT plan, integration lab | Controls defect trend increases | Amber | A1800 | Linked schedule activity | 01.02 | Linked cost package | 0.125 | 13.5 | Open
R-017 | Data / estimate basis weakness | Delivery | 34 | Estimate source data, quantities or benchmarks are incomplete | Baseline cannot be defended under challenge | Confidence reduction and rework of cost plan | Cost Lead | Assumption register, benchmark evidence, quantity validation | Unknown allowance exceeds threshold | Amber | A1500 | Linked schedule activity | 01.07 | Linked cost package | 0.101 | 21.1 | Open
R-014 | Stakeholder change | Delivery | 22 | Sponsor, operator or authority requirements evolve late | Requirements change after baseline freeze | Scope growth, redesign and approval delays | Project Director | Decision log, change board and stakeholder gates | Late decision count increases | Green | A2000 | Linked schedule activity | 01.04 | Linked cost package | 0.103 | 9.7 | Open
R-011 | Quality failure / rework | Delivery | 38 | Installation quality, vendor QA or inspection regime below need | Inspection failure triggers rework | Rework cost, schedule delay and confidence loss | Quality Manager | ITPs, hold points, vendor QA, right-first-time reviews | NCR trend increases | Amber | A1700 | Linked schedule activity | 01.01 | Linked cost package | 0.081 | 23.6 | Open
R-016 | Commissioning readiness gap | Delivery | 30 | Incomplete test packs, operational readiness or training gaps | Commissioning starts without readiness | Repeated tests, handover delay and operational risk | Commissioning Lead | Readiness dashboard, integrated test plan, early ORAT | Readiness score below threshold | Amber | A1400 | Linked schedule activity | 01.06 | Linked cost package | 0.064 | 16.9 | Open
R-010 | Resource availability | Delivery | 34 | Labour, specialist supervisors or commissioning teams constrained | Required resources are unavailable when planned | Productivity loss, resequencing and higher preliminaries | Delivery Lead | Resource loading, framework call-offs, labour strategy | Resource histogram red flag | Amber | A1600 | Linked schedule activity | 01.11 | Linked cost package | 0.043 | 19.1 | Open
R-015 | Funding / approval gate delay | Delivery | 26 | Investment approvals or staged funding gates not aligned with procurement | Capital release is delayed | Procurement missed windows and schedule slippage | Sponsor | Approval roadmap, early board papers, contingency approvals | Approval date slips | Amber | A2100 | Linked schedule activity | 01.05 | Linked cost package | 0.033 | 13.1 | Open

## 03 QCRA Tornado
Rank | Driver | CBS | Mean Cost $B | Action
1 | Market escalation | 01.05 | 0.956 | Early procurement, index-linked allowances, market testing, FX strategy
2 | Design maturity gap | 02.02 | 0.726 | Design maturity gates, independent review, assumption register
3 | Scope growth | 01.04 | 0.714 | Freeze scope baseline, change board, value gates, client decision log
4 | Productivity underperformance | 03.01 | 0.595 | Package productivity controls, daily planning, earned value cadence
5 | Supply chain delay | 03.01 | 0.595 | Alternate suppliers, early orders, expediting, framework options
6 | Interface misalignment | 03.01 | 0.506 | Interface control documents, weekly interface board, accountable owners
7 | Commissioning delay | 03.01 | 0.408 | Commissioning readiness plan, early test packs, digital systems integration
8 | Permits / approvals delay | 02.01 | 0.297 | Authority plan, consent tracker, early submissions, stakeholder map
9 | Weather / environmental disruption | 01.03 | 0.176 | Weather calendars, contingency workfronts, protection strategy
10 | Interface ownership gap | 01.08 | 0.145 | Interface control documents and owner matrix
11 | Commercial claims escalation | 01.10 | 0.14 | Tight change control, entitlement reviews, dispute avoidance board
12 | Cyber / controls integration | 01.02 | 0.125 | Early cyber review, FAT/SAT plan, integration lab

## 04 QSRA Tornado
Rank | Driver | Activity | Mean Days | Action
1 | Permits / approvals delay | A1600 | 24.5 | Authority plan, consent tracker, early submissions, stakeholder map
2 | Quality failure / rework | A1700 | 23.6 | ITPs, hold points, vendor QA, right-first-time reviews
3 | Data / estimate basis weakness | A1500 | 21.1 | Assumption register, benchmark evidence, quantity validation
4 | Resource availability | A1600 | 19.1 | Resource loading, framework call-offs, labour strategy
5 | Scope growth | A1400 | 18.9 | Freeze scope baseline, change board, value gates, client decision log
6 | Weather / environmental disruption | A1900 | 17.6 | Weather calendars, contingency workfronts, protection strategy
7 | Productivity underperformance | A1900 | 17.5 | Package productivity controls, daily planning, earned value cadence
8 | Design maturity gap | A1700 | 17.1 | Design maturity gates, independent review, assumption register
9 | Commissioning readiness gap | A1400 | 16.9 | Readiness dashboard, integrated test plan, early ORAT
10 | Supply chain delay | A1800 | 16 | Alternate suppliers, early orders, expediting, framework options
11 | Commercial claims escalation | A1500 | 15.1 | Tight change control, entitlement reviews, dispute avoidance board
12 | Cyber / controls integration | A1800 | 13.5 | Early cyber review, FAT/SAT plan, integration lab